O-E-13
O-E-13 transition plans
Vera Hansper, CSC/NDGF, Finland

---
POLE2 cf. O-E-13
O-E-13:
definition of best practices, operations procedures,	operations requirements.
Current status:
- Pole2: Operational procedure documentation, Best current practices and training guides for operations
- Pole2 Task Leader and coordinator: Vera Hansper (CSC/NDGF, Finland)
- Supervising coordinator : Helene Cordier (IN2P3, France)
- Current task (POLE2) maps well to that of O-E-13

---
Transition plan for transfer of duties from France to Finland.
- Establish contact with previous coordinators of grid operations and other actors in this area.
  - In practice this is already taking place. Unknown players may still need to be identified. In particular, this will involve persons who will actively contribute to the task.
- Further establish contact with co-ordinators of corresponding tools and tasks. (O-E-1, O-E-4,5,6,7)
- Encourage participation of NGIs, particularly current operations team members.
  - Their experience in invaluable as input for the further development of operational procedures.
- Envisage that O-N-5, O-N-6 and O-N-7 operations staff will have suitable skills.
  - Put forward a call to these National task bodies to contribute to the project.

---
Transition status
In progress
- Good dialogue between current POLE tasks supervisor and future coordinator.
- Dialogue already established between O-E-4, O-E-5 and O-E-13.
  - Further contact between O-E-13 and O-E-6,7 still required.
- Concerns
  - Lack of clear commitment by NGIs to contribute to the work required.
    - Should this be enforced?