## Slide 1: WP CO Status and Progress December 8th, 2010 Johannes Gutleber
R. Gutleber

## Slide 2: Status Report

## Slide 3: Current Phase (Elaboration)
Focus on requirements, architecture, design
Prototype implementation and technology evaluation
Prepare development setup

## Slide 4: Goals for 2010 (Reminder)
Complete architecture and implementing first components
Complete and MTS design and demo core functionality
Complete PCC design and demo core functionality
Make PCO FED ready for production
Elaborate ProShell design and API skeleton
Demonstrate use of RMS, database filler, PVSS filler
Have development infrastructure (HW, SW) operational

## Slide 5: Achievements for 2010
Complete architecture and implementing first components
Complete and MTS design and demo core functionality
Complete PCC design and demo core functionality
Make PCO FED ready for production
Elaborate ProShell design and API skeleton
Demonstrate use of RMS, database filler, PVSS filler
Have development infrastructure (HW, SW) operational

## Slide 6: Additional Achievements!
FECOS documented and ready for pre-release
Virtual Accelerator Allocator first iteration completed
requirements, design, implementation

## Slide 7: Original Plan (Dec. 14, 2009)
JAN
FEB
MAR
APR
MAY
JUN
JUL
AUG
SEP
OCT
NOV
DEC
Framework Agreement
T4 framework definition
PC Interface Def./Impl.
MTS Definition
MTS Functional Product Development
PCC Def.
Procedure Fw Definition
PCC Functional Product Development
Procedure Fw Skeleton Development
Column
Demo
1 SW Eng.
1 engineer,
Junior
partner
5 FTE
Contractor
Interface Prod.
T4 framework development
Repo Sw. Adoption
Repo Sw. Package 1
Repo Sw. Package 2
Repo Sw.
Power Converter Interface Recommendation
Tech. Eval.
Beam Interlock System Specification and Development

## Slide 8: Actual Plan (Dec. 8, 2010)
JAN
FEB
MAR
APR
MAY
JUN
JUL
AUG
SEP
OCT
NOV
DEC
Framework Agreement
T4 framework definition
PC Interface Def./Impl.
MTS Definition
MTS Functional Product Development
PCC Def.
Procedure Fw Definition
PCC Functional Product Development
Procedure Fw Skeleton Development
Column
Demo
1 SW Eng.
1 engineer,
Junior
partner
5 FTE
Contractor
Interface Definition
T4 framework development
Repo Sw. Adoption
Repo Sw. Package 1
Repo Sw. Package 2
Repo Sw.
Power Converter Interface Recommendation
Tech. Eval.
Beam Interlock System Specification and Development
Production
PCC Def.
PCC Functional Product Development
Procedure Fw Definition
Development
Repo Sw. Adoption
Repo Sw. Package 1
RMS not available
On Hold

## Slide 9: Status of Work with Other WPs
WP/Subsystem | Requirements | Design | Implementation | Integration
Power |  |  |  | 
BTS |  |  |  | 
Vacuum |  |  |  | 
Injector RF |  |  |  | 
Synchrotron RF |  |  |  | 
BDI |  |  |  | 
BID |  |  |  | 
Magnets |  |  |  | 
Sources |  |  |  | 
MSS |  |  |  | 
BDS |  |  |  | 
Building |  |  |  | 
IT |  |  |  | 

## Slide 10: MACS Column 2010

## Slide 11: Column Overview
Functional vertical cut through the control system architecture for
  confirming technology choices
  Refining the design
  Improving project cost/time estimate
  Providing users with a working infrastructure skeleton
To be replicated for each subsystem
Leads to a scalable system
  In terms of performance
  In terms of management
Presentation tier (1)
Processing tier (2)
Equipment tier (3)
Frontend tier (4)

## Slide 13: Technical Work for 2011
Continuous integration of MACS column
Finalize development of MTS and PCC
Finalize VAA, dummy BDS and operation chain
Develop & integrate ion source slow control FEC
Develop & integrate injector LLRF FEC
SADS development
CRB integration related work
Integrate family A PCOs into PCC
Vacuum controls technology validation

## Slide 14: Technical Work for 2011 (contd.)
RMS importer, management, exporter chain
Fill RMS with first devices and cycle data
ProShell minimal framework release to users
Beam Interlock System technology validation
Finalization of IT infrastructure definition
Functional integration of control system for ITS

## Slide 15: Support Work
Configuration Management
  Followup of tickets
  Extension of Trac/SVN system
  Training of MA team and supervision of environment
Maintenance of development infrastructure
  Hardware and software administration, scale-up, evaluation
Interaction with WPs
  Interactions with WPs at CERN and Austria
  Interactions with WP suppliers and AE
Risk Management
  Accelerator control system risk analysis (not medical device!)

## Slide 16: Summary and outlook

## Slide 17: Summary
Behind Schedule
  ProShell development
  Finalization of requirements (Linac, SADS, Sources)
  Beam Interlock System development (risk analysis)
  Use of RMS (device specification, filling of database)
Ahead of Time
  FECOS development and provision
  Supervisory Control System architecture/design
  VAA development
In Time
  Development of timing system
  Development of power converter controller
  RMS adaption to MedAustron needs