## Slide 1: CERN BGC updates
Gerhard Schneider and Giannis Papazoglou,
12 March 2021

## Slide 2: Bellows up-date
Bellows company Skodoc finally not bankrupt but communication is difficult – still no delivery date but working on it
Alternative options:
  Flexomat similar bellows proposed some modifications needed, price unknown yet
  Astroflex very close to what we have, 2.000-euro fixed cost and then about 450-euro per bellow.

## Slide 3: V4 Avancement
Agreed that we will have a bellows on either side of the BGC V4
Disagreement without advacement: Space availability for BGC  need to escalde the issue
TPM need shielding
~50 mT field
Assembly not possible

## Slide 4: Limitations on V4 design
Magnet spacers increased on diameter

## Slide 5: Limitations on V4 design
Magnetic field mapping creates problems with the TMPs placement
5 mT
50 mT

## Slide 6: New Vantablack test pieces
New test piece proposed by Chiara
Price about 5.000 euro only the coating

## Slide 7: 2nd Copper liner to CI
Test the complete assembly if we send it
The α-C should not be exposed to air for long time
Additional cost for shipping the 1m long tube + tolls costs to UK

## Slide 8: Next meeting:
Review general action list
Review HEL test stand action list
Up-date on V4 mock-up
Advancement on V4 space conflict