## Slide 1: BGC on the HEL test stand (EBTS)
Gerhard Schneider, Giannis Papazoglou, Ray Veness
Based on Ray’s presentation on December 10th 2020 to collaboration meeting
BGC regular meeting 26.03.2021
Let’s get going 

## Slide 2: Content
List of Hardware needed to the last detail
Identify documentation, personal, safety and training requirements
Cockcroft delivery
BGC tests foreseen in EBTS

## Slide 3: Hardware List – start of this list, please give me you input
Start point: We assume the whole BGC will be delivered to CERN from CI as operated in CI including cables, controllers and whatever you need to have an operational BGC as in CI. This is also including full documentation of the hardware. Can we formally agree on this?
BGC EBTS support  To be done
Identify racks, cables (what distances? Do they need to be secured e.g. anybody rolling with a forklift on them? Overhead cabling? Foreseen rack power sufficient…?
What computing and network requirements exist?
Change from UK to Swiss plugs – where do we foresee issues other than the power plugs?
Space requirements: Is there enough space for primary pumps, do we need PCs?, will they be affected by magnetic fields

## Slide 4: Identify operational, personal, safety and training requirements
Full documentation of the operational aspects of running and servicing the BGC
Any formal preparation work in Covid times when coming from the UK to CERN?
The build access: Which trainings need to be followed?
Job environment: Magnetic fields, electrical hasards, other?
Personal Protection: Safety shoes, others?

## Slide 5: Cockcroft Delivery
Anything to be respected for a scientific instrument delivery in post-Brexit times  Who can consult?
Fully tested BGC delivery
Performance tests made with Neon, Nitrogen (and Argon?)
 Looking forward to see detailed test plan with dates at CI
Make estimation what and how long it takes to mount the BGC on the EBTS, what are the resources needed? Overhead crane?

## Slide 6: BGC tests foreseen in EBTS (List from Ray as from 10th December)
Description | Estimated Duration (d) | Operational requirements | Personnel / comments
Validation of the instrument |  |  | 
General operational tests and optimization for the environment | 10 | Passive | Operator, CI expert,
Testing of the CERN control system | 10 | Passive | Operator, VSC, CI expert,
Field mapping of the HEL stray field | 2 | Dedicated | Technician, Engineer,
Operating modes with the pulsed e- beam (gas pulsing?) | 5 | Dedicated | Operator, CI expert
SR background from the e-gun | 5 | Passive | Operator, physicist, GSI,
Gas transport in the HEL vacuum system | 5 | Dedicated | VSC,
Vacuum system performance in the stray magnetic fields | 3 | Passive | Engineer, VSC,
Electron-specific tests |  |  | 
Estimation of fluorescence cross-section for e- | 5 | Dedicated | Physicist, GSI, CI expert
Electron trapping study | 5 | Dedicated | Experiment design needed
Ionised gas transport in the HEL? | 3 | Dedicated | Experiment design needed
Neutral and ionized emission lines (N vs. Ne), effect of distortion or focussing | 10 | Passive | GSI, physicist, CI expert
Design improvement tests |  |  | 
Possible improvements to SR background | 15 | Dedicated | Marton, physicist, engineer, technician
Using N2 and NEG cartridges | 15 | Passive | VSC, engineer, operator, CI expert,

## Slide 7: BGC on EBTS
Integrate the BGC on EBTS
Repeat test and assure vacuum/gas curtain performance of BGC on EBTS  Should get a copy/paste of the results of CI results with EBTS “off”, no magnetic field and E-beam
Validation of the BGC on the EBTS with magnetic field and with E-beam
Design improvement tests
Work towards handover of LHC beam vacuum operational system with TE-VSC

## Slide 8: Next Steps
Please give me your input by April 7th
  Missing infrastructure, training, dates….
  Tests to be made
Assign names and dates to test to be performed
Assure action on all identified issues

## Slide 9: End
BGC regular meeting 26.03.2021