## Slide 2: 11T QA QC
R. Principe,
C-MAC Review, Mar-1, 2021
EDMS 2492001

## Slide 3: Motivation
A QMS for the 11T project in the production phase:
  Have a global view of the project;
  Understand who does what and when;
  To be sure 11T will be in time for components, materials, tooling (purchase, storage, conformity of the components at the delivery, availability at T0);
  Cover the entire production chain:
      Identify all production steps (tasks);
      Define clear interfaces.
  Have competent personnel on a specific task;
  Profit of the LS1 experience;
  Focus on production.

## Slide 4: Method
Identify all production steps and precise interfaces:
  Flow charts;
  Comprehensive manufacturing procedures;
  Control procedures;
  MIPs, follow-up files and check-lists;
  NB1: iterative process;
  NB2: from production to general procedures = provide clear work instruction first.
Traceability:
  Non conformities (Root Causes Analysis);
  Record of the working methods;
  Identify the tools: EDMS, MTF, EAN.
Competence:
  Documental corpus as a tool for training;
  Personnel (Skill Matrix).

## Slide 5: Manufacturing flow charts
YACA method;
Identify the task;
Reference to:
  Fabrication procedure
  Control procedure
  MIP;
  Execution team.

## Slide 7: Manufacturing procedures

## Slide 8: Control procedures

## Slide 9: Annotated procedures

## Slide 10: Manufacturing and Inspection Plan (MIP)

## Slide 11: Follow up files and check lists

## Slide 12: EDMS AND MTF
LMF QA web page:
  https://te-dep-msc-lmf.web.cern.ch
EDMS = Equipment Data and Management System (EDMS)
  Structure by Project
  All documents produced by TE-MSC in EDMS is mirrored in the EDMS HL-LHC structure
Manufacturing and Test Folder (MTF)
  Structure by Object

## Slide 14: Non-conformities

## Slide 15: Statistics and “deverminage” sessions

## Slide 16: NC Impact
EDMS Criticality | NC Type | Impact (X)
Critical | Level 5 Extreme | X > 1 MCHF or 6 months
Critical | Level 4 Major | X < 1 MCHF or 3 months
Critical | Level 3 Moderate | X < 100 kCHF or 1 month
Non Critical | Level 2 Minor | X < 10 kCHF or 1 week
Non Critical | Level 1 Negligible | X < 1 kCHF or 1 day

## Slide 17: Non Conformity Report (NCR)
Open a NC = provide a NCR
  Description (essential info)
  Decision (Action Plan)
  Root Cause Analysis required for a CRITICAL NC (LEVEL 3, 4 or 5)
  Closure (after implementation of the Action Plan)

## Slide 18: Root Cause Analysis (RCA)

## Slide 20: Skill matrix
S197 coil production;
Personnel experience per production step:
Team (at
  To be trained;
  In training;
  Autonomous;
  Expert-trainer.
  Team: at least one level 3 or 4, not more than 2 level 1 or 2.

## Slide 21: Sharing experience
Documental corpus as a tool for training (weekly in field);
QA meeting WP3-WP11 (weekly);
Dedicated sessions QXF-11T (in 2020):
  Coiling 11T (MON @ EDMS 2393474);
  Reaction MQXFB (EDMS 2399369);
  Splicing 11T (EDMS 2407230);
  Quality Controls (EDMS 2414703).
  Other local exchanges.