## Slide 2
Feedback on ISTs - Coordination Viewpoint
A. Apollonio, M. Solfaroli
03/03/2021

## Slide 3
3
Main message: 1 week dedicated to QDS.IST was VERY effective:
It allowed resolving issues on the QDS side without impacting Phase 1 of the powering tests, optimizing test time and releasing the pressure on the QDS team
Overall, the debugging during Phase 1 was much smoother than in the post-LS1 campaign
Some remarks/lessons learned:
Need to carefully synchronize QH discharges with activities in the tunnel to avoid exposing people to potential electrical hazards. Communication and synchronization improved over the first weeks
Carefully plan the EE ISTs to synchronize with consignation/deconsignation of 600A circuits
QDS.IST – Success!

## Slide 4
4
Additional points for improvement, not strictly related to ISTs:
It is important that interventions on short notice are timely communicated to the coordination team to avoid abruptly interrupting running tests. In most of the cases 30 min-1 h notice would be sufficient
Clarify strategy for test signature:
  Concentrate signatures in MP3 for all tests (e.g. providing expert tools for EE, QDS integrity, etc.)
  Delegate signatures to experts (EE, QDS, etc.)
  In any case, agree in advance signature responsibilities in order to avoid lengthy discussions which block test execution (e.g. MP3 signatures for PIC1, QDS.integrity after successful PCC, etc.)
Additional considerations