## Slide 2: LIU PS Transverse Feedback IST
D. Glenat, W. Höfle, G. Kotzian, R. Louwerse, P. Solvang
Acknowledgements:
D. Landre, K. Marecaux, J. C. Oliveira

## Slide 3: IST tests of PS Transverse feedback
The LIU upgrade of the PS TFB consists of an upgrade of the power system to 5 kW per electrode to cope with the increased beam energy at injection from 1.4 GeV to 2 GeV;
The power of 32 individual RF amplifiers of 800 W is combined to provide 5 kW to each of the four kicker plates installed in the tank in SS97
The power system is installed in building 355/R-009
SS97 Kicker tank
355/R-017 LLRF
355/R-009, new power system

## Slide 4: 5kW RF amplifier power per electrode (x4)
5 kW amplifier set-up

## Slide 5: Planned activities for IST
Test PLC control, interlocks and cooling
RF power tests with and without kickers
Necessary conditions:
  Cooling water
  Electricity in 355
  Vacuum in SS97
PLC rack and HMI display
Water cooling circuits 355/R009

## Slide 6: Activities performed during IST
Water cooling
  ΔT ≈ 9.6 °C, @4.3 l/min for each of the 4 branches, amplifiers in standby with bias current
PLC controls
  Debugging
RF power tests without kickers
  Measurements of 32x 4 W amplifiers
    Gain variation corrected by Reinier
  Measurements of 32x 800 W amplifiers
RF power test with kickers
  Frequency domain measurements of full path on 1 electrode
  Time domain measurements of full path on all 4 electrodes

## Slide 7: Frequency response 4 W + 800 W amplifiers

## Slide 8: Group delay measurements

## Slide 9: Bottom electrode frequency domain measurements

## Slide 10: Bottom electrode time domain measurements

## Slide 11: Unresolved
Heat in impedance matching transformers and protection
PLC and HMI panel: Still some bugs
Impedance matching between 4 W and 800 W amps
Additional amplification between LLRF and power system
Variation of delay and phase with frequency
Water cooling: Protection against insufficient flow
  Flow meters: Remote output limited to 4 l/min, display  5 l/min
  Flow switches: Erratic behavior due to suspended impurity in water Replace?
Flow meters
Flow switch
Impedance matching transformer, 50 MHz full power

## Slide 12: Plan for next IST
Ahead of IST
  Improve matching between 4 W and 800 W amplifiers
  Investigate 2 deviating 800 W amplifiers
  Investigate heat in impedance matching transformer. Measurements in lab. Proposal for protection.
Verification of final patch cables installed after last IST with power
Verification of cable lengths to tunnel in search of delay variation
Verification of measurement results
Verification of PLC interlocks after update of software
Remaining measurements
Further investigate ripple in phase and delay. Faulty connector?
Determine the need for alternative interlock for the water-cooling circuit
  Effect of new water filter

## Slide 13: Conclusion
Water cooling is sufficient to cool the 800 W amplifiers
Interlock and flow measurement needs to be addressed
PLC controls needs to be updated and re-checked
Gain of 4 W driver amplifiers are satisfactory after equalization
The system can deliver 5 kW of rf power
  Maximum frequency limited by digital part to below 40 MHz
Unforeseen issues require additional expenditure

## Slide 15: 5kW RF amplifier power per electrode (x4)
Amplifier Rack 1
Amplifier Rack 2
230 V / 400 V
Demineralized Water 1.25 l/min
Demineralized Water 1.25 l/min
RF ON
RF OFF
PLC Remote Control

## Slide 16: Hardware in tunnel
Kickers
Combined function impedance transformer and combiner
  combines 2 x 2.5 kW
  input impedances 50 W
  output impedance 100 W
  maximum power handling is frequency dependent
full power tests only when tank is under vacuum (feedthrough breakthrough limit unknown)
125 W cable to connect to kicker
  power and voltage limit

## Slide 17: Improvements required 1st look
water filter (Y-type) with 200 um ordered
  waiting for CV, also waiting for answer to a question concerning filtering of the circuit
  manufacturer says filter needs to be 200 um
  hysteresis of interlock switch
replacement of flow switches by new system including individual temperature measurement in each branch?
matching 4 W / 800 W
temperature interlock combiners in tunnel
PLC
Clean-up and next IST, when?

## Slide 18: 3rd order intercept measurement 800 W amplifiers

## Slide 19: 3rd order intercept measurement 4 W amplifiers

## Slide 20: Group delay bottom electrode

## Slide 21: Frequency response 4 W amplifiers

## Slide 22: Power sweep 4 W amplifiers

## Slide 23: Power sweep 800 W amplifiers

## Slide 24: Amplifier BOTTOM 1 (2.5 kW line)
CH3 (blue) – Voltage envelope 1.2872 kVpp  4 kW in 50 Ohms (>2.5 kW)
CH5 (gray) – DC current of one 800W amplifier: 62.10 A peak, 51 A steady state
Similar performance on all amplifiers