## Slide 1: Status on HFM Collaboration with CIEMAT
JC. Perez
May 4th 2021

## Slide 2: Collaboration agreements
2 collaboration agreements signed in March 2019 (PRISMAC)
  Series of magnets for HL-LHC based on NbTi technology (KE3797/TE/HL-LHC)
  The construction of a high field superconducting magnet laboratory at CIEMAT and the contribution to the high field FCC magnet prototypes (KE39207/TE)
Contributions closely related
  Part of a single strategy starting on the development of state of the art existing technology currently available (short term HL-LHC)
  Continue with the exploration on new concepts, technology, materials, processes and first prototypes for HFM

## Slide 3: Agreement KE39207/TE
3 work units (CERN contact: D. Tommasini)
  Magnet Laboratory at CIEMAT
  Manufacturing and assembly of eRMC and RMM magnets
  Manufacturing of a CIEMAT FCC-hh short dipole model magnet
I was asked to be the CERN work unit contact as TE-MSC Magnet expert
D. Schoerling was asked to cover the short model magnet development
Small team of CEMAT’s engineers involved in both agreements

## Slide 4: Building construction for Magnet Laboratory at CIEMAT
The tendering is launched: somme delays due to administrative issues
Contract award and signature expected in September 2021
Construction phase will take around 9 months
Installation of first pieces of hardware can start in summer 2022
This delay is driving schedule and priorities when ordering the components to be provided by CERN

## Slide 5: Status on tooling to be provided by CERN
Collaring & Curing presses
  We foresee to build only 1 press covering curing and collaring operation
  Press design and mechanical calculation for the structure completed
  Technical specification ready and sent to CIEMAT for comments
  We are ready to launch the DR and start the market survey
  The press can be ready for installation and commisioning at CIEMAT’s premisies Q2-2022
Reaction Furnace
  Technical specification ready and sent to CIEMAT for comments
  Ready to launch the DR and start the market survey
  The oven can be ready for installation and commisioning at CIEMAT’s premisies Q2-2022
Pressurized impregnation system for model magnets
  We forese to build an impregnation system inspired from the existing installation at CEDEX
  Waiting for expirience gained during MCBXF coils production in industry to finalise the design
  Impregnation system coul be ready by summer 2022
Magnetic measurement system
  Support table being designed for MCBXF measurements in industry. The final design will be adapted for CIEMAT laboratory
  Magnetic shaft and mechanics to be produced (around 6 months)
  New electronics to be develop and build as components used for existing benches are obselete
  Around one year will be required to get an WMM system installed and operational at CIEMAT

## Slide 6: Manufacturing and assembly of eRMC and RMM magnets
Detailled planning to be discussed and agreed
CIEMAT team 100% loaded with MCBXF prototype magnets construction
Last MCBXFA orbit corrector to be completed by end of 2021
The same team will be involved in HFM activities at CIEMAT
The fabrication of a small SMC coil could be a good first step to master Nb3Sn technology (as agreed for CERN-CEA collaboration)
Sharing of existing magnet mechanical structures at CERN has been considered to speed-up strarting of HFM R&D activities at CIEMAT

## Slide 7: Manufacturing of a CIEMAT FCC-hh short dipole model magnet
A rescoping of the initial plan may be required
Detailled activities to be agreed as some design work could start during second half of 2021
Informal discussions launched with F. Toral during 2020
Existing common coil configuration accelerator-quality magnet designed within EuroCircol to reach 16 T may be tunned to 12-14 T
Could “React and Wind” technology be considered?
Get CIEMAT’s crew involved in SMC second generation activities at CERN?