## Slide 1
Third ARIEL Management Board and PAC meeting
Arnd Junghans, Helmholtz-Zentrum Dresden-Rossendorf
This project has received funding from the Euratom research and
training programme 2014-2018 under grant agreement No 847594 (ARIEL).
www.ariel-h2020.eu
Accelerator and Research reactor Infrastructures for
Education and Learning
ARIEL
Notes: 1

## Slide 2
Agenda 1
Wednesday, May 19:
Management board meeting:
9h00 Status of ARIEL project
Experiments (R. Nolte) Education and Training (H. Pentillä) Schools (C. Guerrero)
Scientific workshop (A. Plompen) Project status and Deliverables (A. Junghans) a.o.b.
12h30 end of Management board meeting

## Slide 3
Agenda 2
Wednesday, May 19:
https://cern.zoom.us/j/62251997301?pwd=QlRsTGNHZk9TVC9CeTM3MjNtZXpnQT09
PAC meeting:
14h30 Evaluation of “Acess to neutron beam facilties and Education and Training of early stage researchers / scientific visits” proposals
16h00 Decision on all applications
16h30 A.O.B. Summary/Comments of PAC members
17h30 End of meeting

## Slide 4
ARIEL amendment
Travel budget reallocation to all partners
CNRS budget transfer from D.5 (not justifiable for CNRS) to (A) as person months for beam line scientist work with external users
Two new partners IRSN and UMCG to the consortium
Re-allocation of D.5 to give budget to new partners
Extension of 6 months to mitigate travel restrictions due to COVID-19 epidemic additional Covid mitigation measures
Change of reporting periods due to extension to: 18-18-18
CA is still under preparation.
ILL subcontracting: Draft for contract (HZDR) has been made and sent to ILL
18 month reporting not yet concluded.

## Slide 5: List of approved E&T proposals from PAC 1
PAC 1 | Visitor | Institute | Contact | Requested weeks | Approved weeks | Total cost
SV_1_1 | Miguel Astrain Etxezarreta | HZDR | Andreas Wagner | 25 | 25 | 6300
SV_1_2 | Ana Maria Gomez | JRC-Geel | Stephan Oberstedt | 12 | 12 | 13000
SV_1_3 | Diego Tarrio | JRC-Geel | Stephan Oberstedt | 4 | 4 | 5000
SV_1_4 | Ali Al-Adili | JRC-Geel | Stephan Oberstedt | 4 | 4 | 5000
SV_1_5 | Jukka Jaatinen | JGU Mainz | Klaus Eberhardt | 2 | 2 | 2500
SV_1_6 | Juan Peñas | HZDR | Arnd Junghans | 4 | 4 | 4800
Total |  |  |  | 51 | 51 | 36600
SV_1_1 completed, all others delayed not canceled

## Slide 6: List of approved E&T proposals from PAC 2
SV_2_5 completed, SV_2_8 started, all others delayed but not canceled
PAC | Visitor | Institute | Contact | Requested weeks | Approved weeks | Total cost
SV_2_1 | Nicolae Carjan | JRC Geel | Stephan Oberstedt | 12 | 6 | 6700
SV_2_2 | Andrea Oprea | JRC-Geel | Peter Schillebeeckx | 12 | 8 | 8800
SV_2_3 (?) | Ahmed Shama (canceled) | JRC-Geel | Peter Schillebeeckx | 12 | 6 | 6700
SV_2_4 | David Knezevic | MTA, Budapest | László Szentmiklósi | 3 | 3 | 3550
SV_2_5 | Quentin Ducasse | PTB, Braunschweig | Elisa Pirovano | 3 | 3 | 3550
SV_2_6 | Riccardo Mucciola | JRC Geel | Peter Schillebeeckx | 12 | 9 | 9850
SV_2_7 | Eckart Grosse | IPN Orsay | Jon Wilson | 4 | 4 | 5000
SV_2_8 | María Ángeles Millán Callado | HZDR | Arnd Junghans | 12 | 11 | 11950
Total |  |  |  | 70 | 50 | 56100

## Slide 7: List of experiments from PAC 1
PAC 1 | Spokesperson | Institute | Facility | Contact | Approved hours
TAA_1_2 | Michal Kostal | CVR Rez | PTB | Ralf Nolte | 64
TAA_1_3 | Gregory Lehaut | LPC Caen | nELBE | Roland Beyer | 168
TAA_1_4 | Massimo Nocente | U of Milano-Biococca | HISPANOS | Carlos Guerrero | 60
TAA_1_5 | Alberto Boso | NPL | CVR | Michal Kostal | 1
TAA_1_6 | Alix Sardet | CEA | PTB | Ralf Nolte | 90
TOTAL |  |  |  |  | 1331.00
TAA_1_2, TAA_1_6 at PTB completed. All other experiments have been postponed due to the current situation

## Slide 8: List of experiments from PAC 2
All experiments have been postponed due to the current situation
PAC | Spokesperson | Institute | Facility | Contact | Approved hours
TAA_2_2 | Greg Henning | IPHC Strasbourg | IFIN-HH | Tiberiu Sava | 168
TAA_2_3 | Stephan Pomp | Uppsala Univ. | JYU | Heikki Penttilä | 104
TAA_2_4 | Markus Nyman | JRC Geel | ELBE | Arnd Junghans | 100
TOTAL |  |  |  |  | 372

## Slide 9: Proposals for this PAC 3
PAC | Visitor | Institute | Contact | Requested weeks | Approved weeks | Total cost
SV_3_1 | Pablo Perez Maroto | n_TOF(CERN) | Alberto Mengoni | 12 | 0 | 13000
Total |  |  |  | 12 | 0 | 13000
PAC | Spokesperson | Institute | Facility | Contact | Requested hours | Unit cost | Facility Cost | Requested user support
TAA_3_1 | Benedikt Bergmann | IEAP CTU | n_TOF | E. Chiaveri | 56 | 273 | 15288 | 4800
TAA_3_2 | Alexander Prokofiev | Uppsala Univ. | NFS | Xavier Ledoux | 136 | 400 | 54400 | 6400
TAA_3_3 | Imre Pazsit | Chalmers Inst. Tech. | BR1 SCK CEN | Jan Wagemans | 24 | 350 | 8400 | 750
TAA_3_4 | Ali Al-Adili | Uppsala Univ. | ILL | Ulli Koester | 144 | 0 | 0 | 5800
TOTAL |  |  |  |  | 360.00 |  | 78088.00 | 17750.00

## Slide 10
Summer schools
Hands-on school on the production, detection and use of neutron beams, University of Seville (18-24 participants) September 2022
Lab course in Reactor Operation and Nuclear Chemistry, University of Mainz (10 participants) October 2023
Nuclear data: the path from the detector to the reactor calculation, CIEMAT, Madrid (20 participants) Jan /Feb 2022 (virtual course)
EXTEND’2023 summer school at Uppsala University (20-25 participants) June 2023
Notes: Summer schools will have up to 80 participants to attract new students to the field.
Organisation will be done by the hosting institutes with advise and help from the PAC and ENEN
10

## Slide 11: Scientific meetings
Month 26 October 2021 First Progress meeting JRC (Virtual meeting ?)
Month 38 October 2022 Second progress meeting NPL (new contact: Michael Bunce)
Month 51 November 2023 Final meeting IPN Orsay

## Slide 12
Unit cost estimate for Transnational Access
Transnational Access to ILL will be subcontracted to HZDR. ILL will participate in all activities.
The ILL unit cost depends on the origin of the experimen-ters. If all users are from ILL asscociated or member countries no beam time cost will occur

## Slide 13
Budget available for each PAC meeting
Support budget: |  | Total for ARIEL (€)
User support for experiments |  | 203 000.00
Facility support |  | 640 450.00
Education & Training budget |  | 264 000.00
35 typical experiments of 5800 € each (4 user , 7days, 150 € per diem, 400 € travel)
30 scientific visits of typically 8 weeks
Budget per meeting:
29 000 € user support (20 users, 4 early stage researcher or 2 scientists)
91 500 € beam time (430 beam time hours, 5 experiments)
37 700 € E & T (34 weeks of scientific visits)

## Slide 14: End of presentation

## Slide 16
Date ordered List of Deliverables 1
Deliverable (number) | Deliverable name | Work package number | Short name of lead participant | Type | Dissemination level | Delivery date
D5.1 | presentation of the kick off meeting | 5 | HZDR | R | PU | 1
D5.2 | project website | 5 | HZDR | DEC | PU | 2
D2.1 | Minutes of PAC 1 meeting | 2 | JRC | R | PP | 3
D5.3 | Communication Action Plan | 5 | HZDR | R | PU | 3
D6.1 | EPQ-Requirement No.1 | 6 | HZDR | ETHICS | Confidential (only for members of the consortium including commission services) | 3
D5.4 | project presentation, leaflet and poster | 5 | HZDR | R | PU | 4
D1.1 | Report on Terms of Reference and PAC composition | 1 | HZDR | R | PU | 5
D5.5 | Data Management Plan | 5 | HZDR | R | PU | 5
D5.6 | report on the summer school in Seville | 5 | USE | R | PU | 7
D2.2 | Minutes of PAC 2 meeting | 2 | JRC | R | PP | 9

## Slide 17
Date ordered List of Deliverables 2
Deliverable (number) | Deliverable name | Work package number | Short name of lead participant | Type | Dissemination level | Delivery date
D5.8 | report on the course on reactor operation and radiochemistry at University of Mainz | 5 | JGU | R | PU | 13
D5.7 | presentations of the first progress meeting | 5 | JRC | R | PU | 14
D2.3 | Minutes of PAC 3 meeting | 2 | JRC | R | PP | 15
D2.4 | Minutes of PAC 4 meeting | 2 | JRC | R | PP | 21
D3.1 | First User status report | 3 | PTB | R | PU | 24
D4.1 | First training status report | 4 | JYU | R | PU | 24
D5.11 | report on the nuclear data school at CIEMAT, Madrid | 5 | CIEMAT | R | PU | 25
D5.9 | presentations of the second progress meeting and scientific workshop | 5 | NPL | R | PU | 26
D2.5 | Minutes of PAC 5 meeting | 2 | JRC | R | PP | 27
D2.6 | Minutes of PAC 6 meeting | 2 | JRC | R | PP | 33
D5.10 | report on the EXTEND summer school at Uppsala University | 5 | UU | R | PU | 37
D2.7 | Minutes of PAC 7 meeting | 2 | JRC | R | PP | 39
D5.12 | presentations of the final scientific workshop | 5 | IPNO | R | PU | 46
D3.2 | Second User Status report | 3 | PTB | R | PU | 48
D3.3 | Experimental Results | 3 | PTB | OTHER | PU | 48
D4.2 | Second training status report | 4 | JYU | R | PU | 48
D4.3 | Results from training activities | 4 | JYU | OTHER | PU | 48

## Slide 18: Deliverables under preparation
D5.3 | Communication Action Plan
D6.1 | EPQ-Requirement No.1
D5.4 | project presentation, leaflet and poster
D1.1 | Report on Terms of Reference and PAC composition
D5.5 | Data Management Plan

## Slide 19
D6.1 EPQ-Requirement No.1
7.1. Further information about the possible harm to the environment caused by the research and the measures that will be taken to mitigate the risks must be included in the grant agreement, kept on file, specified in the grant agreement, and submitted as a deliverable.
7.2. Copies of authorisations for relevant facilities (e.g., security classification of laboratory, GMO authorisation) must be kept on file and specified in the grant agreement.
7.3. The applicant must demonstrate that appropriate health and safety procedures conforming to relevant local/national guidelines/legislation are followed for staff involved in this project. This must be confirmed in the grant agreement.
Collection of all radiation safety permissions or licences by the coordinator
All partners confirm in writing that they keep the appropriate work safety regulations of their respective home countries.

## Slide 20
Communication Action Plan for ARIEL 1
ARIEL activities will result in the generation of new knowledge. The dissemination of the results from the various experiments supported by ARIEL will be promoted by a series of communication actions.
This Communication and Dissemination Action Plan (CAP) gives a scheme for the communication of information during the whole lifetime of the project. Before its implementation by the Consortium the CAP is submitted to the Programme Advisory Committee (PAC) for approval.
The Communication Manager, who is one of the members of the Management Board, supervises all questions of communication and publication of results. The Management Board assists the Communication Manager with the implementation of this CAP and steers its execution.
One of the intrinsic objectives of ARIEL is to communicate the knowledge as fast and as widely as possible. The communication actions target four different groups:
• the Consortium members,
• the neutron data community,
• the wider scientific community,
• the public at large.
It is understood that this Plan cannot foresee from the beginning all communication activities during the whole duration of the four-year project. The present version of the CAP is a guideline and will be updated periodically following a review at each Management Board meeting (each six months). The regular update of the CAP will be discussed as a separate item in the Periodic Activity Report.

## Slide 21
Communication Action Plan for ARIEL 2
Each of the four groups must be addressed in a specific and appropriate way. Therefore the Consortium uses seven different communication channels:
1. Web-based activities,
2. Publicity,
3. Active participation in international cooperation and interaction with other relevant projects,
4. Scientific publications, talks and contributions to conferences,
5. Organisation of meetings and workshops,
6. Contribution to databanks, and creation and maintenance of specific databases,
7. Organisation of education and training activities including summer schools.
The CAP will then list and update the activities in all
seven communication channels

## Slide 22
Accelerator and Research Reactor Infrastructures for Education and Learning (ARIEL)
EURATOM Workprogramme 2018 Education and Training: NFRP-2018-7 Availability and use of research infrastructures for education, training and competence building
EC contribution: 2 Mio. EUR Coordination and Support Action
Project duration: 48 months starting September 1, 2019
Notes: ARIEL proposal to EURATOM Nuclear Fission, Fusion and Radiation Protection Research (NFRP)
Grant agreement has been signed by EC,
22

## Slide 23
Accelerator and Research Reactor Infrastructures for Education and Learning: ARIEL
Notes: 23 Partners from 14 countries
23

## Slide 24
CALL NFRP-2018-7: EDUCATION AND TRAINING Availability and use of research infrastructures for education, training and competence building
Specific Challenge: education and training to maintain nuclear competences scheme offering access to research and training infrastructures
Scope: EU nuclear research laboratories for graduate and post graduate students, researchers and technicians. Links with Euratom fission science networks and technology platforms International cooperation with OECD/NEA, IAEA, GIF
Expected Impact: multi-disciplinary nuclear competences in fields: nuclear safety, radiation protection, decommissioning, radioactive waste management provide young scientists, researchers and experts with access to high quality nuclear research and training facilities.
Notes: Excerpt from the EURATOM call NFRP-7 to which ARIEL was a proposal.
GOAL is development and maintenance of multi-disciplinary nuclear competences in many fields by providing access to nuclear research facilties.
New conditions of the call :
International cooperation with NEA, IAEA.
Quantified information on the expected number of people benefitting from the proposed scheme.
Reduction of beam time support, increase of user support, number of scientific visitors
broadening of research spectrum
Summer schools to attract physics and engineering students to the field.
24

## Slide 25
ARIEL objectives
Integration of access to neutron facilities with education and training Experiments in international teams: Hands-on training for students in the graduate and postgraduate level - lead to PhD and master theses.
Integration of the full nuclear data cycle by collaboration with JEFF (OECD/NEA), IAEA, and TSO’s e.g. GRS, IRSN
Collaboration with research reactor facilities MTK-EA, JGU, SCK*CEN, ILL, CVR and with ENEN
Increase number of students in the nuclear data field
Increase attractivity by widening the research spectrum:
  nuclear data measurements and evaluation + validation, radiation detector development, integral experiments, material irradiation, nuclear data for isotope production, fundamental nuclear physics, medical applications, neutron imaging radiochemical experiments.
Increase support for early stage researchers
Inclusion of technical staff (engineers, operators) in ARIEL activities
Notes: Education and Training for young scientists (Early stage researcher is defined for Marie Curie fellowships)
Here it is meant differently, as students or young scientists until 6 years after PhD.
25

## Slide 26
ARIEL main activities
Transnational Access to Neutron facilities 30 typical experiments, 3000 beam time hours 4 users per experiment supported for 7 days
Training of early stage researchers and scientific visits 30 research stays of up to 12 weeks
Summer schools to reach out to students 4 summer schools organized by University of Seville, Johannes Gutenberg University, CIEMAT and Uppsala University
Scientific progress meetings: Dissemination of results - nuclear data networking: kick-off meeting + three scientific meetings JRC, NPL, IPN Orsay
Joint scientific meetings with SANDA and JEFF
Notes: Structure of ARIEL
Items correspond to the work packages.
26

## Slide 27
Transnational Access to Neutron Facilities
Support for 3000 hours of additional beam time hours, 30 typical experiments
Increased mobility support for external user groups (4 persons, 7 days). Early stage researchers (less than 6 years since PhD) preferably supported.
TAA Pooling scheme successful (see CHANDA, ARIEL, ...)
Selection of Experiments by the Project Advisory Committee based on scientific excellence and relevance to the ARIEL objectives
Synergies with EURATOM SANDA project and other calls from WP2018, e.g. target production activities
Seven calls for proposals starting with November 2019
Notes: TAA should support all suitable activities for EURATOM fission research from the current call.
The TAA pooling scheme has been successful from EFNUDAT onwards.
It is also kept here in ARIEL.
A Project Advisory Committee of 5 external experts decides about proposed activities.
All Support is distributed along the recommendations of the ARIEL PAC.
27

## Slide 28
ARIEL criteria for selection of experiments
Project Advisory Committee to select experiments based on scientific excellence and value to education and training
  Focus on nuclear safety and on support to modelling and evaluation (e.g. ASTRID, MYRRHA, molten salt reactors, spent fuel concepts and decommissioning)
  Research experience for early-stage researchers: advanced techniques for radiation measurements, testing and development of novel detector concepts. Exchange of knowledge and methodologies for senior scientist and technical staff.
  Coordination with EURATOM projects related to nuclear data (SANDA: High precision nuclear data for the major actinides present in advanced reactor fuels)
  Coordination with OECD/NEA (High Priority Request list, JEFF, NEST), IAEA International Nuclear Data Evaluation Network (INDEN) and European Technological Platforms.
Notes: Nuclear Education, Skills and Technology (NEST) Framework of OECD/NEA
28

## Slide 29
Project Advisory Committee
Daniel Cano-Ott, CIEMAT
Roberto Capote, IAEA
Robert Jacqmin, CEA
Maëlle Kerveno, CNRS
Gert van den Eynde, SCK*CEN (nominated after the kick-off meeting)

## Slide 30
Training of early stage reseachers and scientific visits
Up to 30 research stays for up to 12 weeks: Early stage researchers + short term visitors
Full spectrum of experimental capacities of the consortium resulting in a high potential of competence building.
Support student graduate education + training of engineers and technicians + sharing knowledge between experienced researchers.
Participation of IAEA, JEFF(NEA), GRS and IRSN essential
Selection by the Project Advisory Committee based on scientific excellence and relevance to the ARIEL objectives in collaboration with ENEN
Notes: Early stage researchers, senior experts and technical staff and engineers can be supported in education and training.
International Organisations JEFF IAEA TSOs participate as hosts for E & T of students, researchers, experts ...
30

## Slide 31
Summer schools
Hands-on school on the production, detection and use of neutron beams, University of Seville (18-24 participants)
Lab course in Reactor Operation and Nuclear Chemistry, University of Mainz (10 participants)
Nuclear data: the path from the detector to the reactor calculation, CIEMAT, Madrid (20 participants)
EXTEND’2022 summer school at Uppsala University (20-25 participants)
Dissemination and advertisement through ENEN
Notes: Summer schools will have up to 80 participants to attract new students to the field.
Organisation will be done by the hosting institutes with advise and help from the PAC and ENEN
31

## Slide 32
MT
PAC
EC
LC
Management Board
TAC
SC
PC
CM
TC
ARIEL Management structure
5 nuclear data experts (experimentalists + theoreticians) with end-user expertise
+ Management Board
GA
General Assembly MB + one representative
per partner
EC: European Commission
GA: General Assembly
PAC: Programm Advisory Committee
PC: Project Coordinator
MT: Management team
SC: Scientific Coordinator
CM: Communication manager
TAC: Transnational Access Coordinator
TC: Training Coordinator
LC: Local Contact persons

## Slide 33
ARIEL Workpackages
WP1 – Management of the project
WP2 – Transnational Access Management
WP3 – Access to neutron facilities
WP4 – Training of early stage researchers and scientific visits
WP5 – Schools and dissemination
WP6 – Ethics requirements

## Slide 34
WP1
Management of the project
Budget: 204688 €
WP2
Transnational Access Management
Budget 65923 €
WP3
Access to neutron facilties
Budget: 902616 €
WP4
Training of early stage researchers / scientific visits
Budget: 302663 €
WP5
Schools and Dissemination
Budget 521500 €
Total budget 2000000 €

## Slide 35
Management Board
Project Coordinator: Arnd Junghans, HZDR
Scientific Coordinator: Arjan Plompen, JRC
Transnational Access Coordinator: Ralf Nolte, PTB
Communication Manager: Carlos Guerrero, USE
Training Coordinator: Heikki Penttilä, JYU
Dr. Carola Franzen, Dr. Roland Beyer, Katja Gröger, HZDR
Management Team

## Slide 36
Summary and Outlook
Before: TAA support for nuclear data measurements at neutron beam facilties Scientific motivation e.g. WPEC 26, JEFF, HPRL. High quality nuclear data from experiments. Short term visits to support experimental work. Theoretical results e.g. fission models, GEF code Experiments used for Thesis work of students.
Now: ARIEL Education and Training extending over the „nuclear data cycle“ from measurements (differential and integral) to validation and evaluated data libraries
“Hands on training in international teams” Education and Training activities of early stage researchers. Increased mobility support.
E & T of young scientist through scientific visits. Exchange of knowledge for experts.
Consortium and possible scientific activities are broader: JEFF, IAEA-NDS, TSOs (GRS,IRSN) can participate and benefit from the activities .
Collaboration with research reactor facilities JGU, SCK*CEN , CVR, ILL and with ENEN
Progress meetings and scientific workshops (keep up network of users and facilities)
Four summerschools to attract new students to applied nuclear activities