## Slide 1
n_TOF Technical Report
at the 67th INTC Meeting
Oliver Aberle, SY-STI-TCD

## Slide 2
Main activities for LS2 - Facility
  Work in FTN line (PS closure 23rd October)
  Spallation target exchange
    Water cooling station
    Target shielding modification
    Perspective for NEAR-target experimental station
  Horizontal beam line
    Sweeping magnet replacement
    New collimator No2
    NEAR
Outlook LS2

## Slide 3: FTN line
Magnet renovation done
New mobile shielding installed
SEM Grid tank installation done, instrument and Be window installation in January 2021
Alignment completed, line closed und under vacuum
Cabling completed
Completed
Access last week to check ventilation door tightness

## Slide 4: n_TOF target and mobile shielding

## Slide 5: n_TOF spallation target #3
Engineering Design Report EDMS TOF-TAR-ES-0003
Target #3 construction and assembly completed
Target #3 cold tests w/ nitrogen cooling station operational – February 2021
Target #3 Installation Review (TIR) – end of February 2021 (https://indico.cern.ch/event/984553/)
Target #3 installation in the pit and vertical beam line installation – March/June 2021 completed
n_TOF readiness for beam mid-July 2021 Beam on target planned for 19th July 2021 (see ACC-PM-MS-0002 (v.4.0) MASTER SCHEDULE OF THE LONG SHUTDOWN 2 (2019-2020))

## Slide 6
n_TOF target #3
Production completed

## Slide 7
n_TOF target #3
Completed

## Slide 8
Target and vertical beam line installation

## Slide 9
Target and vertical beam line installation

## Slide 10
Target and vertical beam line installation
Completed

## Slide 11: n_TOF target shielding
Access door modification
Reconfiguration of the (fixed) shielding around the spallation target
Mobile part
Third Generation n_TOF Spallation Target and Vertical Neutron Beam Line EDMS TOF-TAR-EC-0001

## Slide 12: n_TOF – original pit (April 2020)
Target pit ±1999
Target pit April 2020
20 years

## Slide 13
n_TOF target mobile shielding
Completed

## Slide 14: Perspectives on ”NEAR-target” station
Discussions and details in TOF-PM-WD-0001
Priority is to get facility running post-LS2, meaning target, shielding & neutron beam line components – funded in a resource-loaded schedule (phase 1)
Study for physics-driven NEAR station currently ongoing, with implementation post LS2 under evaluation (phase 2)
  Dedicated movable/exchangeable moderator on the shaping collimator aperture
  Full size plug under construction for handling tests
   post LS2 possible

## Slide 15: Shielding details for “NEAR”
In-shielding with collimator insert, space for moderator and samples

## Slide 16: Shielding details for “NEAR”
Collimator insert and lifting spreader test

## Slide 17: Shielding details for NEAR
Investigate on possibilities and interest for irradiation for R2E, R2M and physics

## Slide 18: Perspectives for NEAR target station
Synergistic irradiation of materials for acc. complex (R2M) in mixed-field conditions at unprecedented levels at CERN
0.3-0.5 Gy/pulse (~1 MGy/y), homogeneous over “large” volumes
AP. Bernardes, M. Maeder, M. Ferrari, D. Senajova, M. Barbagallo

## Slide 19: NEAR
  Test for accessibility done
  Shelf installed last week
Courtesy D. Senajova

## Slide 20: NEAR
  Test for accessibility done
  Shelf installed last week

## Slide 21: n_TOF water cooling station

## Slide 22: Target #3 cooling and moderator station
Target nitrogen cooling required the full replacement of the target cooling and moderator circuits
Major efforts from CV to develop the technology to match the specifications and RP requests (EDMS 2068336)
F. Dragoni
Charcoal + HEPA filters
Moderators (2x)
N2 compressor
Under pressure room for filters (RP)
This Photo by Unknown Author is licensed under CC BY-NC

## Slide 23: n_TOF horizontal beam line (TT2A)

## Slide 24
New sweeping magnet
Alignment today
Vacuum chamber inserted and welded

## Slide 25: Original second EAR 1 collimator
Consolidation of collimator No2
Functional specification TOF-T-ES-0001 (v.0.1) New Second Collimator in the Horizontal n_TOF Neutron Beam Line

## Slide 26: New collimator #2 EAR1
Carbon steel sheets, laser cut
Borated PE
Manual drive + linear rails
Ø 20mm
Ø 80mm
Movement
Vacuum chambers
Structure: Profils, water jet cut
Mechanical end stops
Two different collimators, swap during run to different diameter
Avoid long procedure for collimator exchange
Green light for design given after a review with n_TOF
Detailed design completed, fabrication launched
Assembly ongoing, installation planned week 27

## Slide 27: n_TOF Experiment LS2 activities
Cabling campaign in EAR1 (remove the old sweeping magnet cables, replace the detector cables in the rack/bunker area) - Completed
Implementation of the ASN-OFSP safety recommendations in EAR2
Consolidation of the gas system in EAR2 - ongoing
Consolidation of the alignment system – after beamline remounting
Upgrade of the n_TOF electronics laboratory - completed
Control room and offices ready
DAQ upgrade
Consolidation and R&D program for detectors - ongoing

## Slide 28: Schedule and coordination
n_TOF Facility Refurbishment Project Schedule: EDMS 2001626
Ready for beam
Target and vertical beam line installation
Horizontal beam line installation

## Slide 29: Conclusions
Target installed
Cooling and moderator stations up and running
Vertical beam line completed
  Horizontal neutron beam – collimator to finalize and to install
  Upgrades and consolidation in both Class A laboratories
First beam on target 19th July 2021