## Slide 1: East Area Renovation – EACM report – 06.07.21
East Hall under construction - 1962
B. Rae (BE-EA), on behalf of the project team

## Slide 2: Early restart of T8 approved by IEFC
Initial schedule:
  Ready for beam commissioning : W37
  Physics restart W42
The main change is the early restart of Physics for Irrad and Charm – T8 primary beamline
  Ready for beam commissioning : W34
  Physics restart W38 (on September 20th)
The restart of the secondary beam lines would remain unchanged as from week 42 – on October 18th

## Slide 3: Current situation
PAD-MAD in operation
Massive RP shielding ready
Primary area ventilation ready
T8 will be restarted on September 20th for IRRAD and CHARM
T9, T10 and T11 will be restarted on October 18th for SBA’s
IST’s and HWC in full swing, no showstopper

## Slide 4: Most recent installation
Control rooms
ATEX ventilation
Gas systems
RP Shielding completion
2 last magnets

## Slide 5: Next steps
Complete ISTs and HWC of T8 beamline
Complete ISTs and HWC of T9, T10, T11 beamline
Coordinate with HSE-RP, BE-OP & BE-EA for the aspects linked to the beam permit for the beam intensity ramp-up
Establish a coordination between IRRAD/CHARM operation team and the EA project/BE-EA physicists

## Slide 6: Thanks for your attention !