## Slide 1: Status and Summary of Beam Lines – Areas Readiness 129th EATM 13th of July 2021
Bastien Rae

## Slide 2: Status of Beam Lines
Building | Zone | Ready for beam | Work to be done | Group involved | Schedule
EHN1 | H2 | Yes | Scaffolding to be removed | NA61 | ASAP
 | H4 | Yes |  | BE-EA/SY-BI | ASAP
 | H6 | Yes | Realign XCON.041.126 | BE-GM | 
 |  |  | XCHV.041.128 doesn’t close beyond +-1.5 mm | SY-BI | ASAP
 | H8 | Yes | Realign XCON.042.130 | BE-GM | Next Access
EHN2 | M2 | Yes | SCRAPER 9 Reading Problem | SY-STI | ASAP
 |  |  | XION seems not connected | SY-STI | ASAP
 |  |  | Access wrong configuration for M2A | EN-AA | ASAP
 |  |  | Problem on SM2 (Software) | SY-EPC/BE-CSS | ASAP
TCC8 | P0 | Yes | XCHV.043.396 and MBNH.043.554 to exchange | BE-EA/SY-STI/TE-MSC | Next MD and TS (TBC)
ECN3 | K12 | Yes |  |  | 
General intervention to be done:
Systems | Still to be done
Magnets | None
Obstacles (coll, target, …) | None
Instrumentation | Beam instrumentation commissioning pending by SY/BI
 | Fiscs High voltage low
Software | Target offset Issue
OP | T4 mini scan
 | Increase intensity on targets

## Slide 3: TT83 Issues week 26
On the end of June we’ve discovered few vacuum leaks in the TT 83 (P42 beam line).
Activities done from the 28th of June to the 2nd of July.
Thanks to the heavy work of teams North Area was ready to take beam on the 2nd July.
Unfortunately, The TBIU/Ds was still not under vacuum.
Devices | Problem | Work doned | Solved
MCAH33 | Colar vacuum leak | Colar exchange | Yes
MDX.043.171 | Soufflet vacuum leak | Repaire the leak with paste | Partially
XCHV.043.396 | vacuum leak | nothing could be done | No
MBNH.043.554 | Soufflet vacuum leak | Repaire the leak with paste | Partially
Pumps | Some Pumps to check | Exchange polarity on one Pump | Yes

## Slide 4: TT83 Issues week 27
As the TBIU/Ds problem was taking more time to be solved.
We profit of this week to fix issues in TT83.
Need a lot of preparation and groups involved thanks to all.
We manage to finish everything around 13h30 on Friday.
North Area commissioning have started on Saturday morning.
Devices | Problem | Work done | Solved
MDX.043.171 | Soufflet vacuum leak | Exchange of the magnet | Yes
XCHV.043.286 | Potentiometer problem (no reading) | Exchange of the collimator | Yes
XCHV.043.396 | vacuum leak | Prepare a spare for exchange | No
MBNH.043.554 | Soufflet vacuum leak | Prepare a magnet for exchange | Partially

## Slide 5
Questions or comments ?