## Slide 1: The North Area Consolidation Project Procurement Plan
Daniel Schoerling
IPT-PI
On behalf of the NA-CONS Team

## Slide 2: North Area Consolidation
Renovation of the Fixed Target Experimetal Area at the CERN Prevessin site, after 45 years of wear-and-tear + fantastic physics
Recover the availability and reliability of the beam- facility
Correct safety concerns and non-conformities
Be prepared for new projects and test beams in next decades

## Slide 3: Schematic view of the North Area
A few numbers:
Overall surface 60000 m2:
  underground 16600m2,
  experimental halls 31000 m2,
  service buildings: 12000 m2
6 beam lines, ~ 6.3 km cumulated
~ 1500 visitors / year
Exp. Halls
Underground
beam tunnels,
caverns
Underground
Technical galleries
Service
buildings
1250 m
300 m
Secondary beam area
Primary beam area

## Slide 4: Project Timeline/Roadmap
Concluded
Budget approved
Planned

## Slide 5: Cumulated budget
Chart: MCHF
| 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
NA HARDWARE PHASE 1 | 373.8 | 1198.871 | 2944.4593 | 5707.74 | 11777.3499 | 20886.8835 | 26994.3289 | 31237.844
NA HARDWARE PHASE 2 | 6529.3193 | 19483.2193 | 42394.121 | 64036.1076
PROJECT COORDINATION | 95.618 | 157.6113 | 389.4678 | 738.6992 | 1158.0199 | 1509.5097 | 2128.7794 | 2759.0994 | 510.5096 | 791.5096 | 1086.5096 | 1795.0096
NA SAFETY PHASE 1 | 281.85 | 604.029 | 1713.9993 | 4842.823 | 6898.7988 | 8870.133 | 10651.8196 | 11089.0073
NA SAFETY PHASE 2 | 152.5051 | 467.5051 | 525.9051 | 640.3051
TT20/TDC2 | 20 | 146.08 | 495.9881 | 1284.3688 | 4711.2806 | 11262.7518 | 15116.113 | 17629.7583 | 460.0661 | 470.0661 | 567.5661 | 1025.0661
 | 80000 | 80000 | 80000 | 80000 | 80000
TF (MTP 2021) | 776 | 2111 | 5607 | 12087 | 21612 | 34027 | 49375 | 60612 | 61741
 | 73000 | 73000 | 73000
Nota: without EL-CONS (~ 20 MCHF)

## Slide 6: Procurement plan: WP

## Slide 7: POLARIS Highlights
IT Manufacturing
188 units
Cat. C
200 units
Cat. C
All new IT contracts
Contracts: 5 years (+2)
IT Power Stacks
438 units
Cat. B
496 units
Cat. B
CONTRACT 1
PHASE I – LS3: commit for qty / contracts in 2022/23
PHASE II – LS4: use optional qty / re-order in 2027/28
396 POLARIS to deliver
188 units
208 units
CONTRACT 2
IT ELCO Capacitors
13 400 units
Cat. B
14 000 units
Cat. B
CONTRACT 7
IT Magnetics
438 units
Cat. B
496 units
Cat. B
CONTRACT 4
Standard off-the-shelf capacitors
360 V / 2000 Apk

## Slide 8: BOREAL Highlights
Manufacturing
9 conv / 28 racks
Cat. A
8 conv / 33 racks
Cat. A
EXISTING CONTRACT
PHASE I – LS3: commit for qty / contracts in 2022/23
PHASE II – LS4: use optional qty / re-order in 2027/28
17 BOREAL to deliver
9 units
8 units
CONTRACT 3-a
CONTRACT 5-a
IT MV Transformer
CONTRACT 6
21 IP00 + IP3x enclosures
Cat. A
28 IP00 + IP3x enclosures
Cat. A
IT Power Stacks
21 units
Cat. A
28 units
Cat. A
Existing + DO + IT
Contracts: 5 years (+2)
DO Magnetics
21 units
Cat. A
28 units
Cat. A
320 V / 6000 Apk

## Slide 9: NEPTUNE Highlights
Manufacturing
2 conv / 18 racks
Cat. A
-
EXISTING CONTRACT
PHASE I – LS3: contracts in 2022/23
PHASE II – no deliverables
CONTRACT 3-b
IT Power Stacks
22 units
Cat. A
-
Existing + IT
IT Magnetics
22 units
Cat. A
-
CONTRACT 5-b
2 NEPTUNE to deliver
2 units
-
120 V / 24000 Apk

## Slide 10: Phase I: Power converter consolidation
2023
2025
2021
2027
2022
2024
2026
COMPONENTS TENDERING
MANUFACTURING TENDERING
PROJECT DEFINITION
PRE-SERIES COMPONENTS
PRE-SERIES CONVERTER
SERIES COMPONENTS
SERIES CONVERTERS
CONVERTER PROTOTYPING
INSTALATION COMISSIONING
Market Survey, IT,
Finance Committee
Contract signature
Production & FATs
Test at CERN platform
Production & FATs
Test with Series Converters
Production & FATs
Tests at CERN Platform
Market Survey, IT,
Finance Committee
Contract signature
Design Approval
Production & FATs
Test with Converter Prototype

## Slide 11: Other requirements
BID (beam intercepting devices) and components & Beam Instrumentation
  ~50 devices need to be consolidated or replaced, foreseen within the next 2 years
Vacuum Components
  Existing/renewed contracts (service & supply)
Civil Engineering
  Mainly roof & envelope renovation
Cooling and ventilation installations
  Consolidation of the existing infrastructure (using existing/renewed service contracts)
Electrical installation (cabling)
  Consolidation of the existing infrastructure (transformers, switchgears, cables, UPS, etc), using existing/renewed service contracts
Fire safety
  Analysis on-going and actions planned to be done with service contracts
Fire and gas detection system
  Existing/renewed service contracts
Magnets and magnet components
  In-house consolidation in CERN workshops with existing/renewed CERN service & supply contracts
Access control system
  Existing/renewed service contracts