## Slide 1: MC RF WG WP structure proposal for next 5 year. v2
Jean-Pierre Delahaye, Alexej Grudiev, Derun Li, Akira Yamamoto on behalf of MC RF WG
2021/08/31
MC RF WG meeting #4

## Slide 2: WP1: Baseline design of the RF system for acceleration to high energy: Design study
Year: | 1 | 2 | 3 | 4 | 5 | input | output | Resources
Baseline design of the RF systems for RCSs including acceleration, longitudinal beam dynamics and stability, bunch length and energy spread control. Provide specifications for cavity design: frequency, R/Q, HOM suppression. Provide specification for RF power sources: frequency, power, … |  |  |  |  |  | HEC, MG, BD | PPC | CERN SY-RF Staff 0.2FTEx3y Fell 1FTEx3y
Calculation of cavity parameters for fundamental mode parameters: R/Q, Vmax; as well as for HOMs and wakes for the design work in 1. |  |  |  |  |  |  |  | 
RF design of the cavities for the RCSs as input to BDR |  |  |  |  |  |  |  | 
Design of the RF cavities for LA and RLAs based on the specifications from HEC and BD |  |  |  |  |  | HEC, BD |  | 
Uni. of Rostock is interested: WP 1.2, 1.3, 1.4
Staff 0.2FTE x 3y
+
pd/PhD
1 FTE x 3y

## Slide 3: WP2: High gradient SRF technology for muon accelerators. Synergy + potential prototypes
Year: | 1 | 2 | 3 | 4 | 5 | input | output | Resources
1. Provide limiting values for RF cavity and RF system design from SRF State of the Art: Gradient and Q0 at different frequencies: 300 - 1300 MHz Tolerances to external (stray) magnetic fields Tolerances to radiation and beam loss |  |  |  |  |  |  | HEC | Expert Staff ? FTE
2. Synergy: Look for synergy in SRF technology with already ongoing projects and R&D activities. Direct them to the parameter space relevant for muon collider High gradient at low frequencies Tolerances to magnetic field, radiation and beam loss |  |  |  |  |  |  |  | Expert Staff ? FTE
3. High gradient prototype at low frequency (~300 - 400 MHz) accelerating structure to target high gradient: >20 MV/m |  |  |  |  |  |  |  | ???
SRF Expert
? FTE x 3-5y
Anybody interested ?

## Slide 4: WP3: Baseline design of the RF system for Muon cooling complex. Design study
Year: | 1 | 2 | 3 | 4 | 5 | input | output | Resources
1. Collect specifications for the design of all RF cavities : frequency, gradient, length, B-field, aperture (window size and thickness), … |  |  |  |  |  | MC |  | 
2. Based on available knowledge both experimental and theoretical, identify best concept for achievable accelerating gradient in magnetic field: material, pulse shape, temperature, gas, … |  |  |  |  |  |  |  | 
3. Calculate parameters of all cavities specified in 1. Provide a consistent set of parameters of all RF cavities and associated RF systems |  |  |  |  |  |  | PPC | 
4. Mitigation of collective effects including beam loading by design |  |  |  |  |  | MC, BD | MC, BD | 
5. Integration of RF cavities into cooling cell, adapting design if necessary |  |  |  |  |  | MC,MG,CR | MC | Eng FTE ?
CEA, LBNL are interested
Staff 0.2FTE x 3y
+
pd/PhD
1 FTE x 3y
Eng. Staff
?FTE x ?y

## Slide 5: WP4: Conceptual design of the RF system for Muon Cooling Demonstrator (MCD). Design study
Year: | 1 | 2 | 3 | 4 | 5 | input | output | Resources
1. Collect specifications for the design of RF cavity for the MCD: frequency, gradient, length, B-field, aperture, … |  |  |  |  |  | MC |  | 
2. Design the RF cavity using the concept identified in WP3.2 |  |  |  |  |  |  | TF | 
3. Design of the associated RF systems for the MCD |  |  |  |  |  |  | TF | 
4. Engineering design of the cavity in its environment including cooling, thermal and mechanical stability, alignment, RF diagnostic and tuning, … |  |  |  |  |  |  |  | 
5. Integration of the RF cavity into the MCD cooling cell including SC solenoid, cryo, etc |  |  |  |  |  | MC,MG,CR,… | TF | Eng. Staff ? FTE x ?y
CEA, LBNL is interested
Eng. Staff
???FTE x ?y
Sinergy with WP3

## Slide 6: WP5: R&D on high gradient NRF in strong magnetic field. Potential test stand + test cavities
Year: | 1 | 2 | 3 | 4 | 5 | input | output | Resources
1. Identify infrastructure available for potential use as (or setting up) an RF test stand for testing RF cavities in strong magnetic field: RF power source, SC solenoid, … |  |  |  |  |  |  |  | ?
2. Design and build RF test stand based on the available infrastructure and specified requirements. |  |  |  |  |  |  |  | ???
3. Propose test program adapted to potential test setup, considering possible limitations in terms of available frequency, power, magnetic field strength and size of a SC solenoid(s) Materials, Temperature Pulse length/shape Surface preparation for FE reduction Gas |  |  |  |  |  |  |  | ?
4. Design and build test cavities |  |  |  |  |  |  |  | ???
5. Test the test cavities |  |  |  |  |  |  | MC | ???
CEA is interested

## Slide 7: WP6: Development of RF power sources for muon collider RF systems. Design study + synergy
Year: | 1 | 2 | 3 | 4 | 5 | input | output | Resources
1. Muon cooling complex RF system. Set target specifications and address potential issues including: Large number of different frequencies, High peak power requirements High efficiency |  |  |  |  |  | MC | MC | 
2. (Initial) Baseline Design of high efficiency RF power source(s) to provide information on the peak power capability, efficiency and cost Proton driver Muon cooling complex Linear accelerators Ring accelerators |  |  |  |  |  |  | PPC | 
Staff 0.2FTE x 3y
+
pd/PhD
1 FTE x 3y