## Slide 1: The North Area Consolidation Project
The NA-CONS Team

## Slide 2: North Area Consolidation:
Renovation of the Fixed Target Experimetal Area at the CERN Prevessin site, after 45 years of wear-and-tear + fantastic physics
In view to:
Recover the availability and reliability of the beam- facility
Correct safety concerns and non-conformities
Be prepared for new projects and test beams in next decades

## Slide 3: Schematic view of the North Area
A few numbers:
Overall surface 60000 m2:
  underground 16600m2,
  experimental halls 31000 m2,
  service buildings: 12000 m2
6 beam lines, ~ 6.3 km cumulated
~ 1500 visitors / year
Exp. Halls
Underground
beam tunnels,
caverns
Underground
Technical galleries
Service
buildings
1250 m
300 m
Secondary beam area
Primary beam area

## Slide 4: Project Timeline/Roadmap

## Slide 5: NA-CONS: Phase 1 & Phase 2
Phase 1: 2019 -2026 => priority to TT20 & NA Transfer Tunnels
Phase 2: 2027 -2030 => H2, H4, H6, H8, M2 & K12 beam lines

## Slide 6: Project Organization
Level 1 : 7 Work Categories
Level 2 : 37 Work Packages
Level 3 : 120 Work units

## Slide 7: Project Organization
Project articulated around 2 main bodies

## Slide 8: Project Board
PBM : Project Board Meetings
Frequency : Monthly
Duration : 2 Hours
https://indico.cern.ch/category/14292/
https://edms.cern.ch/ui/#!master/navigator/project?P:100708504:100708504:subDocs

## Slide 9: Technical Coordination Committee
*ICEA: Integration Committee for Experimental Areas
WGs:
EABI WG
NA-Decabling WG
SLAWG
Reliability WG
NA Commissioning WG
Projects:
TG-CONS
EL-CONS
TCM : Technical Coordination Meetings Frequency : Quarterly
Organized by topical subjects

## Slide 10: Cumulated budget*
Chart: MCHF
| 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
NA HARDWARE PHASE 1 | 373.8 | 1198.871 | 2944.4593 | 5707.74 | 11777.3499 | 20886.8835 | 26994.3289 | 31237.844
NA HARDWARE PHASE 2 | 6529.3193 | 19483.2193 | 42394.121 | 64036.1076
PROJECT COORDINATION | 95.618 | 157.6113 | 389.4678 | 738.6992 | 1158.0199 | 1509.5097 | 2128.7794 | 2759.0994 | 510.5096 | 791.5096 | 1086.5096 | 1795.0096
NA SAFETY PHASE 1 | 281.85 | 604.029 | 1713.9993 | 4842.823 | 6898.7988 | 8870.133 | 10651.8196 | 11089.0073
NA SAFETY PHASE 2 | 152.5051 | 467.5051 | 525.9051 | 640.3051
TT20/TDC2 | 20 | 146.08 | 495.9881 | 1284.3688 | 4711.2806 | 11262.7518 | 15116.113 | 17629.7583 | 460.0661 | 470.0661 | 567.5661 | 1025.0661
 | 80000 | 80000 | 80000 | 80000 | 80000
TF (MTP 2021) | 776 | 2111 | 5607 | 12087 | 21612 | 34027 | 49375 | 60612 | 61741
 | 73000 | 73000 | 73000
* Without EL-CONS (~ 20 MCHF)

## Slide 11: Main items
Objects for procurement in the PBS
Power
Converters

## Slide 12: Main items
Objects for procurement in the PBS
Magnets and
magnet components

## Slide 13: Main items
Objects for procurement in the PBS
Beam intercepting
devices + components
Vacuum
components

## Slide 14: Main items
WBS – Objects for procurement
Building- and
tunnel renovation
Cooling and
Ventilation installations

## Slide 15: Main items
Objects for procurement in the PBS
Electrical installation
and power supply
renovation

## Slide 16: Main items
Objects for procurement in the PBS
Fire- and gas detection
systems
Fire Safety installations
Access control systems

## Slide 17: Experimental Magnets
85 kCHF
525 kCHF
+
155 kCHF
2’490 kCHF

## Slide 18
Status consolidation of power converters for ATLAS/Morpurgo and VERTEX1&2
Xavier Genillon & Yves Gaillard SY/EPC

## Slide 19
ATLAS/MORPUGO:
The power converter is ready and First powering tests in A7 building is ongoing
All Power and Control DIC are done and taken into account
(Final integration for DC cable to be validate by BE-EA)
Installation will start at the end of the 2021 Run (15th of November)
    End of November: Power converter installation
    December 2021: EN-EL and EN-CV installation
First Powering test (Short circuit) will start in beginning of February 2022
Commissionning with the Discharge system will start in middle of February

## Slide 20
VERTEX1/VERTEX2:
The power converters are ready for the tests in A7 building
All Power and Control DIC are done and taken into account
Dismantling of the Vertex area will start at the end of the 2021 Run (15th of November)
Installation will start in January 2022.
The commissionning will be done during March/April 2022.

## Slide 21: Status
Circuit topology study and optimization concluded
Choice of the most appropriate breaker made
  DC circuit breakers chosen
Market Survey and Invitation to Tender for the breakers:
  MS-4680/TE/NA completed in June
  IT-4680/TE/NA completed end of July
  Opening of the bids in August
  Firms screening ongoing
  Contract signature by end of September
Resistors bought and integration started
Budget envelope as indicated in DR should be respected
Working closely with EPC
On schedule !

## Slide 23: The 3 circuits
VERTEX1&2: remove the old equipment and install the new ones
New PC/EE location (keep the old system as a back-up)
ATLAS/Morpurgo magnet
VERTEX 1 and VERTEX 2
ATLAS
Inom = 5000 A
At Inom, U = 3.45 V
For 2A/s, U = 5.64 V
VERTEX 1
Inom = 5013 A
L = 1.68 H
I = 3820 A, U = 1.17 V
I = 5013 A, U = 1.71 V
For 3 A/s, U = 4.3 V
VERTEX 2
Inom = 3820 A
L = 1.68 H
I = 500 A, U = 0.19 V
I = 3820 A, U = 1.37 V
Almost identical parameters for the three circuits