## Slide 1: Summary
Patrick Fuhrmann
EMI data area lead

## Slide 2: Reminder : This is us !
2
EMI Data
Catalogue
Synchronization
SRM
Security
GLUE 2.0
ARGUS
Integration
DATA client
Library consolidation
Standards
NFS 4.1
EMI
Security
Standardization
OGF
IETF
Standards
http(s)
WebDav
SRM Spec
Simplification
Storage
Accounting
UNICORE
Integration
WLCG
ARC

## Slide 3: Reminder : Data Area activities
11 Activities (Details later)
  SRM specification [me , status report ]
  SRM security (httpg/s) [Paul , status report]
  NFS 4.1 development and performance evaluation [ me , status report]
  Catalogue synchronization [Fabrizio , status report]
  Storage Accounting record [Ralph, status report]
  GLUE 2.0 migration [Oliver , status report]
  Client library consolidation client [Zsombor, status report ]
  UNICORE : SRM and catalogue [Christian L., status report]
  Integration of ARGUS [individual, progress by DPM and dCache]
  Monitoring [ nobody yet, but has to be covered]
  Message passing evaluation [ wiki page, don’t now how to proceed]

## Slide 4: SRM
1.0 | SRM specification consolidation |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1.1 |  | Start dicussion within OGF |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1.2 |  | Collect community feedback |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1.3 |  | Initial document |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1.4 |  | SRM integration into UNICORE |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1.5 |  | Review and final document |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2010 |  |  |  |  |  |  |  | 2011 |  |  |  |  | 
Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr |  | 
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 
Year 1 |  |  |  |  |  |  |  |  |  |  |  | Year 2 | Year 3
2.0 | Replacing httpg with https |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2.1 |  | Prototype one client one SE |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2.2 |  | All EMI SE's and clients |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2.3 |  | Migration scenario and design |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SRM specification consolidation
2010 |  |  |  |  |  |  |  | 2011 |  |  |  |  | 
Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr |  | 
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 
Year 1 |  |  |  |  |  |  |  |  |  |  |  | Year 2 | Year 3
SRM security (replacing httpg by https)
Patrick
Paul

## Slide 5: Standard data access
3.0 | Posix Access (NFS4.1) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3.1 |  | Setup of performance test system |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3.2 |  | Performance test results (CHEP) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3.3 |  | Production file:// StoRM and dCache |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3.4 |  | file:// for all SE in production |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4.0 | https/WebDav |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4.1 |  | http(s) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4.2 |  | WebDav |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Standard access protocols (NFS4.1, WebDav)
2010 |  |  |  |  |  |  |  | 2011 |  |  |  |  | 
Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr |  | 
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 
Year 1 |  |  |  |  |  |  |  |  |  |  |  | Year 2 | Year 3
Patrick

## Slide 6: UNICORE : Catalogue and SRM client
6.0 | File catalogue access for UNICORE |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
6.1 |  | Implementation of file catalogue integration |  |  |  |  |  |  |  |  |  |  |  |  |  | 
6.2 |  | Evaluation of file catalogue intergration |  |  |  |  |  |  |  |  |  |  |  |  | PM 15 | 
1.4 |  | SRM integration into UNICORE |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2010 |  |  |  |  |  |  |  | 2011 |  |  |  |  | 
Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr |  | 
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 
Year 1 |  |  |  |  |  |  |  |  |  |  |  | Year 2 | Year 3
UNICORE integration : Catalogue and SRM client
Christian

## Slide 7: Activities (cont.)
7.0 | GLUE 2.0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
7.1 |  | Common interpretation of GLUE 2.0 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
7.2 |  | Publishing 1.3 with 2.0 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
7.3 |  | Publishing 2.0 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
8.0 | Data client library consolidation |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
8.1 |  | Development |  |  |  |  |  |  |  |  |  |  |  |  |  | 
8.2 |  | Migration |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2010 |  |  |  |  |  |  |  | 2011 |  |  |  |  | 
Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr |  | 
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 
Year 1 |  |  |  |  |  |  |  |  |  |  |  | Year 2 | Year 3
2010 |  |  |  |  |  |  |  | 2011 |  |  |  |  | 
Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr |  | 
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 
Year 1 |  |  |  |  |  |  |  |  |  |  |  | Year 2 | Year 3
GLUE 2.0 migration
Data client library consolidation
Oliver
Zsombor

## Slide 8: Activities (cont.)
Integration of ARGUS |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Blacklist integration (at least one SE) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Blacklist integration (all SE's) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Integration of more functionality if required |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2010 |  |  |  |  |  |  |  | 2011 |  |  |  |  | 
Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr |  | 
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 
Year 1 |  |  |  |  |  |  |  |  |  |  |  | Year 2 | Year 3
10.0 | Storage Accounting |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
10.1 |  | Definition of storage accounting record |  |  |  |  |  |  |  |  |  |  |  |  |  | 
10.2 |  | Add support in SE/FTS |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2010 |  |  |  |  |  |  |  | 2011 |  |  |  |  | 
Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr |  | 
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 
Year 1 |  |  |  |  |  |  |  |  |  |  |  | Year 2 | Year 3
Integration of ARGUS
Storage accounting
Ralph

## Slide 9
Managebility |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | CLI and Web Interfaces |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Evalution : Message Passing |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Possible use cases |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2010 |  |  |  |  |  |  |  | 2011 |  |  |  |  | 
Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr |  | 
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 
Year 1 |  |  |  |  |  |  |  |  |  |  |  | Year 2 | Year 3
2010 |  |  |  |  |  |  |  | 2011 |  |  |  |  | 
Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr |  | 
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 
Year 1 |  |  |  |  |  |  |  |  |  |  |  | Year 2 | Year 3
Manageability
Evolution of “message passing”
11.0 | Monitoring |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
11.1 |  | Definition of a common Monitoring Interface |  |  |  |  |  |  |  |  |  |  |  |  |  | 
11.2 |  | Implementing Sensors in SE's and FTS |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2010 |  |  |  |  |  |  |  | 2011 |  |  |  |  | 
Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr |  | 
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 
Year 1 |  |  |  |  |  |  |  |  |  |  |  | Year 2 | Year 3
Monitoring
Activities (cont.)

## Slide 10: Activities in detail
About 20 people in a small room
Agreements on the different activities :

## Slide 11: Catalogue synchronization
Interaction between storage element and catalogue is still the way we would like to go although we are aware that this only partially fixes deficiencies of the current system.
However we will start by :
Improving GFAL to reduce the number of occasions where the content of catalogues and SE’s start to diverge.
We will provide a tool (using an message passing infrastructure) where SE system administrators can provide a list of ‘lost file’. Those entries will then be removed from the various catalogues.
Based on the experience of that approach we will plan further actions.

## Slide 12: GLUE 2.0 migration
Details on the content of GLUE 2.0 are done.
Plans of deployments are not due.
Servers will be updated first :means they will
  Start publishing GLUE 1.3 information into the GLUE 2.0 framework.
  Followed by GLUE 2.0 information.
Clients will follow (about april/may) understanding both GLUE 1.3 and GLUE 2.0. (fallback if necessary)

## Slide 13: SRM , https and delegation
SRM https demonstrator w/o delegation using the https mode of GLOBUS.
Tested against standard SSL library.
Tested GDS delegation service as part of the SRM service (same host same port), as FTS currently does. So we know it works.
On delegation :
  Working group between security/computing and data, with the goal to find a commonly acceptable delegation service. (Goal of our technical director) Groups lead by Paul.
  As far as we understand GDS fulfils all the requirements for data.

## Slide 14: NFS 4.1
Servers implementations are in a good shape. dCache production ready for EMI-1. DPM very likely mid of EMI-1/2.
Clients will become available slowly. Depends on RedHat (6.>2) and FERMI people (providing SLx)
Performance and reliability better than expected. Serious tests done on a 50% Tier II based on NFS 4.1 at DESY with dCache.
Improve collaboration with ROOT people.
Industry solutions on the way. (IBM at CNAF and NetApp at DESY)

## Slide 15: Integration with ARGUS
Individual effort.
DMP and dCache already provide an interface (prototype) with ARGUS.
Very good support by ARGUS team.
We don’t see problems here.
FTS and LFC will follow.

## Slide 16: Storage Accouning
Requirements collected from all kind of sources. (Security, OGF, experiments ..)
First draft of the Storage Record definition available (Wiki)
However still discussions on details.

## Slide 17: Client library consolidation
Groups just created.
Very complex topic.
Doesn’t influence EMI-1
Need to have a f2f meeting with GFAL and ARC developers to understand the potential of merging ARC and GFAL (and maybe dCache and StoRM) libraries.

## Slide 18: UNICORE integration
Work just started. New person has to learn UNICORE.
Catalogue integration : Not clear to either use java/jni with official LFC client library or use plain java and contribute java to official LFC library.
SRM client options :
  Use the dCache one.
  BeStMan : preferred as they provide real client API. (Alex Sim would be happy to support us)

## Slide 19: Monitoring
Will start beginning of next year.
No working group build yet.
No work done yet. (intentionally)

## Slide 20: SRM Specification
Very important have agreement with non EMI bodies. (BeStMAN, OGF, OSG, CASTOR, WLCG).
All relevant people are informed of your efforts.
Agreement so far : no spec nor code changes 
Mostly providing useful documentation to understand SRM and best effort documentation.

## Slide 21: Summary summary
EMI-Data People are very committed to their work in EMI.
All working groups provide workplans, results and meeting minutes in our WIKI.
Working groups all in time.
Trying to have code changes ready for EMI-1 well in advance to avoid delays.
Will start a success ticker page so that management and interested partners can easily follow our work.
Patrick : AHM for EMI-Data has been very effientand surprisingly successful.

## Slide 22: Thank you
EMI is partially funded by the European Commission under Grant Agreement INFSO-RI-261611