NA2: dissemination, training, exploitation
Peter Stefan (NIIFI)

---
Outline
- Dissemination (SC10)
- Exploitation and sustainability
- Conclusions

---
SC 2010
- Brief report on SC10:
- Supercomputing in New Orleans from 15-18 November.
- The largest HPC and grid related event worldwide.
- Nordugrid was represented as an exhibitor.
- Both ARC, the product, KnowARC, the former project and also EMI was highlighted.
- >50 visitors at the booth.
- Interoperability demo was shown in Julich booth having ARC sites heavily involved.

---
SC 2010
    - SC booth image

---
DNA2.4 Exploitation & sustainability plan
- Progress has been made on the document.
- It suffers heavy delay compared to the original work plan.
- The causes are multiple:
  1. the exploitation experience needed some more harmonisation than expected before
  2. we faced a massive amount of lack of manpower working on this task.

---
DNA2.4 Exploitation & sustainability plan
- In the last 2 weeks after PEB warning the edition of the document has boosted.
- Nevertheless the task coordinator needs more commitment (also in terms of dedicated people) from the project.
- Coordinator estimates that with an intensive work the document can be finalized in 2 week at proper quality.
- Coordinator dedicates a full person, Peter Stefan, being experienced in exploitation as well as system operations.

---
Conclusions
- The major HPC/grid related events are addressed.
- More comprehensive work in needed on dissemination and training.
- Training events must be coordinated within EMI and EGI.
- Exploitation and sustainablity is a common effort among all EMI partners, some more intensive works is expected.

---
Thank you
EMI is partially funded by the European Commission under Grant Agreement INFSO-RI-261611