| Coordination meeting #1 of HL-LHC motorized jacks |  |  |  |  |
| --- | --- | --- | --- | --- |
| Date: 2021-09-23 | Project/Activity: WP#3, WP#4, WP#8, WP#15 |  |  |  |
| Attendees:, O. Capatina (OC), D. Duarte Ramos (DDR), P. Fessia (PF), M. Garlasche (MG), M. Gonzalez de la Aleja Cabana (MGAC), L. Krzempek (LK), T. Lehtinen (TL), J. Perez Espinos (JPE), F. Sanchez Galan (FSG), M. Sosin (MS) |  |  |  |  |
| Agenda: - Review and approval of the minutes of the meeting held in June - Review and status of actions - Status of design, open points and next steps (T. Lehtinen) - Mechanical analyses (L. Krzempek) - Agreement on time and frequency of recurrent meetings - Roundtable |  |  |  |  |
| DISCUSSION |  |  |  |  |
| Review and approval of the minutes of the precedent meeting The minutes of the meeting held in June for the review and clarification of the HL-LHC engineering specification are approved. No comments received on them. Review and status of actions Update FRAS specification to be compatible with the HL-LHC motorized jacks one; PF; - OPEN. Clarify jack configuration for Q4, Q5, crab cavities and TAXN; MGAC; - ONGOING. Validate jack configuration for operation; MS; - ONGOING. Validate push system for vertical movement for crab cavities; OC; - CLOSED. Provide interface to motorization systems; MS; - ONGOING. Provide interface to load sensors (for horizontal and vertical cases); MS; - ONGOING. Update integration models for all jacks definition and validate space reservation for them; MGAC; - ONGOING. Provide interface to machine elements; TL; - ONGOING. Contact V. Parma to get detailed information (if available) about the upgrade for the use of the LHC jacks on the triplets; JPE; - CLOSED. Organize meeting to revisit the radiation hardness specification; PF; - OPEN. Review of document prepared by F. Micolon for stiffness requirement; JPE, MS; - ONGOING. - Action not started. To be assigned to WP15.4 - MGAC makes a presentation with the jack configuration of all components, at every point and side. A first layout is already drafted and agreed between MGAC and MS. In principle all machine components are defined and agreed except for the crab cavities. The configuration and orientation of the jacks of the crab cavities is under discussion with Teddy Capelli. Three aspects are being studied: clash between pairs of jack envelopes (including adapters), between jacks envelopes and space reservation for other CC instrumentation and space reservation for potential maintenance of adapters. The objective is to have all changes implemented by the end of W39. Concerning Q4 and Q5, the distance between the pair of jacks is lower than in the rest of new cryostats being constructed for HL-LHC. Following the integration study, the space required for the maintenance of the motorization adapters looks quite limited, so MS questions if there is any option to increase the distance to improve this aspect. DDR announces that the only solution would involve the de-cryostating of the corresponding magnets and re-work behind, involving a huge intervention, not foreseen in the planning (PF). MS will study the option to reduce the envelope for the vertical adapter. - Action linked to the previous one. - OC confirms that the crab cavities will not undergo any configuration or state (at vacuum, at cold, etc.) where the contact between the any of the jacks and them could be lost. Following an external discussion, the point is cross-checked again with DDR and FSG, who also confirm that there is not foreseen any configuration where the contact between any jack and the corresponding support is lost. No showstopper from this side to retain the same concept used in LHC, for HL-LHC. - MS informs that though a lot of progress has been made to design and define the best motorization systems, the details are not yet ready. Following a discussion about a timescale to provide this information and not to delay the overall design (first proposal was to provide it by the end of November), MS will address the topic internally and try to find a solution to provide it in the following weeks, not beyond the end of October (TBC). - A discussion has already been held by TL, LK and Michael Guinchard. The conclusion is that there’s no good or easy solution for the implementation of the load cells, especially for the horizontal mechanism. The Ansys models generated by LK are being studied in detail to evaluate positions where normal strain components are dominant and homogeneus, and suitable for load cell implementation. The models are already sent to M. Guinchard and a feedback is expected soon. MS informs anyway that will organize a meeting during W39 to progress on the topic. - The models used for integration are consistent with the last version supplied by TL some months ago. The last updates are not yet included. It is agreed that TL implements all the changes derived from the Ansys analyses and progresses on the horizontal mechanism before integrating them. No big changes or showstoppers are expected for jack external dimensions, especially those considered critical for the envelope reservation. - The plain bearing used in the current design is the same used for LHC. The interface for them is the one used as a reference for the magnets, crab cavities and TAXN. The action will consist to confirm and consolidate the use of the same type plain bearing as in LHC and ensure that the correct interface is adopted in the machine components. To be closed in the following weeks. - Following a discussion and further clarification during the meeting, it is confirmed the following: the external stiffeners proposed were never implemented in the triplets, while the internal ones were actually used (confirmed by TL during the meeting). Likewise, it is confirmed that the drawings of the LHC jacks (for the triplets) should include the correct and final fit. - No progress. Meeting to be organized in the following weeks. - Several discussions held in the last weeks about this subject between MS, LK and JPE. The origin of the requirement (not included inside the spec. document) has as objective to ensure a resolution of 10 microns on the movement of the mechanisms. The figures are still subjected to discussion and assessment inside the survey team (MS to organize an internal discussion in W39 to analyse its extents). Following FE analyses, JPE informs that not all requirements, as written, seem to be attainable with the current LHC concept and dimensions. More detailed information to be provided during LK presentation. Status of design, open points and next steps (TL) TL presents the status of the design. The design can be considered to be at a preliminary phase and the next weeks will be dedicated to consolidate and detail the horizontal drive, to implement and adapt the construction analysed by LK for the external frame (based on a welded solution) and to optimize the geometry of some parts (push-pull frame and guide cylinder) according to the analyses already made. These points can be dealt quite independently of some other inputs (interfaces to motorization systems and load sensors) but an intensive re-design action could be required for the integration of the load sensors, especially for the radial case; the completeness of the action related to the interface for the load sensors is considered of high priority. A first meeting to assess the options to integrate the load cells has already been held between TL, LK and Michel Guinchard. The first conclusion is that the integration of the load sensor, at least for the radial case, appears to be a big challenge. MS will organize a meeting during W39 to address the topic. Two specific points are addressed during the presentation: - TL questions about the need to maintain the vertical motion system lock nut; MS confirms the need to retain the solution in order to block the system when a maintenance for the vertical adapter is required; - MS asks TL about the potential implementation of stop ends that are regulated after the pre-assembly and first alignment of the system in order to block the movement beyond the 2.5 mm required for the FRAS. No solution is foreseen for the moment for it. MS will organize an ad-hoc meeting during W39 to address the topic. Mechanical analyses (LK) LK presents a summary of the FE analyses made for the current design model, integrating a new welded external frame. The results are focused to check the fulfilment of the model with the ASME standard and the corresponding EU directive, and to assess the stiffness of the solution at push and pull radial directions and compare the results with the values requested in the document created by F. Micolon. The conclusions are the following: - There is a big difference in terms of overall stiffness between push and pull configurations. The stiffness at pull configuration is smaller than that at push configuration. - In view of the absence of stiffness specification in the approved HL-LHC engineering spec. the following values are taken as guidelines: - compatible LHC stiffness specification: 52.8 kN/mm; - stiffness values required in F. Micolon’s document: 43 kN/mm for a jack in single configuration; 70 kN/mm for a jack in double configuration. - At the most unfavourable operational position (ram column at highest position and tilted to the maximum radial displacement), the push configuration is compatible with the lowest two values but not for a stiffness of 70 kN/mm. The pull configuration, however, is not compatible with any of the three figures. - At the most favourable operation position (ram column at lowest position and fully centred wrt frame), the push configuration provides a stiffness slightly lower than 70 kN/mm while the pull configuration remains slightly lower than 52.8 kN/mm. - The stiffness can be increased through design modifications and material choice optimization. The maximum gain is estimated to be 15%-20% higher than the reference values, but with the current concept and envelope constraints it won’t be possible to fulfil a minimum stiffness of 70 kN/mm, and even one of 52.8 kN/mm for the pull configuration (TBC). - Regarding the fulfilment of the ASME standard and the corresponding EU directive, the stress values seem to be inside the requirements. Some model singularity is anyway under study (guide cylinder – ASME standard). Agreement on time and frequency of recurrent meetings JPE proposes to organize a series of meetings (weekly or bi-weekly basis) on Thursdays, from 11h00 to 12h00, until the design and the integration aspects of the jacks are fully consolidated. The objective would be to have a design review (details of the scope TBC) by the end of 2021 (preferably, by the end of November) and to consolidate a planning for the manufacturing of the pre-series for the IT string by the end of October. The slot and recurrence of meetings is approved. Roundtable Linked to the action related to the validation of the push system for the vertical movement of the crab cavities, MS reminds a configuration for which the contact between the jack and its support could be lost. D2 assembles a central jack that involves a hyperstatic configuration. The accumulation of mechanical errors in combination with different loading and cycling conditions, could involve unforeseen supporting conditions. DDR to clarify the actions foreseen by WP3 to avoid this problem [ACTION]. |
| ACTION |  |  |  |  |
| Update FRAS specification to be compatible with the HL-LHC motorized jacks one |  |  | PF | OPEN |
| Clarify jack configuration for Q4, Q5, crab cavities and TAXN |  |  | MGAC | ONGOING |
| Validate jack configuration for operation |  |  | MS | ONGOING |
| Provide interface to motorization systems |  |  | MS | ONGOING |
| Provide interface to load sensors (for horizontal and vertical cases= |  |  | MS | ONGOING |
| Update integration models for all jacks definition and validate space reservation for them |  |  | MGAC | ONGOING |
| Provide interface to machine elements |  |  | TL | ONGOING |
| Organize meeting to revisit the radiation hardness specification |  |  | PF | OPEN |
| Review of document prepared by F. Micolon for stiffness requirement |  |  | JPE, MS | ONGOING |
| Documents: |  |  |  |  |
| Prepared by: J. Pérez Espinós |  | Date: 29-09-21 |  |  |
| Approved by: - |  | Date: - |  |  |
| Distribution List: Participants and WP leaders |  |  |  |  |