## Slide 1: CSP 25th November 2010 Technical agreement number 3: overview
Paolo Fessia
Detailed technical analysis will be provided by Jean-Michel Rifflet

## Slide 2: Work package 3.9 MQXC model coils
Advancement status:
  Components procured or being procured (SC cable, insulated, end spacers are presently being produced by CEA and CERN in parallel with two different suppliers in order to minimize risks, Copper wedges should be delivered soon)
  Test winding coil has provided encouraging results, no need to further end spacer optimization before 2 meters long coil winding and curing
Review for winding start up 14th December
CERN plans for start of magnet assembly in March 2011.
Planning and resources
Delay of about 6 months respect to previously foreseen schedule
Indicative personnel profile |  |  |  | Indicative financial profile |  | 
 | Engineer | Technician | Draft man |  | K€ | KCHF
2008 | 0 | 0 |  | 2008 |  | 
2009 | 1 | 0 |  | 2009 |  | 
2010 | 5 | 14 | 11.3 | 2010 | 79 4.7 spent 25. committed | 127
2011 | 4 | 6.4 |  | 2011 |  | 
Total | 10 | 20.4 |  | Total | 79 | 127
Deliverables |  |  |  |  |  | 
Date |  | Description |  |  |  | 
September 2008 |  | CERN: main coil parameters |  |  |  | 
October 2009 |  | CERN: magnet cross section |  |  |  | 
October 2010 |  | Delivery to CERN of 4 sets of coils |  |  |  | 

## Slide 3: Work package 3.10 thermal studies
Advancement status:
  Done on 2 ceramic coil samples @ 10 MPa and 20 MPa in HeII, results are not published yet
  At present performing tests in supercritical helium and He I on the same porous ceramic coil stack in KEK,
Nearby future status
  First semester of 2011: construction of the 50 MPa stack sample for ceramic coil.
  Second semester: test of the 50 MPa stack sample for ceramic coil.
  2011: start discussion for the classical insulation sample
Planning and resources
Shift of 6 months for the milestones September 2010 on ceramic insulation (enlarged scope)
Shift of about 10-12 months for end of 2010 milestone on classic insulation
Resources for next year should be reviewed on the base of present experience, review between the WP leaders is necessary. In addition He expenditure should be clarified (not accounted up to now)
Warning: present plan shift has not an impact on any construction project but could affect further Eucard work
Indicative personnel profile (man.months) |  |  |  | Indicative financial profile |  | 
 |  |  |  |  | K€ | KCHF
2009 | 3.97 3.7 |  |  | 2009 | 0 0 | 0
2010 | 5.53 2.6 |  |  | 2010 | 25.5 19 | 41.1
2011 | 4 |  |  | 2011 | 24.9 | 40
2012 | 2.5 |  |  | 2012 | 11.7 | 18.9
Total | 16 |  |  | Total | 62.1 | 100
Milestones and Deliverables |  |  |  |  |  | 
Date |  | Description |  |  |  | 
30 September 2010 |  | Report on heat transfer measurements on SMC ceramic coil block |  |  |  | 
31 December 2010 |  | Report on heat transfer measurements on SMC classic coil block |  |  |  | 
30 June 2012 |  | Final thermal measurement report |  |  |  | 

## Slide 4: Work package 3.11 SMC coils
Advancement status:
  One ceramic double pancake was made and is under evaluation (at warm). Very useful exercise
  Extra test on FRESCA on insulation sample are being prepared
  CERN proposes a technical review of the results in order to decide how to proceed with this task in effective way
  Planning and resources
Planning it seems more or less inline, but it strongly depends on the technical evaluation of the 1st results obtained.
Resource call very probably for a strong increase (remark different respect previous accounting because of administrative issue )
Indicative personnel profile (man.months) |  |  |  | Indicative financial profile |  | 
 |  |  |  |  | K€ | KCHF
2009 | 0 6.4 |  |  | 2009 | 0 0 | 0
2010 | 5.3 14.8 |  |  | 2010 | 59.1 16.3 | 95.1
2011 | 5.2 |  |  | 2011 | 34.1 | 54.9
2012 | 0 |  |  | 2012 | 0 | 0
Total | 10.5 |  |  | Total | 93.2 | 150
Milestones and Deliverables |  |  |  |  |  | 
Date |  | Description |  |  |  | 
30 September 2010 |  | 1 ceramic insulated race track double pancake coil finished |  |  |  | 
30 September 2011 |  | 2 ceramic insulated race track double pancake coils finished (second generation ceramics) |  |  |  | 

## Slide 5: Work package 3.12 Coils for FRESCA model
Advancement status
  On the 20th-21st of January and international review panel will scrutinize the present design . As result the coil fabrication phase should be launched
Planning and resources
1st milestone (tooling design report) should be moved to June 2011
2nd milestone: dummy Cu conductor should be moved to September 2011
3rd milestone 2 coils in Nb3sbshoud be moved to December 2012
Resources wise for the moment look to stuffiest but should be re-evaluated in June
Indicative personnel profile (man.months) |  |  |  | Indicative financial profile |  | 
 |  |  |  |  | K€ | KCHF
2009 | 0 0 |  |  | 2009 | 0 0 | 0
2010 | 4 0.5 |  |  | 2010 | 10 0 | 16.1
2011 | 12 |  |  | 2011 | 160 | 257.6
2012 | 5.7 |  |  | 2012 | 16.3 | 26.3
Total | 21.7 |  |  | Total | 186.3 | 300
Milestones and Deliverables |  |  |  |  |  | 
Date |  | Description |  |  |  | 
31 March 2011 |  | Tooling design report |  |  |  | 
30 June 2011 |  | 1 Dummy Fresca2 coil in Cu conductor |  |  |  | 
31 August 2012 |  | 2 Fresca2 coils in Nb3Sn conductor |  |  |  | 

## Slide 6: Work package 3.13 Nb3Sn strands
Advancement status
  Specification has been provided by CERN to CEA end of May 2010
  Common agreement CEA-CERN on specification on the 8th September 2010
  Planning and resources
  15th November CEA will issue the D.O. for 2X15 km of strands (for probably 2X150.000 CHF)
  Delivered probably end 2011
  After procurement 35 Km (D.O. mid 2011)-> delivery probably October 2012
Indicative personnel profile (man.months) |  |  |  | Indicative financial profile |  | 
 |  |  |  |  | K€ | KCHF
2009 | 1.13 0.9 |  |  | 2009 | 0 | 0
2010 | 3 1 |  |  | 2010 | 250 | 402.6
2011 | 3.87 |  |  | 2011 | 450 | 724.6
2012 | 1 |  |  | 2012 | 45.3 | 72.9
Total | 9 |  |  | Total | 745.3 | 1200
Milestones and Deliverables |  |  |  |  |  | 
Date |  | Description |  |  |  | 
31 May 2010 |  | Common strand specification CERN-CEA |  |  |  | 
31 December 2010 |  | First pilot stand delivered |  |  |  | 
1 March 2012 |  | 2 x 10 km pilot strand and 45 km production strand delivered |  |  |  | 
30 April 2012 |  | Report on the validation and tests of delivered conductor (3 contracts) |  |  |  | 
31 July 2012 |  | Final R&D strand delivered |  |  |  | 

## Slide 7: Work package 3.15 inertia tube
Advancement status:
  Kick off meeting CERN CEA SDMS end of September 2010
  Steel procured from Outokumpu, waiting for delivery
  CERN -CEA-SDMS agreed on acceptance material procedure to give green light for machining
  Planning and resources
  Start production December 2010
  Probably 10 months later delivery
  (10 months delay)
Allocated human resources |  | 6 man.months |  | Allocated financial resources |  | 400 K€-238 KCHF | 
Indicative personnel profile |  |  |  | Indicative financial profile (commitment) |  |  | 
 | Engineer | Technician | Draft man |  | K€ |  | KCHF
2008 |  |  |  | 2008 |  |  | 
2009 | 0 |  | 1.2 | 2009 |  |  | 
2010 | 3 | 3 | 2.4 | 2010 | 400 497 10% paid this year |  | 560
2011 |  |  |  | 2011 |  |  | 
Total | 3 | 3 |  | Total | 400 |  | 560
Deliverables |  |  |  |  |  |  | 
Date |  | Description |  |  |  |  | 
December 2010 |  | Delivery of : 7 inertia tubes SSS type 3 inertia tube Q8-Q10-Q11 type |  |  |  |  | 

## Slide 8: Work package 3.16 winding house
Advancement status:
  Design ready April 2010
  Call for tender May 2010, offers opening June 14th , 2010
  Contract fully signed 15th November 2010
  Planning and resources
  Kick off meeting 2nd of December
  Work execution to be re-defined (previous schedule (15th September) set start of work 2nd of February for completion end of April, probably 1 extra month of delay at least)
  Probably 5-6 months delay
Indicative personnel profile (man.months) |  |  |  | Indicative financial profile |  | 
 |  |  |  |  | K€ | KCHF
2008 |  |  |  | 2008 |  | 
2009 | 2 0 |  |  | 2009 |  | 
2010 | 4 1.6 |  |  | 2010 | 621.1 K€ 6938 K€ | 1’000 KCHF
2011 |  |  |  | 2011 |  | 
Total |  |  |  | Total |  | 
Milestones and Deliverables |  |  |  |  |  | 
Date |  | Description |  |  |  | 
March 2010 |  | Tender |  |  |  | 
May, 2010 |  | Contract signature |  |  |  | 
July, 2010 |  | Start up of the works |  |  |  | 
December 15, 2010 |  | Work acceptance |  |  |  | 

## Slide 9: Work package 3.17 Fundamental measurements of He-II heat transfer in small channels
Objective:
Study The steady-state heat transport in superfluid helium through micro-channels to provide a better understanding of the heat transfer mechanisms through helium-permeable superconducting cable insulations.
Indicative personnel profile (man.months) |  |  |  | Indicative financial profile |  | 
 | Engineer | Designer | Technician |  | K€ | 
2010 |  |  |  | 2010 | 20 | 
2011 | 10 |  |  | 2011 | 20 | 
Total | 10 |  |  | Total | 40 | 
Milestones and Deliverables |  |  |  |  |  | 
Date |  | Description |  |  |  | 
October 2010 |  | Identification of the samples manufacturing methods |  |  |  | 
December 2010 |  | Proof of principle |  |  |  | 
April 2011 |  | Execution of the experimental tests, analysis and reporting of the results |  |  |  |