## Slide 1: Accord Technique N° 5 : vue d’ensemble
Etudes d’accélérateurs et fournitures
La contribution du CNRS/IN2P3 comprend la participation à la consolidation du complexe des accélérateurs du CERN, et en particulier:
de l’accélérateur PS, entré en fonction en 1959, par:
  l’approvisionnement de 30 jeux de bobines de correction des aimants principaux du PS
  l’étude de la maille optique du futur accélérateur PS2
du LHC, par
  l’approvisionnement de cryostats
  la conception de la consolidation des cryostats de connexion

## Slide 2: Agreement N° 5/1 : PS2 Linear Lattice Design
Start November 2009
End December 2010
Human resources 4.8 manmonths
Financial resources 0
Responsible A.Tkatchenko & M.Benedikt (CERN)
Milestone | Date | Description | Status
1 | Feb 2010 | Comparative analysis of optics variants for PS2 NCM lattices and identification of preferred version | A preferred NCM lattice has been identified
2 | January 2011 | Contribution to PS2 final report | To be defined
Considering the present strategy for the upgrade of the CERN injectors, a potential contribution to the PS2 CDR needs to be discussed.
The total amount of human resources spent up to now was 2.0 man·months

## Slide 3: Agreement N° 5/2 : PFWs
Start September 2009
End December 2010
Human resources 11 manmonths
Financial resources 750 kEuros
Responsible E.Froidefond (CNRS) & D.Bodart (CERN)
Milestone | Due | Description | Status
1 | Dec 2009 | Signature of contract with manufacturer | March 2010
2 | Sep 2010 | Delivery & tests of 5 pre-series coils | Jan 2011
3 | Oct 2010 | Delivery & tests of 8 coils | Apr2011
4 | Apr 2011 | End of deliveries: in total 30 sets | Sep 2011
5 | Sep 2010 | Procurement of a Reception Test Bench | Dec 2010
Technical status of the project is promising
The availability of the Test Bench is needed by Jan 2011

## Slide 4: Agreement N° 5/3 : LHC spare Vacuum Vessels
Start June 2010
End December 2011
Human resources 3 man.months
Financial resources 208 kEuros
Responsible G.Olivier (CNRS), L.R.Williams (CERN)
Milestone | Due | Description | Status
1 | End 2010 | Place contract for procurement of 2 (or 3) spare MS vacuum vessels for LHC | In progress
2 | By end 2011 | Supply of tested vessels complete with relevant documentation | Pending

## Slide 5: Agreement N° 5/4 : Connection Cryostat
Start June 2010
End December 2012
Human resources 12.48 man.months
Financial resources 0
Responsible D.Reynet (CNRS), J.Ph.Tock (CERN)
Milestone | Due | Description | Status
1 | July 2010 | Identification of consolidation of the LHC connection cryostats | Done
2 | TBD | Proposals of design consolidations | Pending
3 | TBD | CERN acceptabce of drawing files | Pending