## Slide 1: Survey : Proto TCM0 Test Bunker (SM18) 2022
Vivien RUDE
2021-11-16

## Slide 2
Q4
2021
Q1
2022
Q2
2022
Q3
2022
Q4
2022
 April 2022:
Fiducialisation
Installation of FSI targets (Step 8)
UK
CERN SM18
Sept.
Version : 2021-11-08
 May 2022:
Installation of FSI system
Installation of FSI heads (Step 13)
PROTO RFD
Q1
2023
SPS
Jan.
Sept 2022:
Reception : Measurement after transport
Connection (optical fibers)
Test of adjustment system
Aug 2022:
SM18 Preparation
(FSI system, optical fibers, floor marking, jacks)
Oct 2022:
Impact of vacuum (3 cycles)  Tomography ?  photogrammetry
Cooling down / warm up (3 cycles)
Nov / Dec 2021:
Fiducialisation (TANK)
(analyze of CMM)
March 2022:
Alignment ISO 5
Alignment below top plate
Test of adjustment system (Step 6)
Dec 2022 :
SPS : uninstallation DQW
Jan 2023 :
SPS : installation RFD

## Slide 3
Thank you
for your attention

## Slide 4
SPARE

## Slide 5
Q4
2021
Q1
2022
Q2
2022
Q3
2022
Q4
2022
UK
CERN SM18
Sept.
Version : 2021-11-08
PROTO RFD : survey milestones
Q1
2023
SPS
Jan.
Dec. 2021 : Definition of mechanical axis of Dressed cavities
April 2022 : 18 supports + targets + Orientation tools + procedure
May 2022 : 18 FSI heads calibrated (after vacuum test)
May 2022 : 18 Optical fibers
May 2022 : 1 FSI system
August 2022 : 18 protection of FSI heads
Sept. 2022 : 2 inclinometers + interface
Sept 2022 : 2 Gimsa ??