## Slide 1: Non conformities Status: HCACFCA001-RN000001/2
Hector Garcia Gavela
CERN 25.11.2021

## Slide 2: Nonconformities Pre-Series production
NCR ID | Equipment | Short Description | Status | Criticality | Issued by | Action Taken | Process
2188175 | DQW cavity | Nonconformity WPQR 007 Bare Cavities | Closed | Non Critical | RI | Concession | Welding qualification
2222647 | DQW cavity | Nonconformity WPQR 014 Bare cavities | Closed | Non Critical | RI | Concession | Welding qualification
2229210 | DQW cavity | Nonconformity WPQR 008 and WPQR 017 | Closed | Non Critical | RI | Concession | Welding qualification
2242699 | DQW cavity | Bowl thickness | Closed | Non Critical | RI | Concession | Forming
2242738 | DQW cavity | Elliptical cap thickness | Closed | Non Critical | RI | Concession | Forming
2271792 | DQW cavity | Thickness reduction weld between extension tube and HOM/FPC port | Closed | Non Critical | RI | Concession | Design modification
2307879 | DQW cavity | FPC port tube | Closed | Non Critical | RI | Concession | Machining
2338730 | DQW cavity | Thickness reduction welds 35 and 36 | Closed with Warnings | Non Critical | RI | Concession | Design modification
2338731 | DQW cavity | Penetration of welds 17 and 18 (banana) | Closed with Warnings | Non Critical | RI | Concession | Welding qualification
2360124 | DQW cavity | NCR Top ring P111520_20 | Actions Underway | Non Critical | RI | Repair | Deep drawing
2360135 | DQW cavity | NCR ToP ring P111520_06 | Closed | Non Critical | RI | Scrap | Engraving
2360141 | DQW cavity | NCR Main body recalibration | Actions Underway | Non Critical | RI | Repair | Forming
2364755 | DQW cavity | Short Pick up tubes 4094_P111029_01/02/03/04 and Pick up tubes 4094_P111022_01/02/03/04 | Actions Underway | Non Critical | RI | Repair | Bending
2380193 | DQW cavity | NCR Elliptical cap scratches after forming P111520_01 | Actions Underway | Non Critical | RI | Repair | Forming
2380218 | DQW cavity | NCR welding extension pipes | Evaluation | Non Critical | RI | Scrap/Repair | Welding
2413645 | DQW cavity | NCR-Dimensional control Bowl | Actions Underway | Non Critical | RI | Concession | Machining
2414585 | DQW cavity | NCR-Dimensional control main body | Actions Underway | Non Critical | RI | Concession | Machining
2414587 | DQW cavity | NCR- Dimensional control beam flanges | Closed with Warnings | Non Critical | RI | Repair/Concession | Machining
2419566 | DQW cavity | NCR weld ring with tank connection port | Closed with Warnings | Non Critical | RI | Repair/Concession | Welding
2423795 | DQW cavity | NCR- shorter top elliptical cap | Actions Underway | Non Critical | RI | Repair | Machining
2427293 | DQW cavity | NCR-Pick-up flange vacuum grooves | Closed | Non Critical | RI | Concession | Machining
2610747 | DQW cavity | UT Thickness measurements after BCP | Closed | Non Critical | RI | Concession | Testing
2614464 | DQW cavity | RF Measurement at cold - HCACFCA001-RN000001 | Actions Underway | Critical | RI | Repair | Cold Test - Performance

## Slide 3: Nonconformities Pre-Series production
Chart: 
| Welding qualification | Forming | Design modification | Machining | Deep drawing | Engraving | Bending | Welding | Testing | Cold Test - Performance
 | 4 | 4 | 2 | 6 | 1 | 1 | 1 | 2 | 1 | 1

## Slide 4: Nonconformities Pre-Series production
Nonconformities should be taken as a lesson learned
Avoid recurrence in series production is a must (preventive actions to be taken into account for future production) in order to improve efficiency
Evaluation is not always straight forward, and it brings extra work and resources at CERN too (design studies, simulations, etc.). This is a lengthy process and highly dependent on resources availability
In many cases, the impact of the nonconformity is not fully clear until the final test of the cavity is performed