## Slide 1: Ongoing BPM studies at AWAKE
E. Senes

## Slide 2: Outline
Goal of today: make the point on ongoing BPM studies at AWAKE
1x HF-BPM
40 GHz buttons by OMC
2x ChDR BPM
Alumina inserts
TRIUMF electronics
1
2

## Slide 3: View
PLASMA CELL
ChDR BPM
eBPM
eBPM
eBPM
HF BPM
ChDR BPM
e+p BPM
BTV350
eBPM
ELECTRON MERGE

## Slide 4: Purpose
Goal agreed with AWAKE: develop an e-BPM capable to measure the position unbiased by the protons.
Timeline agreed with AWAKE: run 2a, possibly not at the end of the run. Run 2a ends in October 2022.

## Slide 5: Long story short
Acknowledged the need for a BPM working > 10 GHz (AWAKE Collab. Meeting Sept. 2019)
10 Sep 2019
PTFE results presented (6th AWAKE Instrument Meeting)
22 Jan 2020
Detailed analysis of proton bunch presented (9th AWAKE Instrument Meeting)
6 Oct 2020
- Alumina test results presented
- Proposal for 40 GHz buttons upon AWAKE request (12th AWAKE Instrument Meeting)
22 Jun 2021

## Slide 6: 40 GHz buttons BPM

## Slide 7: The HF-BPM
40 GHz buttons from OMC
Michal obtained DESY permission to adapt and produce the buttons
The design is conical
Purchased 6x buttons mid-August
Lead time 5 months (January)

## Slide 8: WBS

## Slide 9: WBS
Simulations DONE
AWAKE beam
CST model based on OMC mechanical design (based on Manfred’s)
Results with both CLEAR and AWAKE parameters

## Slide 10: WBS
Buttons ordered in August, delivery end of Jan
Body drawings signed on 19 November
Body + support production at CERN main workshop
Same length of ChDR BPMs
Mechanics production

## Slide 11: WBS
Tunnel integration
As for ChDR BPM, beampipe resizing is necessary
Intervention agreed for end of YETS 2021/22

## Slide 12: WBS
A preliminary draft exists
Needs completion, waiting for the inputs on the two that are already ongoing
ECR
Budget was discussed with AWAKE, 60k split AWAKE/BI (email June 24)

## Slide 13: WBS
4x corrugated cables pulled before end of 2021 (joint intervention with ChDR BPM IF cables)
Saved 10k CHF from EN-EL quote
Cabling
TODAY !!
OPTICAL LINE
WAVEGUIDES
CABLES
Many thanks to:
Joel, Karim and Laurent !!

## Slide 14: WBS
In a ‘drift’ we have
  3x eBPM
  1x ChDR BPM
  1x HF BPM
I asked SY/ABT (Vittorio) to compute a ballistic optic where we degauss the magnets in the middle
Test
ChDR BPM
eBPM
eBPM
eBPM
HF BPM
Quad + corrector

## Slide 15: Upcoming actions – HF BPM
Mechanics
Body + support ready for installation end of YETS
Installation + beampipe resizing end of YETS
Installation with 2x blank flanges + 2x buttons
Detection
Basic: bandpass filters + Schottky diodes + scope
Need to procure now to arrive in time
Before the protons come, it is easier to test directly in AWAKE unless we foresee to break the vacuum often

## Slide 16: Summary – HF BPM
Mechanics
We can have 1 plane installed for test by (say) March
4x buttons left for possible testing at CLEAR
Detection
I can work out the basic setup, if I get a bit of supervision by a staff of SY/BI/BP

## Slide 17: Cherenkov Diffraction BPM

## Slide 18: A (much) more complicated system
Front-end electronics box
TO STREAK ROOM
ChDR BPM
ChDR BPM
Front-end electronics box
LO 30 GHz
IF ~2 GHz
HF
HF
TRIUMF design
Front-end electronics box

## Slide 19: Outline
Simulations mostly from Collette up to 50 Ohm coax
Prototype in air tested last spring at CLEAR
See IBIC2021 paper MOPP17
Simulations + prototype test DONE

## Slide 20: Outline
Mechanics production
Buttons ready by end of February
Body + support manufactured and fiducialised
ECR under approval AWK-BPM-EC-0002

## Slide 21: Outline
Installation
Modular approach
  Beampipe resized for BPM#1
  Buttons to be swapped with pBPM for BPM#2
Cables installed
Waveguides partially installed
ChDR BPM1
ChDR BPM2

## Slide 22: Outline
RF Front-end
TRIUMF working on operational electronics
Bandpass filter+diode for our tests
Possible test at CLEAR in parallel with the installation in AWAKE

## Slide 23: Outline
Test
Same test platform of HF-BPM
Possible in AWAKE, at least with demodulation + scope
Detailed plan is now premature

## Slide 24: Upcoming actions – ChDR BPM
Mechanics
Body + support ready for installation end of YETS
Buttons + body assembled and tested prior installation
Installation with 4x buttons
Detection
Basic test: bandpass filters + attenuator + Schottky diodes + scope (basically CLEAR test revival)
TRIUMF electronics when available
Transitions
To be discussed with Nicolas

## Slide 25: Summary – ChDR BPM – In short
Mechanics
Install the upstream body and play with it
We are ready for then turning the pBPM into a ChDR BPM quickly (not before TRIUMF electronics)
Detection
Same as CLEAR in spring
… waiting for TRIUMF electronics

## Slide 26: Summary

## Slide 27: My proposal
HF-BPM
Installation of the body in AWAKE equipped with one plane of buttons (2x buttons + 2x blanks) in March
Initial test with bandpass filters + RF diodes
Parallel R&D in CLEAR with remaining 4x buttons is possible (depending on available workforce)
Before May

## Slide 28: My proposal
ChDR-BPM
Installation of one complete body in AWAKE in March
Basic test at AWAKE similar to last year’s CLEAR test
Parallel R&D in CLEAR with remaining 6x buttons (Collette’s thesis, when ready)
TRIUMF electronics delivery time to be assessed
Before May

## Slide 29: Thanks for your attention !