## Slide 1: Service Management
GLM 15 November 2010
Mats Moller IT-DI-SM

## Slide 2: Topics
Additional resource
  Patricia Mendez Lorenzo (soon)
  Thanks to DHO and ES
Visit from Fermilab 29/11-2/12
  Tim Currie, IT Service Manager
Status/Planning
Acceptance Criteria
  GLM through Tim Bell

## Slide 3: Status
Service Catalogue in Service‐now
  Go‐live planned for 15 November
  Data quality checking as from 16 November
  Service Management team sends feedback and suggestions
  Data improvement to be done by Service Owners & Functional Service Managers
Incident & Request Fulfilment processes
  Development ongoing
Standard ticket templates / Record Producer
  In preparation
  Service management team investigates interaction with Service Owners & Functional Service Managers

## Slide 4: Status
Service Desk (building 55)
  Offices being refurbished
  Staff recruited / Training planned and starting this week
  Service Desk go‐live planned for 1 February
Detailed Tool implementation plan

## Slide 5: Acceptance Criteria
Service Catalogue and Workflows
  SC entries should be complete including all IT customer services and IT functions, consistent descriptions, use of opening/support/service hours, ‘request for’ data and IT 2nd level routing
    Quality check as from this week, Service Owners and Functional Service Managers
  List of tasks which can be performed by service desk agreed with tools, required information and execution instructions provided
    Being compiled. SD will only use Service-now, no other tools
  Request fulfilment processes and workflows documented and agreed including links to existing self-service portals
    Yes, links to be added by SO/FSM
  Define procedure for service desk if the Service-now is not available
    Yes, to be defined

## Slide 6: Acceptance Criteria
Functionality
  GGUS interface implementation plan documented and agreed
    In the plan, target December
  Example operational contract reports such as for Serco should be produced and validated
    In the plan, target December, can only be validated for new processes
  Integrate the IT service status into the service desk or provide notification of status to service desk staff
    Yes, planned
  Web portal templates as provided by each service with required information fields should be integrated into the tool
    Yes, planned

## Slide 7: Acceptance Criteria
Training
  Training session in the procedures and tools for service and function owners to maintain the service catalogue data in Service Now
    Done, more sessions if necessary
  Training sessions organised for the service managers and support staff covering new process workflow, logging in, ticket routing, problem opening and closing and work log updates
    Planned. “Train the Trainer” 9-10 December, User training mid January
  A demo system should be available for a week prior to the go-live with the final configuration and catalogue to allow service managers to become familiar with the tools
    Planned for mid January

## Slide 8: Acceptance Criteria
Testing
  A replay of random IT tickets should be performed through the service desk giving the user initial problem statement, work log updates and closure
    Planned, OIS volunteered
  Authorisation and Authentication tests by a sample of service managers and users
    Planned in Validation Runs
  Validation of web portal and application on CERN’s supported platforms/browsers
    To be defined but no problem foreseen

## Slide 9: Acceptance Criteria
Deployment
  A transition plan should be documented including :
    Handling of tickets which are previously open in PRMS
    How user and automated mails to helpdesk@cern.ch will be handled
    Plan for updates to IT web site that refer to new procedures and tools
    Communication plan for end users
    Service Desk Roadmap circulated to GLM
  Define processes and meetings for IT monitoring and feedback on production service desk
    To be defined

## Slide 10
Feedback on document?
Other questions?