## Slide 1: The Linac4 Project at CERN
M. Vretenar for the Linac4 team
PIMS kick-off meeting 17.11.2010

## Slide 2: LHC Luminosity Upgrade
(*) protons per bunch, in 3 mm emittance
 | Luminosity (cm-2s-1) | Beam intensity @ injection (*)
Present (October 2010) | >2 x1032 | 
Nominal | 1034 | 1.1 x1011
Upgraded | ~5 x1034 | ~2.4 x1011
At the moment, the injectors can provide only the intensity required for the nominal luminosity
Upgrade program to reach ~5 x1034, to be completed by 2020
foreseen in near future
requires upgrade of both LHC and injectors, to be achieved by 2020
Notes: Important parameter is the peak luminosity – most important term on lumi formula is brightness (n. of protons in the given emittance – density of the beam) – density is created in the injector, where we have to fight against space charge (couplomb repulsion).

## Slide 3: Limitations to injector intensity
Three bottlenecks identified for higher intensity from the LHC injectors:
Space charge tune shift at PSB injection (50 MeV).
Space charge tune shift at PS injection (1.4 GeV).
Electron cloud and other instabilities in SPS.
Low injection energy into the PSB is the first and most important bottleneck → decision (2007) to build a new linac (Linac4) increasing injection energy from 50 to 160 MeV (no space for upgrade of Linac2).
Linac4 alone can only allow reaching 1.7x1011 ppp out of the PS (“ultimate” intensity) → need to address the other bottlenecks with a specific program.
Additional steps: a) upgrade of PSB final energy to 2 GeV; b) upgrade (coating, new RF) of SPS.
1
2
3
Notes: No space for energy upgrade

## Slide 4: Linac4 – motivations, parameters
Higher intensity in PSB for the LHC upgrade.
Consolidation: more modern and sustainable machine than Linac2 (worries for long-term operation of Linac2 – vacuum, RF).
Flexible operation and reduced loss with new technologies (chopping, H- injection).
Higher intensity for non-LHC users.
Prepare for a possible high-intensity upgrade (neutrino facility).
Energy 160 MeV  factor 2 in bg2 from Linac2  x2 intensity in PSB with same tune shift (DQ~N/bg2).
Use LEP RF frequency of 352 MHz  recuperate some klystrons and RF equipment.
Repetition frequency 2 Hz (1.1 Hz max. PSB), upgradable to 50 Hz with new power supplies and additional cooling installed.
Beam current 40 mA in 400 ms: >2 present PSB maximum.
duty cycle 0.8x10-3
designed for 10%

## Slide 5: Linac4 description
160 MeV
100 MeV
50 MeV
Conventional (normal-conducting) layout:
Pre-injector (source, magnetic LEBT, 3 MeV RFQ, chopper line)
Three types of accelerating structures at 352 MHz (for optimum efficiency at a standardised RF frequency). Focusing by a combination of permanent and conventional quadrupoles.
Beam dump at linac end, switching magnet towards transfer line – PSB.
Transfer line to PSB
Linac length ~ 80 m
3 MeV

## Slide 6: Linac4 civil engineering
ground
Overall floor surface of Linac4 installations = 3’305 m2 (over 4 levels)

## Slide 7: Linac4 groundbreaking
Groundbreaking (and start of civil engineering works) 16.10.2008
1 year and 4 months after approval of the project

## Slide 8: Building construction
“Mount-Citron”, September 2008

## Slide 9: Construction status
Civil engineering completed (in exactly 2 years!).
Installation of infrastructure (crane, lift, false floor, electrical and cooling networks, safety equipment, cabling, waveguides, …) during 2011.

## Slide 10: Linac4 – schedule
Building delivery
2011:
Infrastructure installation
2012/13:
Accelerator installation
2013/14:
Commissioning
2014/15:
Reliability run
End 2014:
Linac4 ready
2016: foreseen shutdown for connection to PSB

## Slide 11: Linac4 – Low energy test stand
Ion source and beam transport assembled and under test.
Radio Frequency Quadrupole being built at CERN (2011).
Chopping line built and tested (w/o beam).
LEP klystron (+ modulator) installed, tested in pulsed op.
Testing of RF structures (PIMS prototype) at 2 Hz.
3 MeV TEST STAND in the PS South Hall

## Slide 12: Linac4 – Drift Tube Linac
3-50 MeV, 3 tanks.
Design Completed and tested on a prototype (1m, 12 drift tubes) at full RF power (10% duty cycle).
Main features: DTs rigidly mounted on a girder, with special mounting mechanism, only metallic joints and no adjustment. Tank in Cu-plated Stainless steel. PMQs in vacuum.
Construction started (DTs with ESS-Bilbao).
Tank1 ready for test in 2011.
Important improvements with respect to present DTL linacs (1 patent pending)

## Slide 13: Linac4 – Cell-coupled DTL
50-100 MeV, 7 modules of 3 tanks each.
Design completed and tested on a prototype (2 tanks, 4 drift tubes) at full RF power (10% duty cycle).
Main features: Focusing by PMQs (2/3) and EMQs (1/3) external to DTs. Tanks with 2 DTs connected by coupling cells.
Construction started at VNIITF (Snezinsk) and BINP (Novosibirsk) in January 2010.
Module#1 to be delivered to CERN for testing in January 2011.
Structure used for the first time in a particle accelerator

## Slide 14: Linac4 – Pi-Mode Structure
100-160 MeV, 12 tanks of 7 cells each.
Design completed, tank #1 completed and tuned, tested (to this week!) at full RF power.
Main features: Focusing by external EMQs, tanks of 7 cells in pi-mode. Full-Cu elements, EB-welded.
Construction will start at beginning 2011 in collaboration with Soltan Institute (Warsaw) and FZ Julich.
Structure used for the first time in a proton accelerator

## Slide 15: Accelerating structures
Construction of the Linac4 accelerating structure – an European enterprise (and beyond…)
Drift Tube Linac (DTL):
prototype from INFN/LNL (Italy), drift tubes from ESS-Bilbao (Spain), tanks and assembly at CERN
Cell-Coupled DTL:
tanks from VNIIEF (Snezinsk), drift tubes and assembling from BINP (Novosibirsk)
PI-Mode Structure (PIMS): tanks from Soltan Institute (Poland), EB welding from FZ Juelich (Germany), assembly and final EB welding at CERN.
Notes: Distribute the work but keep control… integration at the component level.

## Slide 16: Linac4 – External Contributions
H
-
source
RFQ
DTL
45 keV 3 MeV 50 MeV 100 MeV 160 MeV
chopper line
CCDTL
PIMS
transfer line to PSB
LEBT
80 m
Chopper line built in a EU Joint Research Activity
completed
Participation of ESS-Bilbao in DTL construction,
started
Construction of CCDTL in Russia, via an ISTC Project
started
Collaboration agreement with Soltan Institute (Poland) and FZ Julich (D) for PIMS construction, in preparation.
Transfer line vacuum chambers and supports from Pakistan, agreed
Prototype modulator, RF tuners, couplers, waveguides from India, in progress
RFQ RF design, RF amplifiers, modulator construction from French Special Contribution. started.
Network of agreements to support Linac4 construction. Relatively small fraction of the overall budget, but access to specialized manpower !
Integration at the component level.
Agreement with DESY to access drawings of H- source
completed

## Slide 17: Linac4 – virtual tour