## Slide 1: LBNF/DUNE Reviews Update
Mary Bishai
April 5, 2022

## Slide 2: New Recommendation Tracking Form
DUNE FD1/FD2 LArASIC PRR Recommendation Tracking |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SubProject | System | Subsystem | Review Type | Review Title | DATE Format: 1-Jan-70 | REVIEW # | Recommendation # | RECOMMENDATION DESCRIPTION | OWNER | RESPONSE | Status per subsystem manager (New, In-Progress, Completed,For Future,Declined) | SCHEDULED CLOSE DATE (Subsystem Manager) Format: 1-Jan-70 | ACTUAL CLOSE DATE (Subsystem Manager) Format 1-Jan-70 | RECOMMENDATION STATUS per RO (Accepted, For Future, Incomplete) | RO Comment | Recommendation Status per - Senior Project Management (In-complete, For Future, Closed)
FD1-HD | TPC Electronics | LArASIC | PRR | Production Readiness Review of the DUNE LArASIC | 7-Mar-22 |  | 1 | LArASIC performance and FEMB integration tests: Use the current reticle for launching production. | Cheng-Ju-Stephen Lin cjslin@lbl.gov |  |  |  |  |  |  | 
FD1-HD | TPC Electronics | LArASIC | PRR | Production Readiness Review of the DUNE LArASIC | 7-Mar-22 |  | 2 | LArASIC performance and FEMB integration tests: Set up and conduct a lifetime test in LN2 either with chips or with an FEMB board. This recommendation can be completed after the wafers order is released. | Cheng-Ju-Stephen Lin cjslin@lbl.gov |  |  |  |  |  |  | 
FD1-HD | TPC Electronics | LArASIC | PDR | Production Readiness Review of the DUNE LArASIC | 7-Mar-22 |  | 3 | LArASIC procurement plan: Proceed to order 10 LArASIC wafer lots, 25 wafers/lot for a total of 250 wafers. | Cheng-Ju-Stephen Lin cjslin@lbl.gov |  |  |  |  |  |  | 
FD1-HD | TPC Electronics | LArASIC | PRR | Production Readiness Review of the DUNE LArASIC | 7-Mar-22 |  | 4 | LArASIC procurement plan: Work out the delivery schedule with TSMC. | Cheng-Ju-Stephen Lin cjslin@lbl.gov |  |  |  |  |  |  | 
FD1-HD | TPC Electronics | LArASIC | PRR | Production Readiness Review of the DUNE LArASIC | 7-Mar-22 |  | 5 | LArASIC procurement plan: Work out the packaging schedule and strongly consider getting the packaging done on a lot basis. | Cheng-Ju-Stephen Lin cjslin@lbl.gov |  |  |  |  |  |  | 
FD1-HD | TPC Electronics | LArASIC | PRR | Production Readiness Review of the DUNE LArASIC | 7-Mar-22 |  | 6 | LArASIC procurement plan: Strengthen and document the narrative to properly justify the yields, risks and therefore the required number of procured lots. | Cheng-Ju-Stephen Lin cjslin@lbl.gov |  |  |  |  |  |  | 
Automated system may take a while, so currently auditing and manually tracking using new agreed upon sign off procedure and EDMS forms. Links to EDMS tracking forms added to sharepoint lists working backwards from PRR. See sharepoint link here for FD1 FDR, PRR recommendation tracking links

## Slide 3: Automated Recommendation Tracking System (A. Heavey)
Requirements:
Correlated lists: Reviews, Recommendations
Several fields auto-populate in Recommendations list according to most recent recommendation entered:
Review Number,
Review Title,
Subproject,
System,
Review Type,
Review Start Date
Usable by the RO members, admins, recommendation owners, senior project staff -- for different stages of addressing the recommendations and approving the responses.

## Slide 4: Automated Recommendation Tracking System
Workflows:
Send email to recommendation owner if scheduled close date is within N days after "today" and actual close date field is null.
If all recommendations for a given review are "closed" (approved by senior management or delegate), update the review's status in Reviews list to "closed".
If all recommendations for a given review are either "closed" or "for future"; update the review's status in Reviews list to "provisionally closed".
If any recommendation for a given review is anything except "closed" or "for future"; set the review's status in Reviews list to "recommendation tracking".
Run workflows one or two times/week.

## Slide 5: Recommendation Tracking System

## Slide 6: Status of Automated Tracking System
Status:
Reviews and Recommendations lists exists in live site but will require modifications to accommodate this implementation.
The live site was copied to a development site.
We split required functionality into two tasks: recommendations entry forms and workflow.
In development site:
Created/copied several lists
  Reviews
  Recommendations (allows multiple recommendations associated with each review)
  Subproject (provides choice list of subprojects for a review)
  System (provides choice list of systems for a review)
  Review Type (provides choice list of review types -- e.g., CDR, PDR,... -- for a review)
(In progress) Creating form "A" to allow entry of the first recommendation for a given review; this form is simple:
  it includes all required fields, and
  all fields are manual entry (some from "lookup" choice list).
  may develop as upgrade: manually enter Subproject and System (from "lookup" choice list) to provide narrowed list of Review Numbers to choose from.
Added a yes/no "Select" field to the Recommendations list.
Created form "B" for entry of subsequent recommendations for a given review; it has extra functionality:
  it looks like form A, but many fields auto-populate, per requirement
  it populates with the values in the fields of the "Select=yes" recommendation
Email workflow is under development
Review list status field update workflow has not been started. Flowchart of functionality has been agreed on.

## Slide 7: FD1-HD Planned/Future Reviews
Subproject | System | Title | Review Type | Link to Review Site | Start Time | Status
FD1-HD | DSS | DUNE FD1 DSS - tentative | PDR |  | 5/10/2022 8:00 | Initiated
FD1-HD | HV Systems | FD1-HD HV System FDR (tentative) | FDR |  | 6/21/2022 8:00 | Initiated
FD1-HD | TPC Electronics | DUNE FD1-HD TPC Electronics FDR | FDR |  | 8/23/2022 8:00 | Initiated
FD1-HD | Photon Detection | FD1-HD PDS FDR (tentative) | FDR |  | 9/13/2022 8:00 | Initiated
FD1-HD | Photon Detection | FD1-HD DUNE PDS SiPM PRR | PRR | ​Indico 51321​ | 10/11/2022 8:00 | Initiated
FD1-HD | Installation | FD1-HD Installation FDR (tentative) | FDR |  | 11/22/2022 8:00 | Initiated
List of future reviews can be obtained here

## Slide 8: FD2-VD Planned/Future Reviews
Subproject | System | Title | Review Type | Link to Review Site | Start Time | Status
FD2-VD | CRP | DUNE FD2-VD CRP PDR | PDR | Indico 53111 | 3/29/2022 7:30 | Awaiting Report
FD2-VD | HV Systems | FD2-VD HV System PDR | PDR | Indico 53541​ | 4/19/2022 8:00 | Schedule Finalized
FD2-VD | TPC Electronics | FD2-VD BDE PDR | PDR | ​Indico 53544​ | 4/25/2022 8:00 | Schedule Finalized
FD2-VD | Photon Detection | FD2-VD Photon System PDR | PDR | Indico 53542​ | 5/4/2022 8:00 | In Planning
FD2-VD | TPC Electronics | FD2-VD TDE PDR | PDR | ​Indico 53543​ | 5/17/2022 8:00 | In Planning
FD2-VD | Installation | FD2-VD Installation PDR (tentative) | PDR | ​Indico 53545​ | 6/15/2022 8:00 | Initiated
FD2-VD | TPC Electronics | FD2-VD BDE FDR | FDR |  | 10/18/2022 8:00 | Initiated
FD2-VD | TPC Electronics | FD2-VD TDE FDR | FDR |  | 10/25/2022 8:00 | Initiated
FD2-VD | CRP | FD2-VD CRP FDR (tentative) | FDR |  | 11/1/2022 8:00 | Initiated
FD2-VD | HV Systems | FD2-VD HV System FDR (tentative) | FDR |  | 11/8/2022 8:00 | Initiated
FD2-VD | Photon Detection | FD2-VD PDS FDR (tentative) | FDR |  | 12/6/2022 8:00 | Initiated
FD2-VD | Installation | FD2-VD Installation FDR (tentative) | FDR |  | 12/13/2022 8:00 | Initiated
List can be obtained here