## Slide 1: BGC Brief status Ray VENESS

## Slide 2: Impact of the war in Ukraine on the project
The main magnet system for the Hollow E-lens is planned as a fully in-kind contribution from Russia
Cooperation agreements are currently suspended
  Further decisions will be made in the June Council meeting
This has an immediate effect on the HEL project
No immediate effect on the BGC (in-kind contribution via HL-UK2)
  Long-term impact may be seen in the coming months
Statement by the Director General to CERN Personnel on Friday 25th March 2022 [excerpt]:
The CERN Council also decided that, with a view to making a decision at its Session in June 2022 on the suspension of the international cooperation agreements and the related protocols and addenda…, allowing for the participation of the Russian Federation and the Republic of Belarus, their national institutes and JINR in the CERN scientific programme, the Council will consider additional information and an action plan, and will further analyse the full consequences of such a decision.
From: BGC Collaboration meeting. March 2022
https://indico.cern.ch/event/1134241/

## Slide 3: Some key discussions and decisions for this meeting
LHC background gas fluorescence tests
  Ondrej/Stefano presents the test programme
    What can we learn for the BGC design from these key early tests?
    What are the best- and worst-case scenarios (expectation management!)
HEL test stand
  Presentation of the current schedule and test programme
    When will we put the BGC v3 on the stand? What can we do beforehand?
    What do we need to learn from this programme and what are the limitations we should expect?
LHC machine compatible Vacuum control system.
  This is likely to be the critical path to installing the v3 in the LHC
    What can we do to help VSC with their work?
    What tests and validations will we need to make on the HEL test stand and when?
From: BGC Collaboration meeting. March 2022
https://indico.cern.ch/event/1134241/

## Slide 4: Project roadmap (March 2022)
2020
2021
2023
2022
Install the v3 interaction chamber in the LHC
Long shutdown 2 (for the LHC)
YETS
LS3
Install the complete v3 instrument in the LHC
v3 commissioning & experimental programme in the LHC
Modify optics and gas injection for a new background gas measurement
Background gas tests
Continue tests with v2 or v2++ at CI
2024
YETS
v3 commission at CI
Integrate and test ‘Unit-1’ at CERN
v3 install + test on HEL stand
LHC
Surface
Commission and test ‘Unit-1’ at CI
Done
Ongoing
Done
Delay another year? To be agreed in this meeting?
2025
Done
EYETS
What do we do here?
Ukraine impact?: Not for today…
From: BGC Collaboration meeting. March 2022
https://indico.cern.ch/event/1134241/

## Slide 5: Project Management: BI view
Safe operation of the LHC vacuum system is the responsibility of VSC(!)
The technical work package is agreed between VSC (WP12) and BI (WP13)
  The overall project scope and budget was presented and discussed in the HEL kickoff meeting in April 2021
    https://indico.cern.ch/event/1014640/
  We are now here to agree the details and organize the technical project follow-up
The budget comes directly from HL-LHC to VSC (WP12)
  Budget is managed by VSC (WP12)
  BI (WP13) do not plan to follow-up or control the budget
  BI (WP13) do not have any additional budget for this in case of overspend
Any extra money needs to come from the HL project
  Any changes of scope, along with any cost impact need to be carefully agreed