## WP13 BGC
WP13 - BGC
https://edms.cern.ch/document/2489128/1 |  | FSU CHF/h | 60
221 working days
New MKB tanks (cost for 2 units) | Quantity | Unit Price (CHF) | Design | [5 empty] | Fabrication | [7 empty] | Testing |  |  |  |  | Installation |  |  |  |  | From | To | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026
|  |  | Study | Prototyping |  |  |  |  | HW | Assembly | Surface treatment | Bake-out |  |  |  |  | Material |  |  |  |  | Material | [22 empty] | LS3 |  |  |  | LS3
|  |  | CHF | CHF | FTE/y | FSU (CHF) | IS (CHF) | MPA (CHF) | CHF | CHF | CHF | CHF | FTE/y | FSU (CHF) | IS (CHF) | MPA (CHF) | CHF | FTE/y | FSU (CHF) | IS (CHF) | MPA (CHF) | CHF | FTE/y | FSU (CHF) | IS (CHF) | MPA (CHF) |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
BGC Master PLC (GRC) | 1 | 2400 | [6 empty] | 2400 |  |  |  |  | 1440 |  |  |  |  | 240
SVCU Card | 2 | 300 | [6 empty] | 600 | bar: LS3 Q1 to LS3 Q4
SVCU_L crate | 1 | 1800 | [6 empty] | 1800 |  |  |  |  | 1680 |  |  |  |  | 240 | bar: LS3 Q1 to LS3 Q4
SVCU Communication card Profibus | 1 | 1000 | [6 empty] | 1000 | bar: LS3 Q1 to LS3 Q4
BTK Card | 1 | 300 | [6 empty] | 300 | bar: LS3 Q1 to LS3 Q4
1U interlock crate and related cables | 2 | 900 | [6 empty] | 1800 |  |  |  |  | 720 |  |  |  |  | 120
Piezo gauge controller | 1 | 3250 | [6 empty] | 3250 |  |  |  |  | 960 |  |  |  |  | 60
TPG300 controller | 0 | 900 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
Pirani/Penning Card | 0 | 1020 | [6 empty] | 0 | [9 empty] | 0
Profibus card | 0 | 745 | [6 empty] | 0 | [9 empty] | 0
Dual TPG300 Crate | 0 | 350 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
VPGF PLC controller (without TCP350) | 3 | 2600 | [6 empty] | 7800 |  |  |  |  | 5760 |  |  |  |  | 180
VRPPH (Primary Pump) controler | 1 | 900 | [6 empty] | 900 |  |  |  |  | 960
Local crate R2E type | 5 | 700 | [6 empty] | 3500 |  |  |  |  | 9600 |  |  |  |  | 300
Rack 16U | 1 | 800 | [6 empty] | 800
VPG Platines and B50 cable | 5 | 150 | [6 empty] | 750 |  |  |  |  | 2400 |  |  |  |  | 300
LHC: Inter-rack cabling (ICM) | 1 | 1500 | [6 empty] | 1500
LHC: Rack UPS power multisocket (EN/EL) | 2 | 1000 | [6 empty] | 2000
LHC: Rack VRPPH power socket | 1 | 400 | [6 empty] | 400
LHC: Ethernet sockets (EN/EL) | 2 | 600 | [6 empty] | 1200
LHC: Additional cabling | 1 | 4550 | [6 empty] | 4550
Test stand: Cables (ICM) | 28 | 220 | [6 empty] | 6160
Test stand: Ethernet sockects (EN/EL) | 6 | 600 | [6 empty] | 3600
Test stand: Rack | 2 | 1500 | [6 empty] | 3000
Procurement of materials from FSU | 24 | [12 empty] | 1440
Test stand: Cabling installation FSU | 80 | [22 empty] | 4800
Test stand: Installation and commissioning FSU | 80 | [22 empty] | 4800
LHC: Installation and commissioning FSU | 120 | [22 empty] | 7200
Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 47310 | 0 | 0 | 0 | 0 | 24960 | 0 | 0 | 0 | 0 | 1440 | 0 | 0 | 0 | 0 | 16800 | 0 | 0
TOTAL w/o manpower CHF | 47310
Total FSU (CHF) | 43200
TOTAL IS (CHF) | 0
TOTAL MPA (CHF) | 0
Common HW | 24900
Common FSU | 26400
LHC specific HW | 5100
LHC specific FSU | 7200
Test stand specific HW | 12760
Test stand specific FSU | 9600
Note on C13: Nikolaos Chatzigeorgiou: HW + cables and connectors
Note on A15: Lampros Zygaropoulos: Already bought BC: 64062
Note on A16: Lampros Zygaropoulos: Already bought BC: 64062
Note on A17: Lampros Zygaropoulos: Already bought BC: 64062
Note on A18: Lampros Zygaropoulos: Already bought BC: 64062
Note on A19: Lampros Zygaropoulos: 2 pcs already bought BC: 64062
Note on J27: Nikolaos Chatzigeorgiou: 1200 CHF per 2 sockets
Note on A28: Lampros Zygaropoulos: Piezo Controler: NG4 X1 800CHF Pirani Gauge: NG4 X 1 800CHF Inj. Valves: NE8 X 3 or NE28 1500CHF Inj. Primary Pump: PJ3SJ X 1 800CHF Rack Grounding: 250CHF Bottle pressure cable NG4: 400CHF
Note on C29: Nikolaos Chatzigeorgiou: 11 chf/m 20 meters estimation

## Notes
| BGC - Gas injection |  |  | LHC beam vac | DUMP
| Vol1 | Vol2 | Vol3
GAUGES | Active Membrane Gauge
| Penning | Penning | Penning | Penning | Penning | 1 - the back valves could be a block
| Pirani |  | Pirani |  | Pirani | 2- redundances of the valves coudl be removed even on LHC beam vacuum
GATE VALVE | - | - | - | GATE VALVE DN100 | GATE VALVE DN63 | 3 - primaries baseline, RV12: could be swapped to ACP but after lab tests here at CERN
TMP | Hipace 300 - CF - 1000m | Hipace 300 - CF - 1000m | Hipace 300 - CF - 1000m | Hipace 300 - CF - 1000m | Hipace 300 - CF - 1000m | 4 -primaries & pumping groups simplification possible after testing in lab with a different sequencing --> contact Gregory
VVT - venting turbo | VAT - Angle valve DN16KF | VAT - Angle valve DN16KF | VAT - Angle valve DN16KF | VAT - Angle valve DN16KF | VAT - Angle valve DN16KF
VVD - leak detector | VAT - Angle valve DN25KF | VAT - Angle valve DN25KF | VAT - Angle valve DN25KF | VAT - Angle valve DN25KF | VAT - Angle valve DN25KF
VVI - valve to primary | VAT - Angle valve DN25KF | VAT - Angle valve DN25KF | VAT - Angle valve DN25KF | VAT - Angle valve DN25KF | VAT - Angle valve DN25KF
VVP - venting primary | VAT - Angle valve DN25KF | VAT - Angle valve DN25KF | VAT - Angle valve DN25KF | VAT - Angle valve DN25KF | VAT - Angle valve DN25KF
Primary pump | Edwards - RV12 | Edwards - RV12 | Edwards - RV12 | Edwards - RV12 | Edwards - RV12