## Slide 2
Menu
Starter
Main course
Desserts
Digestives
Reminder on Injectors complex,
on Machine Interlocks,
on current installations.
Future deployments for the WIC system Future deployments for the BIS
Resources and possible issues
None !
Wrap-up

## Slide 3: What do we call “Injectors”?
In the future:
  Booster upgrade
  Linac4
  Elena ring
  HIE-Isolde
  … PS2 ?
Other machines & facilities:
Isolde
AD
N-ToF
CTF-3
TT41 line (CNGS)
SPS North area
…
Transfer line
In the coming months:
TT66 line (HiRadMat)
3MeV Test Stand of Linac4
P Injectors chain: Linac2  Booster
TT40 & Ti8 lines
TT60 & Ti2 lines
TT2
Transfer line
Ions Injectors chain : Linac3  LEIR

Transfer line
PS  SPS

Transfer line

## Slide 4: What are the “Machine Interlocks”?
Powering Interlock Controllers
(PLC based)
Beam
Interlock
System
(VME based)
Warm magnet
Interlock
Controllers
(PLC based)
for protecting Super Conducting Magnets
and Normal Conducting Magnets
Fast Magnet Current change Monitor
for protecting the Equipments
for Beam Operation
+
Safe Machine Parameters System
(VME based)
BIS
SMP
FMCM
PIC
WIC
+

## Slide 5: Common Approach
Projects
Design
RS422
PIC
BIS
WIC
FMCM
SMP
Fail Safe concept
Reliability vs. Availability
Redundancy
Maintainability
Critical functions in Hw
Pre operational checks
Full online consistency monitoring during operation
Post operational checks
+

## Slide 6: Machine Interlocks Hierarchy
LHC layout
( MPE systems shown in red )

## Slide 7: already deployed in the Injectors…
YES
YES
YES
YES
TT41 line (CNGS)
Linac2  Booster  PS  SPS
TT40 & Ti8 lines
TT60 & Ti2 lines
Linac3  LEIR
no
YES
YES
FMCM
YES
no

no
no
FMCM
no
no
FMCM
no
no
FMCM
WIC
BIS
SMP
FMCM
YES
no
WIC
BIS
PIC
Except these ones, MI systems not deployed in other machines & facilities of the complex, like Isolde,
AD,
N-ToF,
CTF-3,…

## Slide 8: Future deployments of the WIC system
Machine | Number of |  |  | Installation date
 | Protected Magnets | PLC crate | Remote I/O crates | 
HiRadMat | 25 | 2 | 2 | Jan. 2011
Booster | 172 | 4 | 53 | during 2011 + Xmas 2011/12
Linac4 & Transfer line | 98 | 2 | 6 | 2013/2014
Isolde | 17 | 1 | 2 | not yet known
Elena ring | 48 | 1 | 1 | not yet known
PS main | 100 | 1 | 11 | not known
PS Auxiliary | 50 | 2 | 1 | not known
SPS ring +auxiliaries | 900 | 9 | 15 | Deployment not approved
Machine | Number of |  |  | Installation date
 | Protected Magnets | PLC crate | Remote I/O crates | 
HiRadMat | 25 | 2 | 2 | Jan. 2011
Machine | Number of |  |  | Installation date
 | Protected Magnets | PLC crate | Remote I/O crates | 
HiRadMat | 25 | 2 | 2 | Jan. 2011
Booster | 172 | 4 | 53 | during 2011 + Xmas 2011/12
Linac4 & Transfer line | 98 | 2 | 6 | 2013/2014
Machine | Number of |  |  | Installation date
 | Protected Magnets | PLC crate | Remote I/O crates | 
HiRadMat | 25 | 2 | 2 | Jan. 2011
Booster | 172 | 4 | 53 | during 2011 + Xmas 2011/12
Linac4 & Transfer line | 98 | 2 | 6 | 2013/2014
Isolde | 17 | 1 | 2 | not yet known
Elena ring | 48 | 1 | 1 | not yet known
Notes: HiRadMat :
25 aimants à protéger – (41 entrées, Elettas + câbles refroidis + aimants)
2 PLC (BA6 et BA7)
2 unités déportées
Installation 2ème quinzaine de janvier
Booster :
172 aimants à protéger environ
4 PLC (1 pour les aimants principaux et 3 pour aimants auxiliaires
53 unités déportées
Installation durant 2011 et durant Xmas 2011/2012
PS Main :
100 aimants à protéger
1 PLC
11 unités déportées
Installation non définie
PS auxiliaires :
50 aimants à protéger – (41 entrées, Elettas + câbles refroidis + aimants)
2 PLC
1 unité déportée
Installation non définie
Linac4 et ligne de transfert :
98 aimants à protéger – (Refroidis à air et à eau)
2 PLC (Linac4 et TL)
6 unités déportées
Installation 2013/2014
Rex-Isolde :
17 aimants à protéger
1 PLC
2 unités déportées
Installation non définie
SPS Ring + auxiliaires
900 aimants à protéger environ
9 PLC
15 unités déportées
Installation AZAP
Peut-être faut-il aussi parler du futur ring Elena ?
48 aimants à protéger – (Ring + TL)
1 PLC
1 unité déportée
Installation non définie

## Slide 9: Future deployments of the BIS
Machine | Number of |  | Installation date
 | User Interface | Controller | 
HiRadMat | 10 | 1 | Jan. 2011
3 MeV Test Stand (*) | 7 | 1 | during 2011
Linac4 & Transfer line | 23 | 3 | 2013/2014
Booster ring & ejection | 24 | 2 | 2015?
(*) low energy part of future Linac4
Machine | Number of |  | Installation date
 | User Interface | Controller | 
HiRadMat | 10 | 1 | Jan. 2011
3 MeV Test Stand (*) | 7 | 1 | during 2011
Machine | Number of |  | Installation date
 | User Interface | Controller | 
HiRadMat | 10 | 1 | Jan. 2011

## Slide 10: Straight forward activities?
WIC deployment:
  1 Staff + 1 FSU member: Preparation, Procurement, Test, Installation, & Commissioning
  Support from EN/ICE (PLC software + PVSS)
  Support from BE/CO (Configuration DB)
BIS deployment:
  1 Staff + 1 FSU member: Prep., Procurem., Test, Installation, & Commissioning
  1 student (FESA class, SW configuration, DB,…)
  Support from BE/OP (Java application)
  Support from BE/CO (Configuration DB)
Enough resources?
Technical issues?
WIC : compatibility between Siemens items
BIS : future HW no longer “identical” to current one?
  New VME system (new CPU, new OS, new crate, new Power supply…)
  Obsolescence of components
see 1st talk of session#3

## Slide 11: “MI in the injectors”: Wrap-up
Resources
  Rely on support from external manpower: FSU, Fellows, Students, EN/ICE group,…
  Minimal level of staffing for the coming deployments (and subsequently the maintenance)
  Not possible to tackle large installations in the near future
Few MI systems already present in Injectors complex.
But not uniformly installed:
  BIS deployed in SPS transfer-lines to LHC & CNGS and in SPS-ring
  WIC deployed in SPS transfer-lines to LHC & CNGS (but not in SPS-ring),
  and also in LINAC3 & LEIR.
Next deployments:
  2011 => HiradMat ( BIS + WIC ), 3MeV Test stand (BIS) and Booster ( BIS + WIC )
  Later on: Linac4 ( BIS + WIC ), HIE-Isolde ( WIC + PIC?), Elena ring ( WIC ),….
Foreseen to be expanded with “copy/paste” LHC solution
  But possible issues with backward compatibility and with components obsolescence
What about “piquet” type?

## Slide 13: Spare slides

## Slide 14: WIC Principle
based on Safety* PLC
collects inputs from:
- thermo-switches,
- flow meters,
- red buttons, …
gives Power Permit for the corresponding converter
Magnet 1
Power Converter
Magnet 2
PC Status
Thermoswitches
Water Flow
Red button…
Several thermo-switches @ 60°C
Power Permit
PVSS
Operator Console
Configuration File
PLC + I/Os
Ethernet
Beam Permit
BIS interface
(*) the Transfer Lines WIC (the first one that has been deployed) is not based on Safety PLC
WIC solution = PLC crate + remote I/O crates
Profibus
remote I/Os

## Slide 15: Magnets in the LHC Injectors

## Slide 16: BIS simplified layout
User Interfaces
User
Permit
#1
#14
#2
(installed in User’s rack)
Beam Interlock Controller
(VME chassis)
copper cables
User System #1
User System #2
BIS Hw = User Interfaces + Controller(s)
Technical
Network
User System #14
front
rear
FESA class
Beam
Permit
Loops
(F.O.)
JAVA
Application
copper cables
or
fiber optics links
based on fast electronic
Collects Permits inputs from User Systems
Gives Permit for beam operation

## Slide 17: BIS boards
~20 types of boards
have been designed
CIBUD & CIBUS
CIBD
CIBM
CIBT
CIBMD & CIBTD
CIBE
CIBPL & CIBPS
CIBO
CIBG
CIBI
CIBS
CIBFu & CIBFc
CIBX

## Slide 18: HiRadMat

## Slide 19: Linac4

## Slide 20: 3MeV Test Stand