## Slide 1
TE-MSC Magnet Group
Fusillo CCT Coordination Meeting #01, 4th May 2022
By Arnaud Foussat (TE MSC-SMT), Davide Tommasini (MSC-GLO)
on behalf of Fusillo Project team
indico.cern.ch/event/1157332/
Fusillo provisional project schedule, Milestones

## Slide 2: Timeline & Assumptions
Timeline of Fusillo dipole project is further developed over 24 months span based on last scope proposal report (March 2022). The provisional schedule was elaborated based on a start date beg March 2022 following similar logic of minimum set of Milestones ( review meetings) and Deliverables ( technical reports ) along timeline.
“Proposed Project activity consists of the design, manufacture and test of a technology demonstrator for strongly bent Canted Cosine-Theta (CCT) superconducting dipoles. The Project will also enable internalization and perpetuation of developed CCT design tools.”
Provisional schedule assumes step approach for the program with T0 from beg March 2022.
Milestones and deliverables over three Workpackages to validate each phase and outcomes.
The early specification design phase (WP1), through technology demonstrators manufacture & test ( WP2) followed by Fusillo construction and test (WP3) assumes a degree of parallel tasks which requires integrated resourced workpackages
Adjustment of tasks durations shall be refined based on placeholders feedback.

## Slide 3: Description of the work packages
WP1 : Specifications for the magnet demonstrator and preliminary conceptual design
WP2 : Design, manufacture and test of technology demonstrators
  Sub-scale models
  Small scale demonstrator models
WP3 : Design manufacture and test of Fusillo dipole
  Full-size Fusillo dipole demonstrator

## Slide 4: Milestones and deliverables
ID | Description | Time
M1.1 | Preliminary Functional specifications of the demonstrator | T0+3
D1 | Preliminary conceptual design of the demonstrator | T0+7
M2.1 | Execution of a technology development and subscale | T0+12
D2 | Review of the technology and subscale program | T0+13
M3.1 | Engineering design of Fusillo | T0+15
M3.2 | Completion of the manufacture of Fusillo | T0+22
M3.3 | Readiness of the magnetic measurement system | T0+23
D3 | Report on Fusillo cold tests and magnetic measurements | T0+24
Notes: Up to 4 deliverables per design workpackage

## Slide 5: WP1,2 Milestones & Deliverables

## Slide 6: WP3 Milestones & Deliverables

## Slide 7: Summary
Provisional schedule of the Fusillo project phases drafted with main Milestones and Deliverables over 24 months, T0 from March 2022;
Main procurement scope and milestones identified ( SC Cable, formers, structure)
Pending Milestones and deliverables definition for the Spanish collaboration packages;
Next resource loaded schedule with check of compatibility with budget allocation and expected FTEs.y, including last inputs from proposed outsourced tasks contributions ( Spanish collaborators, industries).
Provisional schedule https://indico.cern.ch/event/1157332/ (pdf available)

## Slide 8
Thank you, any questions ?