## 시트 1
Schedules | Sep. 2015 (Kobe)
Jun. 2016 (Berkley)
Jul. 2017 (Utrecht)
HIM 2017-08: Organization (LOC-ROC-IAC)
SQM2021 IAC: Jan 2019
SQM Logo: Aug. 2019
SQM2021 Outline: Aug. 2020
SQM2021@BNL / SQM2022@Busan: Nov. 2020
SQM2021 LOC Meetings: Jan. - May 2021
SQM2021@BNL (Online Only): May 17 - 22, 2021
SQM2022@Busan: BTO 홍보지원금 신청 (May 23, 2021)
Jun. 2021: SQM2022 PLOC 1st meeting
Jul. 2021: SQM2022 Sponsor mail
Jul. 2021: SQM2022 LOC 1st meeting
Aug. 2021: SQM2022 Dates fix / Paradise Venue 계약추진 / SQM2022 법인등록
SQM2022 (P)LOC (bi-)Weekly meeting: Oct.06 - 32회 개최
Dec. 10, 2021: 1st announcement
Feb. 02, 2022: SQM2022-IAC 1st meeting
Feb. 10, 2022: 2nd announcement
Abstracts/support submission: 3 months ahead
Review & Decisions: < 2 months ahead
Deadlines: Abstract / Support decisions
Jun. 10: Final announcement
Organizations: PLOC - LOC - ROC - IAC | PLOC (PNU, PKNU…): 100
LOC: 50
ROC: 0 ➔ non-used / needed?
IAC 10
Conference Style: Offline only / Online only / Hybrid
any other possibility? if it were in-person only?
Estimation impossible ➔ NO MORE recommendable
Number of participants
135 (in-person) + 191 (online) = 326
(> 270 in Bari, only in-person)
more in-person? E-KAT … VISA?
any problem with online ↔︎ offline?
Diversity? 41 countries / > 20% females
Scientific Program (Length, contents?)
Overview (25’): default / Theory?
Plenary (25’): too few recommendations
Summary (50’):
Parallel (20’)
Poster (online only): too few participants
NOT much response, why?
Social Program
Reception: Meal / program?
Public: NO record?
Banquet: Meal / program
NO excursion!
Venue
Conference Room
Meal: Lunch / Coffee / Vegan?
Banner / Plancard
accommodations (LOC room / night)
Finance
Sponsors
Registration fee
Expense
PCO & TSM
supports: Registration / Travel
any problem with payment? (money transfer?)
Skills
Webpage / Indico / Bulletines
Zoom / Audio / Video
LOC Secretariat
Documentary
Finance
Staffs
TOTAL