## Slide 2: How to follow-up a service contract (RACI Matrix)

## Slide 3: Introduction
Internal audit: Procurement Service to create guidelines (RACI matrix) on the role and responsibilities of technical officer for management of service contracts
Working group created included HSE and representative service contract managers
Document based on best practices

## Slide 4: Definition of technical officer
For the present RACI, the technical officer comprises
Any person helping him/her to supervise the performance of the services
The technical responsible identified in the contract
+

## Slide 5: Legend

## Slide 6: Summary

## Slide 7: BEFORE CONTRACT START
The technical and procurement officers shall monitor the implementation of the contract before its start.

## Slide 8: Kick-off meeting
Nominate CERN’s and contractor’s contacts
1
2
3
4
5
6
7
8
Present CERN property (keys, SIM cards, ODH detectors etc)
Define actions and set deadlines
Safety and financial aspects
Administrative aspects (registration, subcontractors, etc.)
Review main aspects of the contract
Check coherence between the implementation plan and the evaluation questionnaire (ex.: human and material resources)
Draft minutes

## Slide 9: Implementation phase (1)
Organise regular progress meetings (weekly or bi-monthly) to follow the actions decided during the kick-off meeting
Registration and access to the contractor’s personnel (PRT2)
Access to CERN’s buildings (EDH-Adams)
Distribution of CERN property (with inventory, if applicable)

## Slide 10: Implementation phase (2)
Prevention Plan (PP)
Joint inspection visit (VIC)

## Slide 11: Implementation phase (3)
Explain VAT applicable rules:
  Services performed in FR: invoice including French VAT in EUR;
  Services performed in CH: invoice without Swiss VAT (subject to A/OI exemption form, issued by the procurement service)
This requires that:
  the contractor tracks services performed in FR vs CH;
  Issues two separate invoices.

## Slide 12
CONTRACT EXECUTION

## Slide 13: Contract start (T0+6 months)
Check that
All deliverables (QAP, report templates, etc.) are provided and reviewed according to contract provisions
All actions agreed are implemented (number and qualification of resources, organization chart, etc.)

## Slide 14: Follow-up meetings
2 types (different participants)
Operational meetings
Contractual meetings
(with procurement officer)
Safety
Ongoing activities
Schedule
Quality of service
etc.
Volume of work
Organization chart
Safety issues
Non-conformities, PAL, KPI
Contractual issues
etc.
 The technical officer, not the contractor, shall draft the minutes of meeting

## Slide 15: Performance of services
Information provided for
Small work contracts
Maintenance contracts
Contracts remunerated on a lump sum basis or time spent
QA
KPI/ SLA follow-up
Management of non-conformities and application of penalties

## Slide 16: Small works contracts
Notes: :
QA:

## Slide 17: Small works contracts
Notes: :
QA:

## Slide 18: Maintenance contracts (preventive)
Notes: :
QA:

## Slide 19: Maintenance contracts (corrective)
Notes: :
QA:

## Slide 20: Lump-sum or Time-spent based contracts
Notes: :
QA:

## Slide 21: Correspondence
Keep all records in writing. Documents non-conformities via a NC registry.
The ‘Ordre de Service’ (OS) should include a provision such as:
“You are kindly requested to return to CERN a signed copy of the present Service Order within five working days of its reception. Without any response from you within this deadline, the Service Order will be considered accepted.”

## Slide 22: Administrative follow-up
Approval of a subcontractor
Registration and access authorizations
Work outside normal working hours

## Slide 23: Safety coordination
 It is the responsibility of the technical officer to inform the contractor of the risks or hazards related to the performance of the services under the contract.
PP and its update
Declaration of incidents
VIC(s)
Notes:   VIC

## Slide 24: Day-to-day issue settlement
Up to the technical officer;
The procurement officer shall be informed as soon as the performance of the contract is threatened.
  Ex: Services not compliant with contractual requirements

## Slide 25: Dispute settlement
Inform the procurement officer asap:
  document all non-conformities
And together, assess the situation:
  Collect documentation;
  Identify options;
  Prepare negotiations;
  Review termination.
Meetings with the contractor;
Penalties;
Letter of notice;
Decide whether to continue or terminate the contract (withdrawal of bank guarantee?).

## Slide 26: Amendments
Will be needed for the:
  Renewal of a contract
  Any contractual change (name of contractor, prices, scope, etc). Please inform the procurement service before committing to the contractor.

## Slide 27
END OF CONTRACT

## Slide 28: End of contract
Termination
Expiry
Termination may be due to:
Breach
Gross negligence
Willful misconduct
Convenience, etc.
  Inventories of CERN’s assets (spare parts, access cards, keys, vehicles, etc.)
  Date initially foreseen
Notes: Expiry of the contract at the date initially foreseen. Actions remaining:
  Inventories of CERN’s assets (spare parts, access cards, keys, vehicles, etc.)

## Slide 29
BEHAVIOURAL TIPS

## Slide 30: Behavioural tips (1)
1
2
3
4
5
6
Comply with CERN’s Integrity Policy,
including CERN’s Code of Conduct
Read, understand and acquire full
knowledge of your contract
Use templates wherever they exist
Defend CERN’ interests
Keep track of all records, do not
make oral commitments
Clearly define the roles and responsibilities of CERN personnel in charge of the follow-up of the contract

## Slide 31
Behavioural tips (2)
7
Set the relationship with the contractor up for success
Show the example: be prompt, stick to the time frames, be meticulous with paperwork
Be fair and impartial
Be constructive and pragmatic
Distinguish facts and opinions
Trust and verify

## Slide 32: Behavioural tips (3)
Be respected, but not feared, by the contractor
8
9
10
11
12
13
14
15
Learn and share
Be aware of the evolution of applicable law, rules and regulations
Protect ‘commercial-in-confidence’ information
Expect and manage change
Be aware of matters and risks related to “délit de marchandage”
Do not negotiate on your own, inform procurement service as soon as any dispute arises
Contact the procurement officer for any question related to contractual and commercial matters

## Slide 33
Integrity and ethics codes at CERN
Reference document | Applicable to | Referred to in
CERN Code of Conduct | CERN contributors: ”members of the personnel, consultants, contractors working on the site, or people engaged in any other capacity at or on behalf of CERN” | HR’s website WOCS Procurement's website (Key reference documents) Purchase orders
CERN Code of Professional Ethics | “Anyone involved in procurement for CERN” | Procurement's website (CERN personnel) WOCS
CERN Conflict of Interest Policy and Anti-fraud Policy | CERN contributors | CERN Code of professional ethics Procurement's website (Key reference documents)
Guidelines for the implementation of the Conflict of Interest policy | CERN contributors | CERN Conflict of Interest Policy and Anti-fraud Policy
CERN Supplier Code of Conduct | CERN Suppliers (whether on site or not) | Procurement's website (Key reference documents) Tender Forms (done) Purchase Orders (done) WOCS (being updated) General Conditions of CERN Contracts (will be updated asap)
New

## Slide 34: CERN Code of Conduct

## Slide 35: Code of Professional Ethics - Key Principles
Never engage in improper conduct
Avoid any behaviour that could be perceived as unethical or illegal. Never use authority or position for personal gain.
Reject inducements or gifts
Do not accept gifts, favours, or other inducements that may influence or appear to influence your decision making.
Maintain confidentiality
Keep sensitive information private. Do not share details about contracts or procurement processes.
Avoid conflicts of interests
Disclose any potential conflict of interest with suppliers or contractors.
Follow procurement rules
Adhere to all procurement policies and procedures

## Slide 36: Gift policy
“ You should neither offer nor accept gifts, favours or hospitality. This applies equally to your family and friends, as well as any individual or organisation with which you are directly or indirectly connected. Examples include:
1
2
3
4
5
6
7
cash gifts of any amount;
travel and/or accommodation paid directly or indirectly;
invitations to sporting, cultural or social events;
a special entitlement given for private use;
recurrent invitations for meals or even a single invitation for a meal that could be perceived as excessive or unreasonable;
recruitment of a family member as a personal favour;
any items, including advertising and promotional items, the market value of which typically exceeds 30 CHF.”

## Slide 37: Ethics – conflict of interests
“Conflict of interest arises when the impartiality and objectivity of CERN contributors in the performance of their functions for CERN or in the fulfilment of their contractual obligations towards the Organization could be influenced or compromised by their private interests or any other professional obligations or relationships. […] In particular, CERN contributors are required:
1
2
3
not to accept gifts, favours or hospitality that could create or appear to create a situation of conflict of interest;
to discuss the matter with their relevant hierarchy at CERN if they are unsure as to whether a conflict of interest might exist.”
to provide immediate notification to CERN if, in the performance of their functions, they are called upon to advise on, to decide on or to control matters in which they have a private interest or competing professional obligation or relationship which could impair or appear to impair their impartiality and objectivity;

## Slide 38
CERN Supplier Code of Conduct
New
Available in Documents: Key Reference Documents | Procurement and Industrial Services Group (cern.ch)

## Slide 39
RACI MATRIX WEB PAGE