## Slide 1: Coil Fabrication at BNL
Jesse Schmalzle - BNL
CERN-AUP Coil WG – November 16, 2022

## Slide 2: AUP Coil Fab at BNL 50 Coils (# 202-251)
Fabrication Complete | Complete
233 | Ready to be packed for shipment
234 | Ready to be packed for shipment
235 | Ready to be packed for shipment
236 | Ready to be packed for shipment
Fabrication In Progress | Complete
237 | Final Prep – next cmm & final electrical
238 | Final Prep – OL clean up and wiring complete
239 | Impreg – complete
240 | Impreg Prep – leads complete, trace install next
241 | Impreg Prep – starting lead soldering
242 | Wind/Cure – L2 winding complete, preparing for cure
243 | Wind/Cure – starting winding prep

## Slide 3: AUP Coil Fab at BNL 50 Coils (# 202-251)
Fabrication Complete – On Hold | Complete
210 | Cable damage – 2 strands broken at start of IL lead splice
226 | Heater to coil short repaired / coil re-impregnated
228 | Coil to pole NCR - Coil to NL pole segment 52V hipot 14.1µA leakage
  Recent DR:
    Coil 238 – Coil to pole connection after impregnation
      120 kOhm coil to LE pole segment.
      All other pole segments show open to coil.
      Further testing to be done after coil is removed from impreg tooling.