## Slide 1: HL-LHC cable review Close out session Wednesday 14th December 2022
Panel members
J-P. Burnet Chairman, ATS-DO
D. Bozzini Scientific secretary, TE-MPE
Y. Kadi BE-EA
P. Tropea EP-CMX

## Slide 2: Introduction
The panel would like to thank all participants for the quality of the talks, the valuable discussions.
Special thanks go to the HL-LHC project office for the organization of the review and for bringing this ‘CERN wide’ subject to the table.
HL-LHC Cables Review Close Out session – 14 December 2022

## Slide 3: Content
Responses to charge questions
Global reflections about cabling at CERN
HL-LHC Cables Review Close Out session – 14 December 2022

## Slide 4: Context
The panel identified three main domains covered by this review, namely: the cabling related to the EN-EL electrical infrastructure, the cabling of optical fibres and the de- and cabling campaigns for control cables.
The panel acknowledges the robustness of the organization and execution of works related to the EN-EL electrical infrastructure and to the cabling of fibre optics.
The panel recognizes the difficulties in the domain of decabling and cabling campaigns for control cables, mainly generated by an unstructured organization of this activity.
The dedication of the personnel makes it possible to overcome these problems, but tensions are tangible between all actors.
HL-LHC Cables Review Close Out session – 14 December 2022

## Slide 5
Q1: Is the actual policy (responsibility definitions, contract strategy, agility in planning follow-up, etc.) for the intense expected de-/& cabling campaign in RUN3/LS3 sound and securely defined?
Q1: Cabling campaign organization
HL-LHC Cables Review Close Out session – 14 December 2022

## Slide 6
The panel considers that the present organisation of the de- and cabling activities is quite unstructured. EN-EL is responsible for the installation works, EN-EL is not engaged in the completeness of the activities. SCE is taking care of the cable procurement and storage, HSE is taking care of the qualification of cables under radiations, CSTSC is taking care of the technical specification for procurement, HL project office is defining the procurement strategy, EN-ACE is making the planning… The flow of information, roles, and responsibilities is not structured and results in not being clear to an external view, as it is likely the same for any project asking for cabling services.
Despite this situation, previous projects found a way to deal with the cabling campaigns, by taking the lead in this activity for their project. Presented examples are LIU decabling by EN-ACE or East area consolidation by EN-EA.
For 2 years, WP15 is coordinating these activities not in their initial mandate. WP15 is questioning if it is the right way to proceed.
Q1: Cabling campaign organization
HL-LHC Cables Review Close Out session – 14 December 2022

## Slide 7
Based on previous experiences and without changes or clarification in responsibilities, the panel considers that the only way to go for a successful HL-LHC project is by formally taking the lead in WP15. This will require:
  Injection of the needed resources in WP15
  The nomination of an EN-EL coordinator to create a single-entry point for WP15, as it is done for WP17
Q1: Cabling campaign organization
HL-LHC Cables Review Close Out session – 14 December 2022

## Slide 8
Q2: Is the cable procurement plan fully defined? Which is the contingency present? Are the storage places identified for the different phases of the activity?
Q2: Cable procurement plan
HL-LHC Cables Review Close Out session – 14 December 2022

## Slide 9
The procurement plan was presented by the HL-LHC project office, IPT and SCE, highlighting a lack of technical leadership.
The proposed procurement plan introduces many unknowns:
  New way of specifying the cables
  Changes of standards to be applied
  New way of qualification
The new technical specification will not anymore be based on the yellow book compliance but on a new qualification process defined by HSE and CSTSC.
The panel welcomes and support these initiatives.
However the procurement schedule has no margin due to the delay between the Market Survey and the tendering.
Q2: Cable procurement plan
HL-LHC Cables Review Close Out session – 14 December 2022

## Slide 10
The panel considers critical the present procurement strategy with deliveries as from 2025 which can impact, in addition to the HL-LHC project, the whole CERN activities requiring cabling activities.
The panel recommends to revise the procurement strategy and suggests to:
  Split the procurement of general purpose cables from rad tolerant cables
  Prioritize qualification of most urgent cable needs
  Validate the qualification process by placing orders in 2024 to be able to test new products during YETS 24-25 cabling campaigns and confirm supplier’s reliability
As a long-term strategy the introduction of the new class of rad tolerant cables is welcomed by the panel, but it is considered risky on the time scale of LS3.
The storage seems not to be an issue but needs to be organized in the framework of the different projects. The flow of material shall be clarified from the reception in the SCE storage to EN-EL and to the project site areas.
Q2: Cable procurement plan
HL-LHC Cables Review Close Out session – 14 December 2022

## Slide 11
Q3: Is the cable qualification chain correctly defined and secured from the time point of view and adapted to the needs? (i.e. tests and their evaluation, reaction time, etc.).
Q3: Cable qualification
HL-LHC Cables Review Close Out session – 14 December 2022

## Slide 12
The cable qualification process was abandoned by CERN long time ago. This is quite worrying and could be explained by the absence of technical leadership in the cables life cycle.
This led to difficulties, in particular, when new suppliers were introduced: at that stage a new qualification process has been proposed, highlighting the non-compliance of some standard cables (CARE finding).
The new SSI-FS-2-1, Fire Safety And Radiation Resistance Requirements For Cables, seems incompatible with the actual market availability. A derogation process is ongoing and shall be extended to cope with the HL-LHC project needs and schedule.
Q3: Cable qualification
HL-LHC Cables Review Close Out session – 14 December 2022

## Slide 13
The new qualification process for aging, proposed by HSE (CARE), sounds interesting but only few samples have been tested. The robustness and adequacy of the process remains to be confirmed.
The availability of irradiation facilities seems limited as well as resources that can be devoted to the tests.
The qualification proposed during the market survey is introducing a very high number of qualification tests.
The panel believes that choosing such a qualification process introduces a schedule risk for the LS3 activities and suggests to reduce the total number of samples.
The panel would recommend to concentrate the effort on the general-purpose cable first, in order to validate the qualification process as well as the supplier's reliability.
Q3: Cable qualification
HL-LHC Cables Review Close Out session – 14 December 2022

## Slide 14
Q4: Are the cable integration study and its follow-up correctly defined? Which are the possible mitigation actions and options for coping with additional cable space requirements?
Q4: Cable integration
HL-LHC Cables Review Close Out session – 14 December 2022

## Slide 15
The panel considers that at this stage of the project, the cables integration is well advanced but it is suffering from late requests from equipment groups and availability of EN-EL resources.
The integration is complex with many parameters to take into account. Any change or additional request generates additional work to revise the integration with cascade effects on multiple systems and equipment to be integrated.
In the present layout, the F1 to F4 power cables are laid in the ‘’caniveau’’ and won’t be any more accessible, moreover, these cables are located in a highly irradiated area despite not being qualified for radiations. The panel considers that this layout should be revised.
Q4: Cable integration
HL-LHC Cables Review Close Out session – 14 December 2022

## Slide 16
As a mitigation action to reduce the quantity of radiation resistant and radiation hard cables, the panel would recommend:
  studying the possibility to displace some equipment from UJ to the new UR gallery. This would reduce the number of cables passing through the Inner Triplets area, and then, it may help to find space for power cables.
  Evaluate the use of cable ducts (instead of cable trays) which will allow an easy replacement of power cables.
  …
Q4: Cable integration
HL-LHC Cables Review Close Out session – 14 December 2022

## Slide 17
Q5: Is the QA/QC structure for all different phases (cables manufacturing, acceptance, installation) completely defined and ready to be put in place? Are the lessons learned from previous CERN cabling activities taken into account?
Q5: cable QA/QC
HL-LHC Cables Review Close Out session – 14 December 2022

## Slide 18
The panel acknowledge the efforts put in place by each individual stakeholder but considers that a global and coordinated Quality Assurance Plan covering the entire cabling life cycle is missing.
The procurement and reception of cables was based on the trust in the supplier's control. Problems were discovered with new suppliers and QC checks at the supplier’s premises have been introduced.
Quality controls are in place with the EN-EL installation contract. BE-EA presented an enhanced quality assurance and control process enabling an early detection of non conformities. The latter retained the attention of the panel that recommends to follow this way to harmonize and improve the QA plan.
Q5: cable QA/QC
HL-LHC Cables Review Close Out session – 14 December 2022

## Slide 19
Q6: Is the cost evaluation of the global activity (material, qualification and reception tests, installation) sound? Is the uncertainty level assumed considering the difficult market situation?
Q6: Cost evaluation
HL-LHC Cables Review Close Out session – 14 December 2022

## Slide 20
The panel considers that the cost of the de- and cabling campaigns is well-known. A new contract for the cable installation is in place which limits the uncertainties on unit costs.
The panel considers that some uncertainties remain due to the cable quantity which may evolve, and to the evolution of cables prices probably impacted by the market volatility.
The cabling integration isn’t completed yet. Additional costs are likely to come, as solutions to reduce cables exposition to radiations (examples: relocation of vacuum racks, patch-panels, rad-tol and/or rad-hard cables…).
The panel considers that the uncertainty on the budget is above 20%.
Q6: Cost evaluation
HL-LHC Cables Review Close Out session – 14 December 2022

## Slide 21
CARE project will end in 2025, but the activity should continue. Recurrent resources should be allocated for the cables qualification process at CERN level.
The panel recognises that choosing radiation tolerant cables is a comfortable solution but the experience in the injectors (PS, SPS) demonstrated that it is probably a golden plate solution.
An extra cost of 5 to 7 MCHF would be charged to the project in case of the selection of radiation tolerant cables, for the whole HL-LHC requirements. The global budget for cabling with all uncertainties, will then reach more than 20 MCHF.
The radiation aging will not affect the LHC operation up to 3000fb-1. The priorities and efforts shall focus on reducing the exposure of cables to high radiation levels by adding shielding, revising the routings, or playing on operation parameters.
If an extension of the LHC lifetime is proposed beyond 3000fb-1, CERN will have to evaluate the impact on all systems, not only HL-LHC.
Q6: Cost evaluation
HL-LHC Cables Review Close Out session – 14 December 2022

## Slide 22: Summary
HL-LHC is facing the same difficulties as other projects requesting cables.
Without organizational change, the panel recommend to WP15 to take the lead on this activity for the successful completion of HL-LHC.
Minutes of the Cable review will be available there:
  Edms: HL-LHC Cables Review
Responses to charge questions will be available there :
  Edms: HL-LHC Cables Review
Recommendations by sessions will be available there :
  Edms: HL-LHC Cables Review
However, the panel has considered, in the interest of CERN, to extend the scope of his comments to a larger domain than the specific one of the review, in the hope that these inputs may support the management in taking actions to improve this situation.
HL-LHC Cables Review Close Out session – 14 December 2022

## Slide 23: Global reflections about cabling at CERN
Since LS1, the activity of de- and cabling is known as the one limiting the scope of a long shutdown.
The questions raised by the HL-LHC project are relevant and appear to have already been faced by previous projects.
The organisation and responsibilities around cabling activities are spread over many services.
There is no clear leadership on these activities.
HL-LHC Cables Review Close Out session – 14 December 2022

## Slide 24: Global reflections about cabling at CERN
EN-EL: cable installation works
SCE: cables procurement and storage
HSE: cables qualification
SCE: cable quality control
Project offices: cable procurement strategy
Project offices: Cable integration
Project offices, EN-ACE : de-cabling campaign
Project offices, EN-ACE:
Cabling works safety
CSTSC: cable technical specification
HSE: cabling works accident
Projects or equipment groups:
Cables owners
Owners : cables life cycle
SCE, EL, owners: Quality assurance plan, GESMAR data quality
HSE: cable regulation
HL-LHC Cables Review Close Out session – 14 December 2022
Present organisation: Unstructured without technical leadership.

## Slide 25: Global reflections about cabling at CERN
Cabling Services Section, Executive mandate
The Cabling Services (CS) section is part of the Electrical Engineering Group (EN-EL) in the Engineering Department (EN) at CERN. The EN-EL-CS section provides the installation of signal cables, standardised racks and DC power cables for magnets in the accelerators and experimental areas. The section provides engineering support to the CERN users, centralises their cabling requests and organises the installation activities through external industrial-support contractors. The section additionally provides support to the EN-EL group for radiation safety related aspects when working in radiation controlled areas.
HL-LHC Cables Review Close Out session – 14 December 2022
Edms 2638901

## Slide 26: Global reflections about cabling at CERN
The panel would recommend to reinforce the leadership on cabling activities by creating a group in charge of this activity regrouping all people/activities/responsibilities around cabling and providing a service for accelerators and experiments.
With a mandate similar to the Fibre Optics.
HL-LHC Cables Review Close Out session – 14 December 2022

## Slide 27: Global reflections about cabling at CERN
Fibre Optics Section, Executive mandate
The EN-EL-FO section ensures the technical expertise in the field of fibre optics, is
responsible for the CERN optical fibre infrastructure, operates optical fibre-based
systems for radiation dose and fibre degradation monitoring in the accelerator complex,
leads the research and development in the specific domain of optical fibres for both
communication and sensing applications. The section provides expert engineering
support to the CERN users for their projects: assists in the conceptual design phase,
centralises the optical fibre cabling requests and organises the supply and installation
activities through external industrial-support contractors. The section additionally
promotes technology transfer activities and strategic collaborations in the domain of
fibre optics worldwide.
HL-LHC Cables Review Close Out session – 14 December 2022
Edms 2612677