## Overview
Group | Cables LSS1 | Advancement LSS1 [%] | Cables LSS5 | Advancement LSS5 [%] | Comments
SY-BI | 362 |  | 434 |  | Not started yet
BE-CEM | 540 | 50% | 536 | 50%
BE-GM | 236 |  | 321 |  | Anderas will give feedback ~ 12/02/203
EN-AA | 459 | 20% | 490 | 20% | Not final answer before end of February 23
EN-CV | 79 |  | 81 |  | No representative in the meeting
EN-EL | 1820 |  | 3561 |  | Nuno checking separetly.
EN-EL DC | 417 |  | 415 |  | To start
EP | 118 |  | 128 |  | Meeting will be organised by EP
HSE-RP | 33 | 50% | 43 | 50%
IT-CS | 56 |  | 68 |  | No representative in the meeting
SY-EPC | 4 |  | 3 |  | Cto be checked by Georgi and Nuno, after contact H
SY-RF | 3 |  | 3 |  | Georgi will triger a meeting
SY-STI | 229 |  | 195 |  | No representative in the meeting
TE-CRG | 352 |  | 440 |  | No representative in the meeting
TE-MPE | 536 | 75% | 550 | 75%
TE-MSC |  |  |  |  | Cables coming from TE-MPE
TE-VSC | 636 | 80% | 639 | 80%
Total: | 5880 |  | 7907