Project Overview EMI 1 Kebnekaise
SA1.3 – Release Management
Aiftimiei Doina Cristina (INFN)
EMI Release Manager
EMI All-Hands Meeting
Lund, 30 May – 1 June 2011

---
Content
12.05.2011
EMI 1 (Kebnekaise) was released
30 May - 1 June 2011
EMI All-Hands Meeting - Lund

---
Release Management process
EMI 1 Release Schedule
  - Milestones & Important dates
- EMT coordination
- Build process:
  - ETICS configurations
  - Nightly Builds
Repositories:
  - RCx repositories
Release preparation:
  - Release notes
  - Acceptance Criteria
  - Public web pages
  - Signing

---
EMI 1 Release Schedule
Deliberately aggressive schedule:
  - https://twiki.cern.ch/twiki/bin/view/EMI/EMI1Schedule
  - due to late start
  - Accumulated delays
Frequent adjustments of the schedule
  - Learning phase
- Testing & certification require more time
- RCx deployment on the EMI Testbed:
  - time consuming & limited effort
Lessons:
  - Code freeze earlier – functionality implemented earlier
  - testing & certification during JRA1 phase before hand-over to SA1

---
EMT Coordination
- https://twiki.cern.ch/twiki/bin/view/EMI/EMT
- The EMT is the Engineering Management Team and is responsible for managing the release process and the software changes. This is lead by the release manager. It is composed of:
  - Product Team leaders & represetatives.
  - QA representative
  - Security representative
  - Operation team representatives of major infrastructures (EGI, PRACE, etc)
  - Invited experts

---
Build process & Repositories
ETICS infrastructure:
  - Lot of development done in critical moments
ETICS builds:
  - Increased successful build rate:
    - Better understanding of the tool & of packaging requirements
Repositories:
  - Populated with packages from the nightly builds
  - Now manually updated
  - Automatic update will improve availability

---
Release final preparation
Production repository preparation:
  - Builds for emi_R_1_0_0_1 – locked
  - Signing – Signing Procedure
Acceptance Criteria table preparation
  - http://www.eu-emi.eu/kebnekaise-acceptance-criteria
- EMI 1 Release public area preparation
- EMI 1 rollout on the EMI testbed:
  - from the production repository
    - signed packages

---
release.xml
‘Contract’ between EMI & EGI
  - Base for software hand-over between EMI & EGI
  - What is release.xml?
  - How difficult it is?
  - Easy to have mistakes/errors
    - E.g. one certified &released component rejected
  - Validation necessary
  - Automatic creation would reduce errors

---
Thank you
Thank you
EMI is partially funded by the European Commission under Grant Agreement INFSO-RI-261611