## Slide 1: RENOVATION OF THE B60 - PRESENTATION OF THE PROJECT TO NEIGHBOURS
Z. Arenas & V. Ricodeau
04/04/2023 EDMS- 2874893

## Slide 2: Global Picture
MAIN BUILDING
SCHERRER ROAD
BUILDING B60

## Slide 3: Key Facts
Asbestos is the major hazard
Fire safety non-compliance hazard
No thermal insulation
CHARPAK ROOM
BRIDGE
Built in 1959 (Charpak room added in 1975)
Exceptional architectural value (Swiss Architect Steiger)
Unusual structure bridge-like

## Slide 4: Environmental remediation Strategy
Constraints due to asbestos contamination
  Impossible to renovate with operation of offices
  Full asbestos cleaning calls for full interior demolition
  Keep only the structural elements
Asbestos
4

## Slide 5: Rehabilitation Strategy
Project: Restore the original image of the building’s
Rehabilitation Specs
  Consideration of original architectural features
  Adding an additional level (Charpak room enlargement)
  Reconstitution of the original Attic (Sun breaker)
  Technical rooms on the roof
5

## Slide 6
Project: Restore the original image of the building’s
Project: 4 levels + Charpak + Technical rooms

## Slide 7: Nominal Schedule
Project:
  Works in building B60 : 2,5 y
  Asbestos intervention: 10 m : April – November 2023
  Design and tender: 11 m : April – December 2023
  Rehabilitation: 18 m : 2024 – mid-2025
2023
2024
2025
S1 | S2 | S1 | S2 | S1 | S2
 |  |  |  |  | Available

## Slide 8: Methodological Strategy
R+1
  Next presentations :
  Information:
  Asbestos topic – O. Prouteau
  Works-related nuisances:
  Circulation inside and outside the main building – VR
  Building containment (Asbestos related) – V. Ricodeau
  Work-related noise – V. Ricodeau
8