## Slide 1: Task 2 : optics & layout
R. De Maria

## Slide 2: Layout 1.7
Follow-up integration progress: PPS2 options, small D2 assembly internal repositioning. Timeline: Ideally new layout in engineering check by June, but status of PPS2 makes uncertain. If no decision, probably engineering check postpone.
Vacuum layout completion: WIP in vax area, crab cavities, PPS2 changes.
Follow-up layout database readiness, that is validate:
  Functional position: correct position and y-rotation (needed to determine connection side)
  Aperture model: check it does not have gaps and it does not have discontinuities
  Circuit definitions: MAD-X variable to be compatible with circuit definitions (change in optics files), filling connection side
  Sequence generation: make sure LDB generated sequence are usable in MAD-X.
Responsibility passed from WP15 to EN/ACE. As far as I know, and despite our requests, HL-LHC project have not set any timeline or requirement to EN/ACE. Timeline: I have asked to EN/ACE that ideally we should have it by June, not realistic without coordination by WP2, because EN/ACE is new to HL-LHC project and cover only a) and b) limited to non-vacuum equipment, person in charge for a, b) on vacuum equipment have other priorities. c) is in between WP2 and MCF. d) is in between WP2 and BE/CSS. Thankfully a lot of goodwill from people involved, Bruno Feral, Samy Chemli (EN/ACE), Joao Oliveira (WP15), Pascal Le Roux (BE/CSS), Eric Page (EN/VSC), make the activity move forward!

## Slide 3: Aperture model and beta* reach
Document Alignment and mechanical tolerances for HL-LHC in Point 1 and 5 (LHC-G-ES-0023) contains enough updates for a new release. Timeline: release at the same time of layout 1.7
New approach to calculate the most likely beta* reach, rather than the most pessimistic (and unlucky) in progress. Motivation: there is a large uncertainty of the beta* reach (or aperture for a given beta*) due to the stack of tolerances. Worst case scenario approach, likely to give unlikely scenario, that does not help in guiding operational scenarios development. Timeline: ideally a year ago, tentatively together with Run 4 scenarios
Follow-up tolerances: measurement on production of beam-screen should give an update on tolerance during summer
Follow-up fiducialization and magnetic measurements. Montecarlo studies show that reducing feed-downs from the quadrupoles is more effective for beta* reach that aligning the aperture. Needs to connect magnetic measurements to fiducialization frame and effectively collect and combine the data. Discussion started with WP3 and WP15.4, followed up in WGA. Timeline: uncertain.

## Slide 4: String test
First HL-LHC beam line construction.
WP2 involved in giving the exact location of the beam points and voluntary displacement. Presently working on installation drawings, presently bloked on D1.
Workflow so far:
WP2 gets the CCS coordinates of the beginning of line and computes CCS coordinates for all beam line elements in survey table to Survey team and defines voluntarily displacement according to “Accelerator and Beam Line Element Definitions with Conventions and Derivations”
Survey team asks installation drawings (which is a responsibility of the equipment owner according to “Survey guidelines and requirements for an alignment of a new accelerator component on a beam line at CERN” from the design office that marks the beam points, voluntarily displacement together equipment mechanical position of the alignment jacks.
Design office ask equipment owner about mechanical drawings and beam points. The equipment owner does not know about beam points, layout drawings show beam points in 2D only and not exactly in scale and the design office asks again WP2. The design office does not also know how to mark voluntarily displacement (sometimes <1mm in a 50 m range) and comes back to WP2.
Survey/design office to meet again tomorrow.
S
R
Start
String
D1
D1 tilted
T
NB VD is in (-R)ST frame

## Slide 5: Run 4 optics scenario
Main activity during the following month together with Yannis Angelis.
Define optics for all the steps in the pp-cycle for Run 4.
Injection | Review phase advance to be MO friendly. Optionally revise Point 4 optics (was optimized for e-lens…), 10Hz noise in Q6 Point 2 ?
Ramp and squeeze | Point 1, 5: Decide flat top βx*,βy* based on 8b+4e and 2.2 1011 to reach 2 1034, minimize beta at crab, decide ATS factors, check tcdq/tclia settings. Point 2,8 Stick with β*=10/1,5 for 2,8. Revise phase to be CRAB-TCP, MO and beam-beam friendly. Integrate new impedance-improved IR7 optics.
Lumi ramp | Decide βx*,βy* based on 8b+4e and 2.2 1011 to reach 200 pile-up. Maximise beta at crab.
Lumi levelling | Match points down to 7.5/18 cm passing through 9/18 cm. Optimize phases to be CRAB-TCP, MO, beam-beam and TCT-MKD friendly. With polarity reversal or wire!
This scenario will be used for preparing an MD program 2024-2025.