## Slide 1
MUCOL General Information
Funded by the European Union under
Grant Agreement n. 101094300

## Slide 2: General Information
Mucol start is 1 March 2023.
Reporting to EU is required twice:
  M24
  M48
This is less than with other projects (good!) but remember that it will oblige all Institutes to keep the proof of expenses for that period (e.g. receipts of travels).
Continuous reporting is however necessary:
  We announced a technical report every year
  We need to announce on the EU portal the achievement of milestones and deliverables
  We need to store on Zenodo the reports which are object of a milestone or a Deliverable.

## Slide 3: General Information
Funds:
  The first instalment will be sent to all beneficiaries today
  70% of the funds received (about 50% of total)
  Remaining 30% will be sent after the approval of the first annual report by the Governing Board at the end of the first year
  Following funds will have to wait the end of the first reporting exercise M26.

## Slide 4: Annual report
Information that will be in the report:
  Technical progress
  Milestones and Deliverables achieved
  Hiring stats
  List of publications
  Dissemination (conferences, presentations etc…)
  Public events
  Gender dimension actions

## Slide 5: Website
We have a (preliminary) website!
https://mucol.web.cern.ch/
Please have a look, provide suggestions, pictures, events to be publicised.
We will add links to publications and jobs.

## Slide 6: Data Management Plan
In three months we have to provide a data management plan
Elias and myself will coordinate it
We will contact you to make sure we do not miss anything.
We will assume all relevant reports will be published on the CERN CDS or/and Zenodo (the latter necessary for reports which are for deliverables or milestones.
You will have to help us to make sure we quote any important data you need to store somewhere (e.g. GitHub for code, EDMS or any other PLM for engineering drawings etc…).
Data have to be stored according to the FAIR principle
  Findable
  Accessible
  Interoperable
  Reusable

## Slide 7: Data Management Plan
In three months we have to provide a data management plan
Elias and myself will coordinate it
We will contact you to make sure we do not miss anything.
We will assume all relevant reports will be published on the CERN CDS or/and Zenodo (the latter necessary for reports which are for deliverables or milestones.
You will have to help us to make sure we quote any important data you need to store somewhere (e.g. GitHub for code, EDMS or any other PLM for engineering drawings etc…).
Data have to be stored according to the FAIR principle
  Findable
  Accessible
  Interoperable
  Reusable

## Slide 8: Good enough FAIR software
Findable:
Make your software easier to discover by using descriptive metadata.
Publish a citation for your software.
Add it to a community registry, if one exists.
Accessible:
Put your source code in a code repository, and deposit major versions in a preservation repository to get a DOI.
Interoperable:
Describe the functionality of your software.
Use open data formats that meet domain-relevant community standards.
Provide references to associated research objects.
Modularise your code and document design.
Reusable:
Choose a license and apply it to your software.
Document dependencies.
Ensure that others can understand and execute your code.
Academic Lecture on FAIR software

## Slide 9: Data Management Plan
Data have to be stored according to the FAIR principle
  Findable
  Accessible
  Interoperable
  Reusable
If you think this is a problem, we should discuss…

## Slide 10: Deliverables & milestones
 | Milestones | Means of Verification | Month
M1.1 | Website | Website online | 2
M1.2 | Kickoff | Indico site | 3
M1.3 | Tentative parameters | Database available | 6
M2.1 | Training material | Presentations, lectures etc… | 6
M2.2 | MDI/IR workshop | Indico Site | 13
M1.4 | Annual 1 | Indico Site | 15
M5.1 | MW pulsed magnets | Indico site | 15
M1.5 | Preliminary parameters | Database available | 18
M2.3 | DELPHES | Model published on website | 18
M5.2 | Tentative IR design | Optics files | 18
M5.3 | Prelim design of collider and pulsed synchrotron | Optics files | 19
M2.4 | Workshop on detector design with public lecture | Indico Site | 25
M5.4 | Prelim FFA design | Optics files | 25
M5.5 | Prelim Impedance budget | Dataset | 26
M1.6 | Annual 2 | Indico site | 27
M1.7 | Consolidated parameters | Database available | 30
M7.3 | Workshop on Ultra High Field Solenoids | Indico Site | 30
M8.3 | 3D design | 3D model completed & Report | 33
M1.8 | Annual 3 | Indico site | 39
M7.7 | Workshop on HFM for collider | Indico site | 42
M2.5 | Reviewed paper submitted | Article ready for submission | 48
 | Deliverables | Month
D1.1 | Data man. Plan | 5
D1.2 | Prelim report n 1 | 12
D1.3 | Preliminary report n.2 | 24
D4.1 | BDSIM | 24
D2.1 | Beam induced back | 30
D4.2 | Prelim report | 33
D7.1 | Interm. Report | 33
D1.4 | Intermediate report | 36
D2.2 | Detector performance | 36
D6.1 | Power source rep | 42
D5.1 | Collider ring | 44
D3.1 | Consolidated report | 45
D4.3 | Consolidated report | 45
D5.2 | HE complex | 45
D6.2 | RF report | 45
D7.2 | Consolidated report | 45
D1.5 | Consolidated report | 48

## Slide 11: Deliverables & milestones first year
Already achieved
  M1.1 : Website
  M1.2: kick-off meeting
To be achieved:
  D1.1 : Data Management Plan : M5 (end July)
  M1.3 : Tentative parameters : M6 (end August)
  M2.1: Training material (on detectors…) : M6 (end August)

## Slide 12: Deliverables & milestones to be prepared during first year
  D1.2 : Preliminary report (for EUSPP) : M12 (linked to funds)
  M2.2: MDI/IR workshop M13 (end April 2024)
  M1.4: first Annual Meeting: M15 (end June 2024)
  M5.1: workshop on MW pulsed magnets M15 (end June 2024)

## Slide 13: Task Leaders
We need to officially endorse the task leaders:
I prepared an excel table so that we can have all names easily.
You may use it also to give responsibility for milestones and deliverables…

## Slide 14: Technical discussion
Need to have a coherent roadmap for all the Wps
  How many people will you hire and for doing what
  What is the workplan
  How do you connect to the other WPs and to the IMCC
  How do we setup the parameters table, which spec do you need etc…

## Slide 15
Thank you
for your attention