## Slide 1: EBTS BPM and Collector installation sequence
Antti Kolehmainen EN-MME
Frantisek Sanda EN-MME
2023-04-05

## Slide 2: INTRODUCTION
Based on BI 3D model ST1564092 HEL TEST STAND INTEGRATION – PHASE 4
Installation sequence proposal for the BPM
Straigthforward collector installation
Overhead crane available for the installation

## Slide 3: INSTALLATION START
Access to the valve

## Slide 4: STEP 1
1. Install the BPM inside the double solenoid
2. Add valve side edge welded bellow on the BPM

## Slide 5: STEP 2
1. Add solenoid leaving space for flange connection
2. Bring solenoid with BPM as close to the solenoid as possible
3. Pull the bellow and connect flange on the valve

## Slide 6: STEP 3
1. Bring solenoids and BPM into final position
2. Mount edge-welded on the BPM
4. Bring BGC on the chassis, pull bellow to connect flanges
3. Bring solenoid into position

## Slide 7: STEP 4
1. Bring BGC to final position
2. Add bellows for HEL collector connection

## Slide 8: STEP 5
1. Bring the last solenoid into final position

## Slide 9: STEP 6
1. Connect the HEL collector to EBTS vacuum and bring it to the final position