## Slide 1: Algorithm-System-Hardware Co-Design for Efficient Point Cloud Processing
Achievements in the past month:
  Submitted TorchSparse++ to MICRO 2023:
    Achieved 2.9X speedup over MinkowskiEngine (from NVIDIA).
    Achieved 3.3X and 1.8X speedups over SpConv v1/v2 (from TuSimple).
  Submitted BEVFusion-R to CVPR 2023 VCAD Workshop:
    Achieved 2X speedup over the state-of-the-art CRN.
Goal for the next month:
  Present BEVFusion at ICRA 2023.
  Present FlatFormer and SparseViT at CVPR 2023.
Team at MIT: Zhijian Liu, Haotian Tang, Yujun Lin, Song Han

## Slide 2: Interpretable & Scalable Geometric Deep Learning
Team at GT&Purdue: Siqi Miao, Haoteng Yin, Jiajun Zhu, Mia Liu, Pan Li
Achievements in May:
Interpretable GDL models
  Proposed a metric (label fidelity) to measure model trustworthiness
  Tested classifier randomness and explainer randomness in interpretable methods
Scalable geometric deep learning (GDL)
  For the HEP tasks
    Low-rank transformers for HEP tasks
      Tracking, Pileup mitigation, particle flow, etc…
    Modify vanilla transformers w/ advanced kernels to approx. GNNs’ performance
      Design more expressive kernels that have low-rank forms
Plans in June:
  Further modify vanilla/low-rank transformers to approx. GNN SOTA in HEP tasks
  Organize experiments of the interpretation project to prepare paper writing

## Slide 3: Domain Adaptation on Graph Machine Learning & OOD
Team at GT&Purdue: Shikun Liu, Tianchun Li, Yongbin Feng (Fermi), Nhan Tran (Fermi), Han Zhao (UIUC), Qiang Qiu, Pan Li
OOD team: Deyu Zou, Siqi Miao, Shikun Liu, Pan Li, Shiyu Chang (UCSB)
Achievements in May:
  StruRW project
    Prepare the camera-ready version
  OOD project
    Benchmarking general baselines under different types of distribution shifts across HEP, material science datasets.
Plan in June:
  Develop fundamental methods to address graph conditional shifts

## Slide 4: Sync with Scott Hauck’s group
Students are for internship: I am in the process of catching up with the project progress.