## Slide 1: EuCARD HFM CERN meeting 22/03/2011
Task 3 : High Field Magnet
Report on the ESAC dipole review

## Slide 2: Report on the ESAC dipole review
The high field dipole design Review was hold at CEA Saclay, on January 20-21, 2011
Review committee:
Giorgio Ambrosio (Fermilab)
Shlomo Caspi (LBNL)
Pasquale Fabbricatore (INFN Genova)
Yukikazu Iwasa (MIT)
Tatsushi Nakamoto (KEK)
Lucio Rossi (CERN)

## Slide 3: Report on the ESAC dipole review
12 Presentations:
The EuCARD context Gijs de Rijk
Dipole Overview JM Rifflet
Conductor Choice Luc Oberli
Conceptual Design Attilio Milanese
Engineering Design Pierre Manil
Protection study Philippe Fazilleau
The SMC program Juan Carlos Perez
Fabrication process Maria Durante (pres P. Manil)
Validation tests Françoise Rondeaux
Cooling and heat transfers Slavek Pietrowicz
Interface with the insert Mélanie Devaux
Planning Gijs de Rijk

## Slide 4: Report on the ESAC dipole review
Is the magnet design globally credible? (1/2)
The choice of a block design with flared ends was decided during EuCARD meeting in June 2010
  Only that design was presented
  No evaluation of this choice by the committee
very little experience in the selected concept  actions to further understand the concept and make it credible :
…/…

## Slide 5: Report on the ESAC dipole review
Is the magnet design globally credible? (2/2)
  Review and analyze the past experiences, (i.e. LBNL HD2 and reassemblies).
  Experimental plan to address all possible issues : mechanical models, winding tests and practice coils
  complete 3D analysis of the proposed design (axial prestress, mechanical coupling between double pancakes and with mechanical structure, effect of winding tension)
  Take into account all deviations from ideal geometry and imperfection of various systems, to check how much the design is sensitive to tolerance, discrepancies and defects
  study of the thermo-mechanical stresses during cooldown and quench

## Slide 6: Report on the ESAC dipole review
Is the conductor design valid, what could be the open issues?
The conductor design looks valid (virgin strand tests)
Stability of cabled strands  test on extracted strands
degradation due to cabling and external stress (in particular PIT (EU))  experiments and measurements
cable significantly bigger than any other cable recently used by Nb3Sn high-field magnets
.
Start qualification as soon as possible on extracted strands to detect possible issues

## Slide 7: Report on the ESAC dipole review
What risks are seen in the assembly process?
Assembly plan is still at the conceptual level and needs more details for a thorough review.
Wind full-scale dummy (copper) coils to test tooling and procedures
Wind full-scale dummy (underperforming) nb3Sn coils to check fabrication process and conductor behaviors)
Make a mechanical instrumented model cold test
The assembly process should have features that can accommodate tolerances

## Slide 8: Report on the ESAC dipole review
Are there unaddressed issues in the fabrication process? (1/2)
Rely on SMC program (Strong coordination) to :
  Draw lessons from tests (and also CEA quadrupole)
  Develop and check the Nb3Sn technology:
    insulation and impregnation materials; splice design; coil manufacturing technology and instrumentation; assembly; and loading procedures

## Slide 9: Report on the ESAC dipole review
Are there unaddressed issues in the fabrication process? (2/2)
To be defined or taken into account:
  Insulation material and thickness: (mechanical and electrical requirements with adequate margin)
  Coil dimensions after winding (ceramic binder)
  Dimensions of reaction and impregnation cavity (how to accommodate conductor expansion?)
  Impregnation materials
  Splice design
  Quench heaters (type; location; power requirement)
  Instrumentation plan (strain gauges; voltage taps; thermometers; field sensors)

## Slide 10: Report on the ESAC dipole review
Is the quench protection for the dipole sufficient?
Decrease propagation speed (axial) and use no transverse propagation to be more conservative.
Study the case where the quench is starting from low field region when the magnet is carrying its nominal operating current
Consider protection where each coil is shunted by a resistor. (but non-uniform induced current  unbalanced forces)

## Slide 11: Report on the ESAC dipole review
Is the dipole sufficiently protected from the insert in case of quench or failure?
This analysis was not presented and should be done at a future time.

## Slide 12: Report on the ESAC dipole review
Is the schedule credible? (1/2)
The overall schedule is very aggressive and success oriented.
Need of a resource loaded planning (The committee had the impression that more resources are needed)
additional steps (dummy coils, …) may induce delays, but increase considerably the probability of success
It may be prudent to start thinking ways to secure supports and additional funds for a possible extension of the project.
Focus on FRESCA2 magnet: (skip time and resources consuming accelerator features)

## Slide 13: Report on the ESAC dipole review
Is the schedule credible? (2/2)
Actions recommend to make the schedule as credible as possible:
  Implement a resource-loaded schedule
  Involve more manpower
  Plan a series of decision points and small readiness reviews
  Speed up the conductor procurement
  Take full advantage of the work presently underway at LBNL  visit

## Slide 14: Report on the ESAC dipole review
Proposed reviews (Gijs) :
1) End April 2011: conductor progress review
2) July 2011: SMC performance review
3) July-Aug 2011: Magnet structure and assembly review
4) Oct-Novt 2011:Tooling design review
5) Dec-2011: Coil manufacturing readiness review
6) April 2012: First coil manufacturing review
7) end 2012: coil manufacturing and quality review
8) mid 2013 ?: Magnet assembly readiness review
9) End 2013 ?: First magnet test review