## Slide 1: LHC BWS Mechanics
BWS project team meeting
13/6/2023

## Slide 2: Action in progress since the last meeting
Build 2 additional Hybrid+ designs for installation in YETS23-4
  Modified bellows extremity incorporating a mini-conflat(?) and support for the cable connector
  No change to the fork/wire design
  No change(?) to the bellows design – perhaps use recovered bellows?
Work on the assumption that the Hybrids designs installed in LS2 can be considered ‘operational’ by YETS23-4
  This means we are free to choose the best locations for the new Hybrid+ instruments

## Slide 3: Fully consolidated design status
ML still not able to fully commit to working on this design
  SPS and LHC operational wire scanner issues are more urgent
  Teresa still not out of the SPS-BGI production launch, but hopes to be (~fully) available in 2 weeks
  New Quest will be Autumn 2023 earliest

## Slide 4: Fully consolidated design development tasks
SLAC-type double bellows design
Mass-optimisation for drive
45 degree design issues
Impedance design due to ‘double-sided’ fork
BAT coupled drive design
BAT development
In-vacuum position sensor development
[45 degree design issues]
[Impedance design due to ‘double-sided’ fork]
‘Optional’ common development tasks
Linear motor, either for SLAC or BAT design
Wire ‘card’ for CNT-type wires

## Slide 5: LHC BWS Mechanics
BWS project team meeting
2/5/2023

## Slide 6: Some ‘definitions’
Hybrid design
  2 instruments currently installed in the LHC
  Compatible with the LIU control system
  Using the existing support and infrastructure
  0/90 measurement configuration
  Ball screw drive and encoder
  All vacuum components (bellows, fork assemblies, feedthroughs) unchanged
Hybrid+ design
  Nothing currently installed in the LHC
  Compatible with the LIU control system
  Using the existing support and infrastructure
  0/90 measurement configuration
  Ball screw drive and encoder
  Re-design fork assemblies and feedthrough
  Magnetically coupled drive depends on ongoing development
Full Consolidated design
  Nothing currently installed in the LHC
  Compatible with the LIU control system
  New support design
  45 degree measurement configuration?
  Drive and fork position system to be decided
  Fork assembly and feedthrough to be decided
  Drive coupling (bellows/magnetic?) and (linear?) motor to be decided

## Slide 7: Current list of ‘urgent’ questions
Do we agree on the hybrid strategy that:
  We aim to consider the 2 ‘Hybrid’ instruments as available for operations by end 2023
  We aim to build and install 2 additional ‘Hybrid+’ designs, replacing 2 ‘legacy’ designs for YETS 23-4
As a strategy for the Fully consolidated design…
  We design and build a linear motor test bench
    Procure one or more linear drives to test technology
  We design and build a 45° tank
    Do we install it in the SPS, LHC in YETS23-4 or just on a test bench?
  Position sensor R&D
    Depends on magnetically or bellows coupled