## Slide 1
HL-LHC Upgrade Project
Joint KEK - CERN Committee, Dec 2023
O.Brüning, on Behalf of the HL-LHC Project

## Slide 2: Outline
HL-LHC schedule
Status of key technologies towards the HL upgrade
  Civil engineering
  Final focusing magnets for lower beta*
  Superconducting Link
  Crab Cavity System
  D1
Inner Triplet String
Ongoing (and potential future) collaborations KEK – CERN
Conclusions

## Slide 3
Run3 operation
Approval of
HL-LHC Project
EU funded HiLumi
Design Study
HL-LHC Operation
We are here
2 years until start of Long Shutdown 3
The project is ready for installation start in 2026!  endorsed by 2023 C&SR

## Slide 4: Goal of HL-LHC upgrade project
The main objective of the HL-LHC is to determine and build a hardware configuration and a set of beam parameters that will allow the LHC to reach the following targets:
Prepare machine for operation beyond 2025 and up to 2040
Devise beam parameters and operational scenarios for:
# enabling at total integrated luminosity of 3000 fb-1
# implying an integrated luminosity of 250 fb-1 per year,
# design oper. for μ ≤ 140 ( peak luminosity 5 x 1034 cm-2 s-1)
-> A challenge as well for the experiments! Operation with levelled luminosity!

## Slide 5: New interaction region layout
New insertion and final focusing magnets
  Main quadrupole magnets MQXFA (Q1, Q3) from AUP and MQXFB (Q2) from CERN
  Superconducting separation and recombination dipoles, D1 from Japan and D2 from Italy
  Higher Order Corrector package (CP) and orbit correctors (MCBX) from Italy and Spain
LHC
HL-LHC
ATLAS
CMS
ATLAS
CMS

## Slide 6: International Collaboration
SC Links
D1
DFX
CP
Q3
Q2b
Q2a
Q1
Service gallery (UR)
Connection to LHC (UL)
TAXS
DFM
DFHM
DFHX
QHPS
Overall reduction of in-kind contributions from ca. 129 MCHF to 93.6MCHF with cancellation of Russian agreements
HEL & Dilution Kicker descoped from HL-LHC project
Currently pursuing additional contributions with Japan for QHPS and Crab-Cavity powering system - both are well advanced!

## Slide 7: The MS region with in-kind contributions
Crab cavities
D2
Collimators
TAXN
Service cavern
UA gallery
Q4
(BBLR)
CC Powering System

## Slide 8
Technology
Landmarks
Separation / Recombination
dipole magnets: D1 & D2
Finished in 2023
Finished in 2023
Successfully deployed in 2023 Pb-Pb run
½ system already installed for Run3
Series production in Industry well underway
Complete Prototype System installed in SM18 and under testing
Fully validated in 2023 and first magnets ready for installation
Prototype and first series delivered to CERN
Prototype cryostated @ CERN

## Slide 9: Outline
HL-LHC Schedule
Status of key technologies towards the HL upgrade
  Civil engineering
  Final focusing magnets for lower beta*
  Superconducting Link
  Crab Cavity System
  D1
Inner Triplet String
Ongoing (and potential future) collaborations KEK – CERN
Conclusions

## Slide 10: Ceremony for completion of CE on January 20th 2023
Notes: To be updated with latest plans for Ceremony

## Slide 11: Completion of Surface buildings in 2023
SF17
SHM17
SD17
SE17
SU17
Example Point 1
20th January 2023
Celebration Ceremony: Point 5
Work Ended Spring 2023

## Slide 12: Lift Installation in Pt1 and Pt5
    PM17 issue resolved thanks to help of many CERN teams (EN-ACE, SCE, HSE WP17,…)
25/01/2023
concrete spalling
30/01-03/02/2023
Inspection
30/06/2023
Closure of NC
Impact on Schedule minimized by swapping start of Lift Installation from Pt1 to Pt5
But overall ca. 6 month lost for installation of technical infrastructure
Not critical  Completion of Technical Infrastructure installation before start of LS3

## Slide 13: Status MQXFB – Q2 - Assemblies at CERN
MQXFBP1: test at CERN in 2020
  Failed to reach nominal current @ 1.9K But:
    Reached 6.4TeV equivalent without Quench; limitation only in one coil, all concepts validated @ 15.15kA
     Plan to exchange the limiting coil  procedure test for 4+1  MQXFBMT4 July 2023 ✓
    MQXFBP2: test at CERN in 2021
        Limited at around nominal current and eventually reached nominal current at 1.9K at lower ramp rates
         review of assembly  3 Phase Improvement plan
        1) Stainless Steel prestress; 2) Assembly procedure of Cold-Mass; 3) Coil production
MQXFBP3: test at CERN in 2022 – Lower shell pre-stress  1) but after disassembling 01
  Nominal +300A @ 1.9K and 3 TC ✓
  Still limited at 4.5K  but compatible with powering at ultimate current at 1.9K
MQXFB02 test at CERN in 2023 – 1) plus New Magnet Assembly procedure  1) & 2)
  nominal +300A @ 1.9K and 3 TC ✓ Still limited at 4.5K but compatible with ultimate at 1.9K!
MQXFB03 test at CERN in 2023 – New coil production  1) & 2) & 3)
  Nominal + 300A @ 1.9K and 4.5K and after TC!  Full validation of magnet concept!
13
Decision to use P2 and P3 for the IT-String even though they are limited @ 4.5K
Re-cryostating of the cold-masses in final cryostat configuration
P2 already in final configuration in SM18 on the test bench!
Lost one coil during preparation for cold-test in final cryostat configuration
 Plan to exchange the damaged coil and keep 02 as a spare
First Magnet that will go into the machine!
Magnets produced  None showing degradation!
3 [last 3] consecutive Magnets passed acceptance criterial!!!

## Slide 14: Status MQXFA – Q1 & Q3- Assemblies at AUP
8 out of 20 magnets build, tested and validated!
From 15 that were produced – 3 during COVID  all non-conformed being repaired  2 repaired validated
MQXFA08b & MQXFA14b repaired and validating coil replacement procedure and coil production planning
Endurance test on MQXFA05: 50 quenches, 5 TC  magnet remains @ nominal! ✓
Unscheduled mechanical robustness test for MQXFA11  road accident ✓
Magnet passed acceptance criteria at vertical test station ✓
CA-01: First cold mass reaching nominal performance – no retraining after thermal cycle
Nonconformities but accepted in close collaboration with AUP to assure in-time delivery for IT-String
 Shipped in November  Arrived @ CERN in December [acceptable for IT-String, not yet for machine]
Cabling completed: https://newscenter.lbl.gov/2023/08/30/cabling-for-lhc-upgrade-wraps-up/
Second Cold-Mass Assembly being prepared for testing at FNAL  second out of 10 CMA
STATUS
CA01 Leaving FNAL October 30th 2023
CA01 Arriving @ CERN November 28th 2023

## Slide 15: 1st CERN-DQW Series, Qualified
3rd test beyond the specification with additional chemistry of HOMs & deg vacuum bake

## Slide 16: Industrial DQW Series (RI)
1st pre-series jacketed cavity with excellent results, metrology to be finalized before acceptance
2nd cavity in metrology and cold tests soon

## Slide 17: RFD Cold Mass Assembly – UK1 Collaboration
Lowering of Top plate to Cavity String successful !!
Since last PSM (July), important alignment issue between top plate and cavity string corrected with some non-conformities (not ideal but ok)
Delivered to CERN in time in October for installation deadline in the SPS Test-facility!
But unfortunately observed major Nonconformities following reception tests @ CERN
Electrical Short of coupler to ground / housing & vacuum leak
Will NOT be installed in the SPS in YETS 23 / 24
But important lessons learned for series production with UK and AUP / TRIUMF!!!!!!

## Slide 18: Cold Powering System
D2
DSHM
DFHM
Q1
Q2A
Q2B
Q3
CP
D1
DCM
DFM
DFX
DSHX
DFHX
140 m
89.5 m
Power converters: (18, 7, 2) kA
Power converters: (18, 0.6) kA
Power converters: (60, 120, 200) A

## Slide 19: MgB2 Superconductor and Superconducting link
Cable production complete !
Assembly of the first complete
system incl. flexible cryostats
is ongoing
Demo-3 in SM18
Successfully Demonstrated
Concept between 2020 / 22
with > 120kA @ 30K
19

## Slide 20
SC-Link-DFHX assembly in pictures
Complete System Test planned for End 2023 in SM18

## Slide 21: Collaborations: D1
D1 prototype completed cryostating – tested end 2023 at CERN
MBXF1 magnet reached performance requirements (first long magnet to ultimate)
MBXF5 magnet completed and tested @ KEK; upgraded test station at KEK
Half of the coils for the production completed
STATUS
MBXFP1 in the cryostat
MBXF power tests (T. Nakamoto, M. Sugano, et al.)

## Slide 22
HL-LHC IT STRING: P5L
P5
P5L
P5R
SPS
HL-LHC
P1
P2
P3
P4
P5
P6
P7
P8

## Slide 23: HL-LHC testing facilities in SM18
SRF Section
Magnet Testbenches
Cold-powering Test Area
IT Test Area

## Slide 24: IT String Status in pictures
On top of the empty metallic structure
Under the metallic structure
PC and Energy Extraction racks installed on the metallic structure
Cryo Distribution
Q4 2024
Q2-Q4 2025
Q1’26
Q2’26
Q1’25

## Slide 25: THE IT-STRING INGREDIENTS ARE GETTING READY
Dates given in schedule change request, EDMS 2898265
  Q1: magnet cold mass being welded  Available in September 2024
  Q2a: MQXFBP3b completed  Available for Testbench Jan.  April 2024
  Q2b: MQXFBP2b completed  On SM18 Testbench  Available April 2024
  Q3: arrived at CERN December 2023  Available July 2024
  CP cryostating Phase II ongoing  Available August 2024
  D1 cryostating completed  On SM18 Testbench  Available March 2024
CP
Q2a
(in SMI2)
CP
(SMI2)
Q3
(in FNAL)
D1
(in SMI2)
Q2b
(in SM18)
Q2b
In SM18
Notes: To be updated by Ezio’s PSM presentation

## Slide 26: Outline
HL-LHC design parameters and project planning
Status of key technologies towards the HL upgrade
  Civil engineering
  Final focusing magnets for lower beta*
  Superconducting Link
  Crab Cavity System
  D1
Inner Triplet String
Ongoing (and potential future) collaborations KEK – CERN
Conclusions

## Slide 27: Other ongoing KEK collaborations/exchanges with HL
Separation/recombination dipole D1
  Prototype delivered and tested at CERN and re-assembled in its final cryostat configuration
  3 Series dipole magnets completed and validated at KEK – inclusive upgrade of the test station @ KEK
Beam Instrumentation
  Halo monitoring important for HL-era due to higher beam intensity and (likely) overpopulated tails
  Coronagraph prototype developed and installed in LHC, simulations show challenges to reach expected performance down to 5.5 sigma; Tests in the LHC Machine postponed to 2024
  Following LHC beam measurements, workshop planned by end 2024 to review results and explore eventual other options
Machine Protection
  First delivery of capacitors for QHPS received and being used for IT String units. Testing is ongoing
  New in-kind contribution of the full HL-LHC QHPS series to the HL-LHC project [630 units]
  Agreement being circulated for signature
Crab cavities
  Encouraging discussions towards potential additional in-kind contributions to HL project for IOTs and power transmission chain for CCs. CERN sent a contract proposal to KEK on the 2nd of November. Issue of invoicing to be agreed on
  MS being launched in parallel in-line with master schedule

## Slide 28: Quench Heater Power Supplies (DQHDS)
All 60 units (52 + 8) for the IT String have been manufactured with capacitors provided by KEK.
Testing of the units is ongoing.
Ready for installation in the IT String.
Series production:
The units for the tunnel will be provided as in-kind contribution from Japan under the lead of KEK (in total 630 units).
Nichicon has introduced (small) modifications in the capacitor model (new base-plate, reduced variation of capacitance [4.7 mF +20% -5 %])
20 prototype capacitors have been delivered to CERN from KEK and have been successfully validated.

## Slide 29: HPRF, Japan-CERN
The IOT technology at 400 MHz is the baseline for HL-LHC crab cavities
Recently, in kind from Japan to provide the HPRF system is in final stages of negotiations – outcome in Dec 2023. MoU addendum in draft
Schematic of one IP-side
IOT TH795 & TH1895 Trolley
Circulators & Loads
WR2300 waveguides
RF Coaxial Lines

## Slide 30: References
Technical info: https://cernbox.cern.ch/s/IZ9HucUqBj7PE3u
Specification of the HPRF: https://edms.cern.ch/document/2874821/1.0
Addendum: KR5904/SY/HL-LHC ADD #5: https://edms.cern.ch/document/2975586

## Slide 31: Conclusions
HL-LHC project has entered full series-production phase
Tunnel installation will start in 2 years from now, with IT String as very important intermediate validation milestone starting operation in Q4’24
Excellent and very pro-active collaboration with KEK, with promising discussions on further enlargement of the contributions within the HL-LHC project scope

## Slide 32
MQXFB02
D1
proto
Repaired
MB Dipole
CP
MQXFBP3
The project is on Track for installation
during LS3 starting in 2026
Available beginning of 2024
Open Access Publication
https://doi.org/10.1142/13487
ISBN: 978-981-127-894-5

## Slide 34: Outline
HL-LHC Schedule
Status of key technologies towards the HL upgrade
  Civil engineering
  Final focusing magnets for lower beta*
  Superconducting Link
  Crab Cavity System
  D1
Inner Triplet String
Ongoing (and potential future) collaborations KEK – CERN
Conclusions

## Slide 35
Re-Organisation of the HL-LHC Project Office
Departure of Beniamino di Girolamo
 Appointment of Lars Jensen as new Collaboration Officer
Request after the Cost & Schedule Review 2022 to separate Budget and Schedule Office
 Reinforcement of the Schedule monitoring & control
 Redefinition of Project Office Mandates and names
 Dedicated Schedule Officer to be appointed by the end of the year
Internal Audit of the HL-LHC project by CERN audit team
 Revision and update of ALL HL-LHC related mandates
Migration of the Project Webpages to the New SharePoint platform
https://cern.sharepoint.com/sites/HL-LHC/WP1/SitePages/Collaborations.aspx -> new Collaborations office pages
https://cern.sharepoint.com/sites/HL-LHC/ -> new project Intranet
https://cern.sharepoint.com/sites/HL-LHC/CB/ -> new HLCB site
The HL-LHC Project is in the process of
Strengthening the liaison with the CERN central support team and
Safety Units for the
LS3 Organization

## Slide 36: HL Project Management and Organsiation

## Slide 37: HL-LHC technology landmarks
HL-LHC is an accelerator upgrade project with many challenging novelties covering a broad technology spectrum
Technology intensive project!
Finished in 2023
Successfully deployed in 2023 Pb-Pb run
Finished in 2023
½ system already installed for run3
Series production in Industry well underway
Complete Prototype System installed in SM18 and under testing
Fully validated in 2023 and first magnets ready for installation

## Slide 38
UA57
US57
UR55
UL57
UPR57
PC IT
PCs IT Trims
DFX
DSHX
DFHX
CDBs
PIC,BIS
QDS
CLIQ
Warm Diodes
DCM
Q1
Q2A
Q2B
Q3
CP
D1
OC PCs
D1 PC
Cold Diodes
OC EE
DSHM
D2 PC
D2 OC EE
Cold box
CDBs
DFM
DFHM
DQHDS
D2
Q4
Q5
Q6
Valve box
D2 OC PCs
Crab
Cavities
RF Powering
UW57
TAXN
Civil Engineering work completed by end of 2022!
Cooling and Ventilation

## Slide 39: General status and progress since CSR22 – 6 –
TASK 13.6 Upgrade of Synchrotron radiation (SR) monitors
  Streak Cameras and optical hutches have been descoped as SR source not appropriate to observe beam crabbing
  Development of Beam halo monitoring is on hold waiting for the tests of the Coronagraph prototype on Beam2 in LHC
    Not possible this year due to beam availability issues in 2023 – to be done in 2024
    This also puts the development of the second SR source on hold as it is foreseen to be used for Coronagraph.
      A new design of SR extraction tanks was built and installed in LHC (B1-5L4) to check impedance / heating problems. – nothing issue observed so far
    All those activities delayed by more than one year
    on critical path ! Risk Exercise (EDMS 2922920)
    Rediscuss specifications with WP2 & WP5
    Launched the studies of alternative solutions
      i.e. beam gas ionization and wire scanner
    Additional workforce planned
    i.e. post-doc in early 2024 and Ph.D in fall 2024
    Review/Workshop later in 2024

## Slide 40: Conclusions
We report very good technical progress on many tasks with the successful validation of prototypes
Procurement and production of WP13 major items are well defined and followed-up closely.
Main risk is on overcost as we will be progressively moving into final tendering phase for most of the tasks
Beam halo monitoring is on critical path – current development on hold pending beam validation
  EVM not representing the correct situation yet – would need to restructure the WUs
  Put in place a plan to study alternative solutions
  Review / Workshop end of 2024 to monitor progress and propose solutions