## Slide 1: Status of CC cryomodules
Niklas Templeton – STFC Daresbury Laboratory
On behalf of the UK Crab Cavity collaboration
13th HL-LHC Collaboration Meeting – Vancouver (CA) – 26 Sep ‘23

## Slide 2: Status of CC cryomodules
UK involvement in HL-LHC Crab Cavities
RFD SPS Cryomodule Build
  Last 12 months
  Challenges & Lessons Learnt
DQW LHC Cryomodules
  Challenges & Continuous Improvement

## Slide 3: UK involvement in WP4 collaboration
2011
4-Rod Crab Cavity
DQW Prototype CM
DQW LHC CMs
RFD SPS CM
2025

## Slide 4: RFD SPS Cryomodule Build
Poster by Teddy Capelli

## Slide 5: Status Sep ‘23
DONE 
On Tack
NC

## Slide 6: RFD As-Built Timeline (simplified)

## Slide 7: Highlights (last 12 mo.)
Coded welding qualification & 1st CM welds – Jan ‘23

## Slide 8: Highlights (last 12 mo.)
Top Plate Equipped - Warm Mag Shield, Thermal Screen, MLI
New MLI skills!

## Slide 9: Highlights (last 12 mo.)
Bi Phase Cryoline delivered Feb ’23
18 months late
Several NCs found after delivery – some with major impact
Pressure test failure
  Rig design not fit for purpose

## Slide 10: Highlights (last 12 mo.)
Bi Phase line NC resolution
New Pressure Test Rig
  Developed & delivered in-house min timescales
  54 components
  24 unique parts
  FEA verification
He Level Ports replaced in-house
Re-qualification tests passed 

## Slide 11: Highlights (last 12 mo.)
Bi Phase, Tuner & Top Plate integration (steps 3-5)

## Slide 12: Highlights (last 12 mo.)
Cavitystring to Top Plate load transfer (step 6)

## Slide 13: Highlights (last 12 mo.)
Thermal Screen & 50K MLI (step 9)

## Slide 14: Highlights (last 12 mo.)
Lower OVC integration

## Slide 15: Highlights (last 12 mo.)
Many CERN visitors for knowledge transfer & build support:
RF
Fibre optic strain gauge
Survey & alignment
Cryo instrumentation
TIG & orbital welds
Tuner assembly
Management & load transfer oversight
Transport tooling & logistics

## Slide 16: Highlights (last 12 mo.)
Elegant solutions to incidental challenges
Faster in-house manufacturing
Vacuum & pressure test rigs & procedures
3D printed leak test tools (clamshells)
Qualification of assembly tooling & infrastructure
Organisational evolution
Notes: Cryomodule transport
Torque Calcs
Agile Project Management Principles

## Slide 17: Assembly Procedures
Based on poster logic + tooling & infrastructure
To troubleshoot & de-risk technical tasks
‘BOM kits’ can be prepped by sub-step
Extremely valuable for LHC CC Cryomodules
Includes requirements, torques & sign-off checklists for travellers

## Slide 18: Some RFD Metrics
Total Assembly Procedures = 840 pages!
Cryomodule Components: 10K (>5k unique)
Tooling drawings: 524
28 NCRs Resolved
Total build team effort <9 FTE per year!
  FT engineers & technicians + shared specialist & support staff
  *not including apprentice effort

## Slide 19: Challenges & Lessons Learnt
Integration complexity, sensitivity & design ‘teething’
Recruitment & retention
Supplier QA Management
Internal QA & EDMS/MTF management effort
Material specifications, traceability, coating & cleaning
Co-ordinating specialist support & visits

## Slide 20: UK DQW Schedule
RFD build delays impacted DQW progress
RI Cavity Delivery delays

## Slide 21: DQW Tooling & Infrastructure
(Re)design work:
Top Plate Lifting Gantry Mods 
Transfer Table 
Cavitystring tooling – nearly done
Next:
Anti-shock transport frame
Bi Phase Qualification Rig

## Slide 22: DQW Cryomodule Procurement
Beamline vac equipment - received or on-order
Cavitystring Trolley II - received
2x common string trolley tooling - on-site
OVC tender - live
Warm Mag Shield tender - live
Cryolines materials & fabrication - on-going (critical)

## Slide 23: DQW Improvements
More staffing & more experience
Infrastructure upgrades
Parts management workstation 
Build area flooring
Improved storage, workbenches & layout
Parts management
5S consultancy discussions 
ID > QC > Processing > Label + Storage
Technical sub-team
Dimensional control
Mock assembly
Managing cleaning etc.
BOM kit prep.
More info in WP4 break-out talks

## Slide 25: Shipping
Agreed with CERN to use CERN transport team and truck

## Slide 26: Shipping
Documentation is progressing well with tight coordination between AJBM + Ben Lewis (STFC Logistics) + Simon Barriere (CERN)

## Slide 27: DQW Series Build Timeline (Sep ‘22)
Start 01/04/20
Finish 15/04/27
Apr '20
Jul '20
Oct '20
Jan '21
Apr '21
Jul '21
Oct '21
Jan '22
Apr '22
Jul '22
Oct '22
Jan '23
Apr '23
Jul '23
Oct '23
Jan '24
Apr '24
Jul '24
Oct '24
Jan '25
Apr '25
Jul '25
Oct '25
Jan '26
Apr '26
Jul '26
Oct '26
Jan '27
Cryomodule UK Design Activities 01/04/20 - 14/06/23
Procurement Activities 05/09/22 - 07/03/25
11/23
CM2 General Assembly 17/11/23 - 26/04/24
CM3 General Assembly 07/10/24 - 06/02/25
25
CM4 General Assembly 17/01/25 - 03/06/25
CM5 General Assembly 07/05/25 - 26/09/25
Infrastructure Upgrade 16/03/21 - 03/10/23
RFD Pre-series Cryomodule - SM18 Testing 27/03/23 - 02/10/23
HL-LHC-UK2 WP2 Start 01/04/20
CM2 Cavity Set Received 21/08/23
CM5 Ready to Transport 24/10/25
Cryomodule UK Design Activities 01/04/20 - 14/06/23
Procurement Activities 05/09/22 - 07/03/25
CM2 Acceptance Tests
CM2 Clean Assy
CM2 General Assy
CM3 Clean Assy
CM3 General Assy
CM3 Acceptance Tests
CM4 Clean Assy
CM4 General Assy
CM4 Acceptance Tests
CM5 Clean Assy
CM5 General Assy
CM5 Acceptance Tests
Infrastructure Upgrade 16/03/21 - 03/10/23
RFD Pre-series Cryomodule - SM18 Testing 27/03/23 - 02/10/23
HL-LHC-UK2 WP2 Start 01/04/20
CM2 Cavity Set Received 21/08/23
CM5 Ready to Transport 24/10/25
Apr '20
Jul '20
Oct '20
Jan '21
Apr '21
Jul '21
Oct '21
Jan '22
Apr '22
Jul '22
Oct '22
Jan '23
Apr '23
Jul '23
Oct '23
Jan '24
Apr '24
Jul '24
Oct '24
Jan '25
Apr '25
Jul '25
Oct '25
Jan '26
Apr '26
Jul '26
Oct '26
Jan '27
Apr '20
Jul '20
Oct '20
Jan '21
Apr '21
Jul '21
Oct '21
Jan '22
Apr '22
Jul '22
Oct '22
Jan '23
Apr '23
Jul '23
Oct '23
Jan '24
Apr '24
Jul '24
Oct '24
Jan '25
Apr '25
Jul '25
Oct '25
Jan '26
Apr '26
Jul '26
Oct '26
Jan '27
Apr '20
Jul '20
Oct '20
Jan '21
Apr '21
Jul '21
Oct '21
Jan '22
Apr '22
Jul '22
Oct '22
Jan '23
Apr '23
Jul '23
Oct '23
Jan '24
Apr '24
Jul '24
Oct '24
Jan '25
Apr '25
Jul '25
Oct '25
Jan '26
Apr '26
Jul '26
Oct '26
Jan '27
Apr '20
Jul '20
Oct '20
Jan '21
Apr '21
Jul '21
Oct '21
Jan '22
Apr '22
Jul '22
Oct '22
Jan '23
Apr '23
Jul '23
Oct '23
Jan '24
Apr '24
Jul '24
Oct '24
Jan '25
Apr '25
Jul '25
Oct '25
Jan '26
Apr '26
Jul '26
Oct '26
Jan '27
Apr '20
Jul '20
Oct '20
Jan '21
Apr '21
Jul '21
Oct '21
Jan '22
Apr '22
Jul '22
Oct '22
Jan '23
Apr '23
Jul '23
Oct '23
Jan '24
Apr '24
Jul '24
Oct '24
Jan '25
Apr '25
Jul '25
Oct '25
Jan '26
Apr '26
Jul '26
Oct '26
Jan '27
Apr '20
Jul '20
Oct '20
Jan '21
Apr '21
Jul '21
Oct '21
Jan '22
Apr '22
Jul '22
Oct '22
Jan '23
Apr '23
Jul '23
Oct '23
Jan '24
Apr '24
Jul '24
Oct '24
Jan '25
Apr '25
Jul '25
Oct '25
Jan '26
Apr '26
Jul '26
Oct '26
Jan '27
Apr '20
Jul '20
Oct '20
Jan '21
Apr '21
Jul '21
Oct '21
Jan '22
Apr '22
Jul '22
Oct '22
Jan '23
Apr '23
Jul '23
Oct '23
Jan '24
Apr '24
Jul '24
Oct '24
Jan '25
Apr '25
Jul '25
Oct '25
Jan '26
Apr '26
Jul '26
Oct '26
Jan '27
Apr '20
Jul '20
Oct '20
Jan '21
Apr '21
Jul '21
Oct '21
Jan '22
Apr '22
Jul '22
Oct '22
Jan '23
Apr '23
Jul '23
Oct '23
Jan '24
Apr '24
Jul '24
Oct '24
Jan '25
Apr '25
Jul '25
Oct '25
Jan '26
Apr '26
Jul '26
Oct '26
Jan '27
Apr '20
Jul '20
Oct '20
Jan '21
Apr '21
Jul '21
Oct '21
Jan '22
Apr '22
Jul '22
Oct '22
Jan '23
Apr '23
Jul '23
Oct '23
Jan '24
Apr '24
Jul '24
Oct '24
Jan '25
Apr '25
Jul '25
Oct '25
Jan '26
Apr '26
Jul '26
Oct '26
Jan '27
Apr '20
Jul '20
Oct '20
Jan '21
Apr '21
Jul '21
Oct '21
Jan '22
Apr '22
Jul '22
Oct '22
Jan '23
Apr '23
Jul '23
Oct '23
Jan '24
Apr '24
Jul '24
Oct '24
Jan '25
Apr '25
Jul '25
Oct '25
Jan '26
Apr '26
Jul '26
Oct '26
Jan '27
Apr '20
Jul '20
Oct '20
Jan '21
Apr '21
Jul '21
Oct '21
Jan '22
Apr '22
Jul '22
Oct '22
Jan '23
Apr '23
Jul '23
Oct '23
Jan '24
Apr '24
Jul '24
Oct '24
Jan '25
Apr '25
Jul '25
Oct '25
Jan '26
Apr '26
Jul '26
Oct '26
Jan '27
Apr '20
Jul '20
Oct '20
Jan '21
Apr '21
Jul '21
Oct '21
Jan '22
Apr '22
Jul '22
Oct '22
Jan '23
Apr '23
Jul '23
Oct '23
Jan '24
Apr '24
Jul '24
Oct '24
Jan '25
Apr '25
Jul '25
Oct '25
Jan '26
Apr '26
Jul '26
Oct '26
Jan '27
Apr '20
Jul '20
Oct '20
Jan '21
Apr '21
Jul '21
Oct '21
Jan '22
Apr '22
Jul '22
Oct '22
Jan '23
Apr '23
Jul '23
Oct '23
Jan '24
Apr '24
Jul '24
Oct '24
Jan '25
Apr '25
Jul '25
Oct '25
Jan '26
Apr '26
Jul '26
Oct '26
Jan '27
Apr '20
Jul '20
Oct '20
Jan '21
Apr '21
Jul '21
Oct '21
Jan '22
Apr '22
Jul '22
Oct '22
Jan '23
Apr '23
Jul '23
Oct '23
Jan '24
Apr '24
Jul '24
Oct '24
Jan '25
Apr '25
Jul '25
Oct '25
Jan '26
Apr '26
Jul '26
Oct '26
Jan '27
Apr '20
Jul '20
Oct '20
Jan '21
Apr '21
Jul '21
Oct '21
Jan '22
Apr '22
Jul '22
Oct '22
Jan '23
Apr '23
Jul '23
Oct '23
Jan '24
Apr '24
Jul '24
Oct '24
Jan '25
Apr '25
Jul '25
Oct '25
Jan '26
Apr '26
Jul '26
Oct '26
Jan '27
Apr '20
Jul '20
Oct '20
Jan '21
Apr '21
Jul '21
Oct '21
Jan '22
Apr '22
Jul '22
Oct '22
Jan '23
Apr '23
Jul '23
Oct '23
Jan '24
Apr '24
Jul '24
Oct '24
Jan '25
Apr '25
Jul '25
Oct '25
Jan '26
Apr '26
Jul '26
Oct '26
Jan '27
Apr '20
Jul '20
Oct '20
Jan '21
Apr '21
Jul '21
Oct '21
Jan '22
Apr '22
Jul '22
Oct '22
Jan '23
Apr '23
Jul '23
Oct '23
Jan '24
Apr '24
Jul '24
Oct '24
Jan '25
Apr '25
Jul '25
Oct '25
Jan '26
Apr '26
Jul '26
Oct '26
Jan '27
Apr '20
Jul '20
Oct '20
Jan '21
Apr '21
Jul '21
Oct '21
Jan '22
Apr '22
Jul '22
Oct '22
Jan '23
Apr '23
Jul '23
Oct '23
Jan '24
Apr '24
Jul '24
Oct '24
Jan '25
Apr '25
Jul '25
Oct '25
Jan '26
Apr '26
Jul '26
Oct '26
Jan '27
Apr '20
Jul '20
Oct '20
Jan '21
Apr '21
Jul '21
Oct '21
Jan '22
Apr '22
Jul '22
Oct '22
Jan '23
Apr '23
Jul '23
Oct '23
Jan '24
Apr '24
Jul '24
Oct '24
Jan '25
Apr '25
Jul '25
Oct '25
Jan '26
Apr '26
Jul '26
Oct '26
Jan '27