## Slide 1: HL-LHC Crab Cavities: DQW HOM couplers & FPC challenges
Simon Barrière, Eric Montesinos – CERN
on behalf of the WP4 manufacturing team
13th HL-LHC Collaboration Meeting – Vancouver, Canada – 27th September 2023

## Slide 2: Outline
Scope of Production
Status & Planning
Manufacturing Challenges & Highlights
Many interactions between HL-WP4 teams
A status update on ongoing productions and some fabrication highlights for:
  DQW High-Order Modes Couplers;
  RFD & DQW Fundamental Power Couplers;
  with particular focus on:

## Slide 3: Production Scope
HOM Couplers, Feedthrough & Field Antennas for all LHC-series* DQW crab cavities are being manufactured at CERN Main Workshop
HOM Couplers + Feedthroughs
x 34 units*
RF Field Antenna
x 12 units*
*quantities for 8 cavities including spares
HF-HOM Couplers
x 12 units*
Fundamental Power Couplers
x 14 + 14 units*
also for RFD series
Production kicked-off in Q4-2021:
Definition of project team, mandates & milestones
Launch of raw materials procurement
Preparation & approval of MIPs

## Slide 4: Why are these Objects a Manufacturing Challenge?
  (S)RF performance highly dependent on geometry and surface quality
    Final tolerances in few tens of millimetres after many assembly (welding!) steps
    Machined and welded RF surfaces = specific parameters
  Specific (and expensive!) materials
    Extra-pure niobium, OFE copper, titanium grade 23 (TA6V ELI), stainless steel 316LN
  Multi-Technology components with pressure joints
    ~13 technologies involved and intertwined
    Multiple activities and actors in parallel in different groups
    Advanced follow-up to fulfil HL-LHC quality standards (PED-related normative, MTF steps, traceability)

## Slide 5: From Prototypes to Series Production
Key updates:
  Easier welding configurations to ease assembly and improve precision
DQW series production built according to consolidated design thanks to prototyping at CERN: DQW SPS (2015 – 2016) & RFD SPS (2019 – 2020)
SPS-DQW HOM Coupler
LHC-DQW HOM Coupler
Hippodrome shape
Circular joint =
hook orientation issues
Cylinder-cylinder interface
Thickness variation
Fixed flange
(more titanium = higher strains)
Rotative flange
Leak checks Penetrant testing
Stress analysis
Modified design for flat interface
Easier to weld
Reduced number of components for easier assembly
  Brazed feedthrough design: stress reduction on ceramics

## Slide 6: Production Status

## Slide 7: Manufacturing and Inspection Plans
From detailed manufacturing sequences…
…To MIPs and MTF assets
Strong commitment from WP4 teams to fulfil HL-LHC quality standards
More than 120 assets to be managed in MTF!

## Slide 8: Raw Material Procurement
RRR300 Niobium
320 kg of ordered in 2021 (rods, plates, sheets)
316LN stainless steel, OFE copper
  CERN “standard” materials, no shortages expected as of today (procurement anticipated)
Titanium Grade 23
Received and available for remaining production
All raw materials available at CERN to build the DQW LHC couplers

## Slide 9: RF Field Antennas Status
Final assembly
EB weld tooling for last weld
Brazed feedthrough with RF clamp
Bulk-machined OFE copper hook welded to a “standard” 25Ω RF brazed feedthrough
2022 |  |  |  |  |  |  | 2023 |  |  |  |  |  |  |  |  |  |  |  | 2024 |  |  |  |  |  |  |  |  |  |  | 
06 | 07 | 08 | 09 | 10 | 11 | 12 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
3x
Field Antenna
5x
Field Antenna
4x
Field Antenna

## Slide 10: HF-HOM Couplers Status
X-rays µ-computed tomography
Macrograph
Metrology before final assembly
Final EB weld
  Cu-Nb transitions
    Complex joining of two heterogenous materials
    New process developed at CERN fully tested and qualified
2022 |  |  |  |  |  |  | 2023 |  |  |  |  |  |  |  |  |  |  |  | 2024 |  |  |  |  |  |  |  |  |  |  | 
06 | 07 | 08 | 09 | 10 | 11 | 12 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
3x
HF-HOM
5x
HF-HOM
4x
HF-HOM

## Slide 11: Brazed HOM Feedthrough Status
Vacuum brazing
EB weld of RF clamp
2022 |  |  |  |  |  |  | 2023 |  |  |  |  |  |  |  |  |  |  |  | 2024 |  |  |  |  |  |  |  |  |  |  | 
06 | 07 | 08 | 09 | 10 | 11 | 12 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
8x
HOM Feedthrough
6x
HOM Feedthrough
8x
HOM Feedthrough
14x
HOM Feedthrough
    Improved quality control thanks to µ-computed tomography (quality and dimensions of inner surfaces)
Rugosity measurements
    Ra 0,4
    Machining of inner volume to reduce weight as much as possible

## Slide 12: HOM Couplers
  Final EB weld to close helium vessel
    160+ fabrication steps to be managed in series production: intense intertwining of techniques
    PED requirements impose full qualification of all weld & inspection processes with full traceability down to all subcomponents

## Slide 13: HOM Couplers
2022 |  |  |  |  |  |  | 2023 |  |  |  |  |  |  |  |  |  |  |  | 2024 |  |  |  |  |  |  |  |  |  |  | 
06 | 07 | 08 | 09 | 10 | 11 | 12 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
8x
HOM Coupler
8x
HOM Coupler
10x
HOM Coupler
10x
HOM Coupler
  3D-scan of final assembly

## Slide 14: FPC Status
2022 |  |  |  |  |  |  | 2023 |  |  |  |  |  |  |  |  |  |  |  | 2024 |  |  |  |  |  |  |  |  |  |  | 
06 | 07 | 08 | 09 | 10 | 11 | 12 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
2x
DQW FPC
4x
DQW FPC
4x
DQW FPC
4x
DQW FPC
2x
RFD FPC
2x
RFD FPC
4x
RFD FPC
6x
RFD FPC
Air side
Vacuum side
100% of production complete!
Transport engineering also ongoing!
Vacuum bodies
FPC DQW antenna

## Slide 15: Master Planning
4x DQW delivered to UK
4x RFD delivered to CAN
1x DQW delivered to UK
2x RFD delivered to CAN
Effort is now on RF Lines for first modules
We put a lot of efforts to match:
RF cold testing planning @ CERN
Assembly planning @ CERN and collaborations
So far, RF ancillaries are on track!

## Slide 16: A Few Technical Highlights

## Slide 17: Machining
Machining is key to ensure optimum EB welding morphology (thickness uniformity, 3D profiles)
Recent developments for hook machining & drilling (200 mm depth in Nb!)
  Nb machined Hooks (before and after BCP)
Finishing 2nd side
Roughing 1st side
200 mm

## Slide 18: Electron Beam Welding
  EB Weld Hook to Nb Collar
Neat processes for series production of SRF ancillaries (tooling, shrinkage management)
  St. Steel jacket welding
  St. Steel jacket welding
  Full penetration weld of Nb hook to the collar
  Field Antenna EBW fixture

## Slide 19: Calibration
Final EB welds on FPC antennas induce deformation leading to hook position out of tolerance (> 0,5 mm)
Many thanks to Laurent
and Jean-Philippe!
Manual (delicate!) calibration needed to bring the hooks closer to nominal position
EBW
Precise adjustment & monitoring

## Slide 20: 3D Laser Scans
1,1 mm
0,13 mm
0,9 mm
0,16 mm
DQW FPC
RFD FPC
Calibration is followed by leak checks, visual inspection (as per required standards) and RF commissioning

## Slide 21: Lessons Learned
Many techniques intertwined: advanced coordination and follow-up daily through all processes
Fragile and high added-value components: require specific processes for clean handling and storage, especially for series production. Logistics, packaging, transport… to be tackled as soon as possible
Typical issues inherent to this kind of productions debugged and documented on the field, NCR written and checked by project when needed
Synergy between SY-RF, EN-MME and TE-VSC groups at CERN

## Slide 22: Conclusion
  We are still learning many things on-the-field during this series production phase and implementing actions to improve quality & production lead times.
  Fabrication of RF couplers & antennas at CERN for DQW series is currently on track for assembly on series cavities in coming months/years
  RF Lines will be another challenge – efforts are ongoing to conclude production for 1x DQW and 1x RFD cryomodule as soon as possible
  We stay attentive and flexible to meet the Project needs, both for CERN and collaborations activities

## Slide 23: Many thanks to all the colleagues involved in the production of such beautiful objects!
Special thanks to Thomas, Julien, Sébastien, Stefanie & Eric for the inputs

## Slide 24
Thank you!