## Slide 1: TE-VSC contribution to WP4: Vacuum aspects & procurement status EDMS 2954141
V. Baglin, G. Bregliozzi, C. Pasquino, I. Lopez Cuevas on behalf of TE-VSC contribution to WP4
13th HL-LHC Collaboration Meeting, Vancouver, Canada, 25-28th September 2023
https://indico.cern.ch/event/1293138/overview

## Slide 2: Outline
Overview
Status of the series production
Layout

## Slide 3: 1. Overview

## Slide 4: TE-VSC to WP4 contributions
What is planned to be installed:
  SPS – LSS6 : 1 X RFD – LHC type cryomodule (EYETS 2023/2024);
  LHC – LSS1 (L+R) : 4 (2 + 2) DQW cryomodules;
  LHC – LSS5 (L+R) : 4 (2 + 2) RFD cryomodules;
What is planned for production: 10 CC cryomodules
  SPS – LSS6 : 1 RFD (spare RFD);
  LHC:
    5 (4 + 1 spare) DQW;
    5 (4 + 1 spare) RFD;
UK-CERN DQW CMs
Canada-CERN RFD CMs

## Slide 5: TE-VSC to WP4 contributions
Extremity vacuum chamber LHCVMACAA_T0001
Extremity vacuum chamber LHCVMACAA_T0001
Extremity vacuum chamber LHCVMACAA_T0001
Beam screen Cold/Warm transition Long
Cavity Cold/Warm transition Long
Inter beam screen plug-in module
Inter cavities plug-in module
Beam screen Cold/Warm transition Short
Cavity Cold/Warm transition Short
Beam screen
Beam screen
Courtesy of WP4
Extremity vacuum chamber LHCVMACAA_T0001

## Slide 6: 2. Status

## Slide 7: Beam screens in non-crabbed line
RFD type is1019 mm long, DQW type is 800 mm long
Item | Needed | Spare | Produced | Comments
Beam screen | 20 | 2 | 29 | 14 DQW, 15 RFD, 4 DQW aC coated 2 RFD aC delivered to UK
BS Bellows | 20 | 2 | 9 | 63 bellows delivered by Q4 2023 (more spares for the bellows) 2 delivered to UK
RFD beam screens in CERN storage
Ongoing production

## Slide 8: Plug-In-Modules & cold to warm transitions
Item | Needed | Spare | Produced | Comments
PIM & cold to warm transitions | 60 | 6 | 21 | 63 bellows delivered by Q4 2023 (more spares for the bellows) 6 assemblies for RFD delivered to UK
PIMs and cold to warm transitions production
Ongoing production

## Slide 9: Extremity vacuum chambers
Item | Needed | Spare | Produced | Comments
Ext. Vac. Ch | 40 | 4 | 44 | 4 for RFD delivered to UK
Production completed

## Slide 10: DN80 Sector valves
Item | Needed | Spare | Produced | Comments
Sector valves | 40 | 4 | 44 | 4 for RFD delivered to UK 5 for RFD delivered to TRIUMF
Sector valves in CERN stores
Sector valves at TRIUMF
Procurement completed

## Slide 11: Standard equipment
Item | Needed | Spare | Received | Comments
Vacuum Manifold (VGP, VGR, VVR, VV) | 40 | 2 | 42 21 (LHCVTFGC0001) 21 (LHCVTFGA0001) | 4 delivered to UK
Other/Standard Equipment’s:
Rupture disks
Ion pumps
Gauges
Roughing valves
Vacuum transition
All ordered/Received
Vacuum manifold in CERN stores
LHCVTFGA0001
LHCVTFGC0001
Production / procurement completed

## Slide 12: Project & quality management
TE-VSC WP4 contributions EDMS node:
  TE-VSC production Plan
  Spending Profile
  Long Term Planning (WP4 planning)
  List of Assets
  Monthly reports
Production status for a specific item and related documentation
TE-VSC Budget follow-up
TE-VSC Production follow-up
TE-VSC Contribution to WP4 definition
TE-VSC MTF

## Slide 13: Vacuum acceptance tests
Residual gas composition.
  The RGA scan must be normalized to the highest peaks (H2 or H2O) and the RGA is considered non-conform if one of the following levels is not respected (EDMS 2779658)
    Highest gas not being H2 or H2O;
    Mass of 40 (argon) > mass 39: indication presence of air;
    Light hydrocarbon (27,29,35,37,39,41): at least 100 times lower the maximum peak;
    Masses > 50: at least 1000 times lower the maximum peak;
    Presence of mass 4 (He).

## Slide 14: 3. Layout

## Slide 15: Inter-crab vacuum sector: integration
Inter-tanks cryomodules design is at his final step
Layout already in Optic LS3 V1.7 of Layout Data Base
Engineering report will circulate soon for a final approval at the project level:
  EDMS 2045739
Optics v1.7
LSS5R
Top view
Side view

## Slide 16: inter-crab vacuum sector: components
Compact and easy installation or intervention
Support integrated in the CRAB vessel (EDMS 2899757)
Stainless steel vacuum fired
Copper Pated, NEG coated
Special RF shield for pumping and valves ports

## Slide 17: Electron cloud mitigation
NEG
NEG
NEG
aC
aC
aC
aC
No coating
No coating
Crab cavities are not expected to contribute to the e-cloud: EDMS 2663141

## Slide 18: Pressure profile in D2-Q4
Simulations of the blue beam (B1) in LSS1R as a worst-case scenario:
  LSS1: shorter inter-cavity sector
  Outgoing beam from IP having more SR radiation from the D2 dipole
Three configurations investigated:
  All extremity vacuum chambers uncoated
  Baseline: aC coating on the extremity vacuum chambers of the non-crabbed line only
  All extremity vacuum chambers aC coated
D2
Q4
TCLM
CC
CC

## Slide 19: Pressure profile in D2-Q4
Beam parameters:
  Energy: 7 TeV
  Intensity: 1.08A per beam (2748 bunches, 2.2×1011ppb)
Baseline:
  P@NCL = 2 10-10 mbar
  P@CL = 3 10-10 mbar
All aC coated:
  P@NCL = 2 10-10 mbar
  P@CL = 1.5 10-10 mbar
Full conditioned machine:
  P@NCL = 4 10-11 mbar
  P@CL = 4 10-11 mbar

## Slide 20: Thank you for your attention
Many thanks to all contributors

## Slide 21: Inputs for simulation scenarios
Intensity ramp up scenario | Fully conditioned machine scenario
Electron flux only on uncoated parts: | No e- flux (SEY < ecloud threshold)
ESD yields conditioned by a factor 10 (after scrubbing run) | No ESD
Synchrotron radiation imported from Synrad+ | Synchrotron radiation imported from Synrad+
PSD yields of materials as received | PSD yields conditioned (dose ≈1023 photons/m)
Beam parameters: Energy: 7 TeV Intensity: ≈1.08A per beam (2748 bunches, 2.2×1011ppb) | Beam parameters: Energy: 7 TeV Intensity: ≈1.08A per beam (2748 bunches, 2.2×1011ppb)
Intensity ramp up scenario | Fully conditioned machine scenario
 | No e- flux (SEY < ecloud threshold)
ESD yields conditioned by a factor 10 (after scrubbing run) | No ESD
Synchrotron radiation imported from Synrad+ | Synchrotron radiation imported from Synrad+
PSD yields of materials as received | PSD yields conditioned (dose ≈1023 photons/m)
Beam parameters: Energy: 7 TeV Intensity: ≈1.08A per beam (2748 bunches, 2.2×1011ppb) | Beam parameters: Energy: 7 TeV Intensity: ≈1.08A per beam (2748 bunches, 2.2×1011ppb)
Notes: Note that the script to extract the photon flux from synrad does a first averaging on segments of ~1m of lenght

## Slide 22: a-C coating for beam screen: Argon cleaning
Argon glow discharge surface preparation step before a-C coating
  Remove the native oxide layer
  Then build a new oxide layer with dry air to avoid presence of copper hydroxides, detrimental for the adhesion.
Beam screen
Plasma cleaning process
Insertion on special support system

## Slide 23: Plasma cleaning of cold bore
Plasma cleaning of the cold bore using O2 glow discharge.
  Generation of a plasma inside the cold bore, using a Ti wire in the centre of the cold bore as anode and grounding the cold bore, that acts as a cathode.
  O radicals and O ions are formed and clean the cold bore surface.
  The O ions acquire an energy of ~200 eV and cause some sputtering of the cold bore.
  The cleaning effect is clearly seen by comparing the spectra before and after cleaning. (the cold bore was dirty)
ONGOING:
  Finalization of a plasma cleaning process using a “remote plasma source”: the plasma is generated in a source and then injected in the cold bore -> The main advantages are the lower energy of the ions (~50 eV, practically no sputtering), and the simplicity (do not require the assembly of an anode; easier to operate).