## Slide 1: UK DQW Challenges & Schedule Discussions
Niklas Templeton – STFC Daresbury Laboratory
On behalf of the UK Crab Cavity collaboration
13th HL-LHC Collaboration Meeting – Vancouver (CA) – 27 Sep ‘23

## Slide 2: UK DQW Challenges & Schedule Discussions
Schedule
  Keys to success
Open discussion on challenges & mitigations
  Please contribute
  I don’t want to talk everyone to sleep (even more)
Comments, suggestions, questions on all UK talks

## Slide 3: UK DQW Schedule
Success Requirements
Maintain effort & output
Use experience & lessons learnt
Keep staff + more where & when need
Upskilling new technicians for parallel build management
Better suppliers & supplier management

## Slide 4: Equipment Challenges
# | CHALLENGES | TYPE | CRITICAL (/5) | MITIGATION OPTIONS | ACTION(S) | OWNER
1 | Cryoline raw materials (plates, tube, bar) | Equip. | 5 | CERN supply low vol items (t>15mm) STFC & TRIUMF share plate proc. (t<15mm) | Evaluate combined plate requirements & options | RL
2 | Equipment underspend FY23/24 | Finance | 4 | More CM Proc. info & drawings Bring forward off-shelf / short-lead items FSI? Instruments? More raw materials, rf adaptors? |  | 
5 | Parts Management (storing & locating) | Equip. | 4 | Collaboration knowledge transfer 5S consultancy Improved incoming travellers |  | 
15 | Fastener grades, mag perm, coating & venting | Equip. | 2 | Relax and/or simplify specs Procurement support |  | 

## Slide 5: Staff Challenges
# | CHALLENGES | TYPE | CRITICAL (/5) | MITIGATION OPTIONS | ACTION(S) | OWNER
7 | Retaining key staff | Staff | 4 | New pay deal DL Programme resource discussions Rewards & recognition |  | 
8 | Securing & training additional mech techs | Staff | 4 | RFD Technician knowledge transfer Technician CERN & TRIUMF knowledge transfer visits UK-CM2 placements for new staff |  | 
9 | Apprentice supervision load | Staff | 3 | Discussed with apprentice & DL management Improved Tech Man planning | Raise formally | NT
17 | Info & EDMS drawing releases | Staff | 3 | More design & manufacturing readiness reviews Improve release processes |  | 
16 | PLM usability (where used & export BOMs) | Staff | 2 | Improve usability & access Use EDMS instead CERN BOM Support |  | 
19 | Procedure bottleneck | Staff | 1 | More staff Improved & hybrid styles (detailed vs lightweight) Use CERN DQW |  | 
20 | Coded & Orbital Welding | Staff | 0 | More welding and weld eng staff |  | 

## Slide 6: Management Challenges
# | CHALLENGES | TYPE | CRITICAL (/5) | MITIGATION OPTIONS | ACTION(S) | OWNER
12 | Co-ordinating specialist resource & visits | Planning | 4 | Develop & improve DQW logic poster | Draft poster logic with CAD for discussions | EJ
6 | Storage space | Infrastr. | 3 | Build area optimisations on-site mitigation options |  | 
11 | Top plate integration strategy | Infrastr. | 3 | Design mods: gantry, floor, pushers, FPC top-hat Survey & rigging analysis |  | 
18 | In & Out manufacture processes | Infrastr. | 2 | On-board machinist |  | 

## Slide 7: QA & Technical Challenges
# | CHALLENGES | TYPE | CRITICAL (/5) | MITIGATION OPTIONS | ACTION(S) | OWNER
3 | Supplier QA | QA | 5 | Free issue materials Market surveys Large tender processes - more control More staffing |  | 
4 | Protecting bellows | Technical | 5 | Bellow guards on as much as possible (Eliminate, Reduce, Isolate, Control, Protection, Signs) |  | 
10 | Survey effort & strategy | Technical | 3 | Recruitment, upskilling, outsourcing Changing & improving strategy |  | 
13 | RF tasks | Technical | 3 | Better planning, Upskilling (UK), more staff (CERN) |  | 
14 | EDMS & MTF barriers & workload | QA | 3 | Local Instructions / Procedures, more training, resource management, outsourcing |  | 

## Slide 8: Comments, suggestions, Qs for UK
…

## Slide 9: Thank You! Questions?

## Slide 10: UK DQW Project Structure
HL-LHC-UK PM
Graeme Burt
PM Support
Anna Vikhoreva
WP Lead
Nik Templeton
Tooling & Procedure Lead
Ed Jordan
QA & Weld Lead
Carlos G
FAT Lead
Andy B-M
Design Apprentice
Dan Skae
Mech Eng
Ricardo L
YII Mech Eng
Luke C
Lead Technician
Luke Bladen
Senior Technician
Tom Hanley
Cryo Tech
Ivan S
Senior Vac Eng.
Stuart Wild
Survey & Alignment
Ryan Cash
Riggers
Welder
John Hassall
CC Sponsor
Ian Lazarus
Senior Mech Eng
James Bourne
Technician
Abigail Lee
Mech Tech Apprentices
+2 Mech Tech’s (peak)
Tech Manager
Paul Hindley
Tech Oversight
Phil Atkinson
Vac Eng.
Ollie Poyton
Outside Manufacturing (Procurement)
Vac Processing
*Does not reflect STFC pay bands. Some staff are shared between multiple projects.
In-house Manufacturing
New/Change
Leaving project
Specialist Support
Logistics

## Slide 11: Infrastructure Layout