## Slide 1: UK Crab Cavity Project Structure
Niklas Templeton – STFC Daresbury Laboratory
On behalf of the UK Crab Cavity collaboration
13th HL-LHC Collaboration Meeting – Vancouver (CA) – 26 Sep ‘23

## Slide 2: UK Crab Cavity Project Structure
Meetings & Organisation
Management Changes from RFD to DQW
Staffing Changes
Team Structure
Sub-team management
Parts Management

## Slide 3: Phase I vs Phase II Management Changes
RFD SPS
PM: Andy B-M (was Shrikant)
  Schedule, finance, status reports
Sponsor: Alan W
Technical Manager: Nik T
DQW LHC
PM (HL-LHC-UK): Graeme B
WPL: Nik T
  Schedule, finance, status reports
Sponsor: Ian L

## Slide 4: Meetings & Organisation
Meeting / Freq. / Chair / Traceability
Toolbox Meeting (1/wk) NT
  Tech Task Board
UK Project (1/2wks) NT + mins
  1 slide (2 min) updates
UK-CERN Technical (1/wk) NT
UK-CERN Project (1/2wks) NT + mins
Design sub-group (1/2wks) EJ + mins
Quality sub-group (1/2wks) CG
FAT sub-group (ad-hoc) AM
Marco 1-1 (1/2wks)
Sponsor 1-1 (1/mo.) + min
PM Board (4/yr)
UK Oversight Committee (2/yr)
CERN Steering Committee (1/yr)
MS To-do Task Planner

## Slide 5: Staffing
 |  | FTE (yrs) |  | 
 | Role | 23/24 | 24/25 | 25/26
IL | 0-Sponsor | 5% | 5% | 5%
NT | 1-WPL | 50% | 50% | 50%
NT | 2-Lead Mech Eng | 40% | 40% | 10%
EJ | 2-Mech Eng | 70% | 50% | 10%
CG | 2-QA/Mech Eng | 70% | 70% | 50%
PC | 2-Design Eng | 40% | 30% | 10%
TS | 3-RF Eng | 7% | 7% | 7%
SP | 4-Cryo Eng | 20% | 20% | 10%
AM | 4-Cryo Tech | 0% | 20% | 10%
KM | 5-Snr Vac Eng | 20% | 20% | 10%
SW | 5-Vac Eng | 15% | 30% | 10%
PA | 6-Tech Man. | 10% | 30% | 20%
PH | 6-Tech Man. | 0% | 0% | 0%
LB/TH | 6-Senior Techs | 160% | 400% | 180%
- | 6-Techs | 80% | 100% | 90%
RC | 7-Survey | 25% | 50% | 25%
 | 8-Other | 25% | 70% | 45%
 | Total | 6.4 | 9.9 | 5.4
RL | Lanc Mech Eng | 100% | 100% | 
 |  | 7.4 | 10.9 | 5.4
 |  | FTE (yrs) |  | 
 | Role | 23/24 | 24/25 | 25/26
IL | 0-Sponsor | 5% | 5% | 5%
NT | 1-WPL | 70% | 70% | 30%
EJ | 2-Lead Mech Eng | 100% | 90% | 50%
JB | 2-Mech Eng | 50% | 50% | 10%
CG | 2-QA/Mech Eng | 90% | 90% | 50%
KC/LC | 2-Design Eng | 40% | 50% | 50%
TS | 3-RF Eng | 0% | 0% | 0%
AM | 4-Cryo Eng | 60% | 60% | 50%
IS | 4-Cryo Tech | 10% | 20% | 10%
KM | 5-Snr Vac Eng | 20% | 20% | 10%
SW | 5-Vac Eng | 20% | 30% | 20%
PA | 6-Tech Man. | 10% | 10% | 10%
PH | 6-Tech Man. | 10% | 10% | 10%
LB/TH | 6-Senior Techs | 160% | 400% | 180%
TBD | 6-Techs | 80% | 100% | 90%
RC | 7-Survey | 20% | 30% | 20%
 | 8-Other | 30% | 70% | 50%
 | Total | 7.8 | 11.1 | 6.5
RL | Lanc Mech Eng | 100% | 100% | 
 |  | 8.8 | 12.1 | 6.5
Dec ‘22
Mar ‘23

## Slide 6: Change Request After RI Cavity Delays
 |  | FTE (yrs) |  | 
 | Role | 23/24 | 24/25 | 25/26
IL | 0-Sponsor | 5% | 5% | 5%
NT | 1-WPL | 70% | 70% | 30%
EJ | 2-Lead Mech Eng | 100% | 90% | 50%
JB | 2-Mech Eng | 50% | 50% | 10%
CG | 2-QA/Mech Eng | 90% | 90% | 50%
KC/LC | 2-Design Eng | 40% | 50% | 50%
TS | 3-RF Eng | 0% | 0% | 0%
AM | 4-Cryo Eng | 60% | 60% | 50%
IS | 4-Cryo Tech | 10% | 20% | 10%
KM | 5-Snr Vac Eng | 20% | 20% | 10%
SW | 5-Vac Eng | 20% | 30% | 20%
PA | 6-Tech Man. | 10% | 10% | 10%
PH | 6-Tech Man. | 10% | 10% | 10%
LB/TH | 6-Senior Techs | 160% | 400% | 180%
TBD | 6-Techs | 80% | 100% | 90%
RC | 7-Survey | 20% | 30% | 20%
 | 8-Other | 30% | 70% | 50%
 | Total | 7.8 | 11.1 | 6.5
RL | Lanc Mech Eng | 100% | 100% | 
 |  | 8.8 | 12.1 | 6.5
Mar ‘23
 |  | FTE (yrs) |  |  | 
 | Role | 23/24 | 24/25 | 25/26 | 26/27
IL | 0-Sponsor | 5% | 5% | 5% | 0%
NT | 1-WPL | 70% | 70% | 70% | 40%
EJ | 2-Lead Mech Eng | 100% | 90% | 90% | 50%
JB | 2-Mech Eng | 50% | 50% | 10% | 0%
CG | 2-QA/Mech Eng | 90% | 80% | 40% | 20%
KC/LC | 2-Design Eng | 40% | 50% | 50% | 0%
TS | 3-RF Eng | 0% | 0% | 0% | 0%
AM | 4-Cryo Eng | 60% | 50% | 40% | 20%
IS | 4-Cryo Tech | 10% | 10% | 20% | 10%
KM | 5-Snr Vac Eng | 20% | 10% | 20% | 10%
SW | 5-Vac Eng | 20% | 20% | 30% | 20%
PA | 6-Tech Man. | 10% | 10% | 10% | 0%
PH | 6-Tech Man. | 10% | 10% | 10% | 10%
LB/TH | 6-Senior Techs | 160% | 200% | 400% | 120%
AL | 6-Techs | 80% | 80% | 100% | 50%
RC | 7-Survey | 20% | 20% | 20% | 10%
 | 8-Other | 30% | 30% | 50% | 20%
 | Total | 7.8 | 7.9 | 9.7 | 3.8
RL | Lanc Mech Eng | 100% | 100% |  | 
 |  | 8.8 | 8.9 | 9.7 | 3.8
Sep ‘23

## Slide 7: UK DQW Project Structure
HL-LHC-UK PM
Graeme Burt
PM Support
Anna Vikhoreva
WP Lead
Nik Templeton
Tooling & Procedure Lead
Ed Jordan
QA & Weld Lead
Carlos G
FAT Lead
Andy B-M
Design Apprentice
Dan Skae
Mech Eng
Ricardo L
YII Mech Eng
Luke C
Lead Technician
Luke Bladen
Senior Technician
Tom Hanley
Cryo Tech
Ivan S
Senior Vac Eng.
Stuart Wild
Survey & Alignment
Ryan Cash
Riggers
Welder
John Hassall
CC Sponsor
Ian Lazarus
Senior Mech Eng
James Bourne
Technician
Abigail Lee
Mech Tech Apprentices
+2 Mech Tech’s (peak)
Tech Manager
Paul Hindley
Tech Oversight
Phil Atkinson
Vac Eng.
Ollie Poyton
Outside Manufacturing (Procurement)
Vac Processing
*Does not reflect STFC pay bands. Some staff are shared between multiple projects.
In-house Manufacturing
New/Change
Leaving project
Specialist Support
Logistics

## Slide 8: Project Management
HL-LHC-UK PM
Graeme Burt
PM Support
Anna Vikhoreva
WP Lead
Nik Templeton
Tooling & Procedure Lead
Ed Jordan
QA & Weld Lead
Carlos G
FAT Lead
Andy B-M
Design Apprentice
Dan Skae
Mech Eng
Ricardo L
YII Mech Eng
Luke C
Lead Technician
Luke Bladen
Senior Technician
Tom Hanley
Cryo Tech
Ivan S
Senior Vac Eng.
Stuart Wild
Survey & Alignment
Ryan Cash
Riggers
Welder
John Hassall
CC Sponsor
Ian Lazarus
Senior Mech Eng
James Bourne
Technician
Abigail Lee
Mech Tech Apprentices
+2 Mech Tech’s (peak)
Tech Manager
Paul Hindley
Tech Oversight
Phil Atkinson
Vac Eng.
Ollie Poyton
Outside Manufacturing (Procurement)
Vac Processing
*Does not reflect STFC pay bands. Some staff are shared between multiple projects.
In-house Manufacturing
Logistics

## Slide 9: Build Leadership
HL-LHC-UK PM
Graeme Burt
PM Support
Anna Vikhoreva
WP Lead
Nik Templeton
Tooling & Procedure Lead
Ed Jordan
QA & Weld Lead
Carlos G
FAT Lead
Andy B-M
Design Apprentice
Dan Skae
Mech Eng
Ricardo L
YII Mech Eng
Luke C
Lead Technician
Luke Bladen
Senior Technician
Tom Hanley
Cryo Tech
Ivan S
Senior Vac Eng.
Stuart Wild
Survey & Alignment
Ryan Cash
Riggers
Welder
John Hassall
CC Sponsor
Ian Lazarus
Senior Mech Eng
James Bourne
Technician
Abigail Lee
Mech Tech Apprentices
+2 Mech Tech’s (peak)
Tech Manager
Paul Hindley
Tech Oversight
Phil Atkinson
Vac Eng.
Ollie Poyton
Outside Manufacturing (Procurement)
Vac Processing
*Does not reflect STFC pay bands. Some staff are shared between multiple projects.
In-house Manufacturing
Logistics

## Slide 10: Quality Assurance (All)
HL-LHC-UK PM
Graeme Burt
PM Support
Anna Vikhoreva
WP Lead
Nik Templeton
Tooling & Procedure Lead
Ed Jordan
QA & Weld Lead
Carlos G
FAT Lead
Andy B-M
Design Apprentice
Dan Skae
Mech Eng
Ricardo L
YII Mech Eng
Luke C
Lead Technician
Luke Bladen
Senior Technician
Tom Hanley
Cryo Tech
Ivan S
Senior Vac Eng.
Stuart Wild
Survey & Alignment
Ryan Cash
Riggers
Welder
John Hassall
CC Sponsor
Ian Lazarus
Senior Mech Eng
James Bourne
Technician
Abigail Lee
Mech Tech Apprentices
+2 Mech Tech’s (peak)
Tech Manager
Paul Hindley
Tech Oversight
Phil Atkinson
Vac Eng.
Ollie Poyton
Outside Manufacturing (Procurement)
Vac Processing
*Does not reflect STFC pay bands. Some staff are shared between multiple projects.
In-house Manufacturing
Logistics

## Slide 11: Quality Management
Non-Technical Support
Ensuring EDMS & MTF requirements are met
Ensuring local ISO 9001 requirements are me:
  Awareness
  Processes & Procedures
  Competence
  Continuous Improvement
  Etc.
Driving Culture
EDMS & MTF Local Instructions ‘knowledge base’
WP Lead
Nik T
QA Lead
Carlos G
Anna Vikhoreva
Howard Cheng
Peter Bates

## Slide 12: Cryomodule Procurement
Technical Management / QA
Non-Tech. Management (Low  High Value)
Nik T
Andy B-M
Carlos
Ed J
James B
Ricardo
Peter B
Howard
Diane (OM)
Jac (OM)
Nick (OM)
UKRI Proc.
Lanc Proc.
Stu W
Large Proc. Items | Responsible
OVCs | Ricardo (+ Carlos & Nik)
Warm Mag Shields | James Bourne (+ Nik)
Cryolines | Andy & Carlos (+ Ricardo)
Thermal Screens | Nik (+ Ed)
Cavity Support Systems | Ed (+Nik)
Procurement Thresholds |  |  | 
<£2.5k Credit Card | <£10k Single Quote OK | <£115k Managed by OM | >£115k UKRI Proc.

## Slide 13: Design Management
Assembly tooling & infrastructure
Design development & review
Check & approval of drawings
Nik & Carlos available supervision, support (& design if necessary)
Discussions on-going for JB replacement
Nik T
Ed J
Carlos G
Dan Skae
Ricardo L
Luke C
James Bourne

## Slide 14: Parts Management
QC &
Processing
In / Out
Logistics
All incoming & Outgoing items managed by Carlos
All inventory & storage managed by Carlos & Luke
Abi, Luke & Tom to manage QC & processing
  Dimensions control
  Mock assembly
  Cleaning
  Degaussing
  BOM Kits
Carlos G
Luke B
Tom H
Abigail L
Storage
Mech Techs & Apprentice

## Slide 15: Parts Management Process
Processing
Incoming Acceptance
Incoming Item
Unique ID & Assy Step?
Dimension Control
Visual Inspection
Mock Assy
QA Accepted?
Cleaning
Degaussing
Pack, label & Store by CM# & Step#
NCR (concession, repair, return…)

## Slide 16: Infrastructure Layout

## Slide 17: Assembly Management
Mech Techs
Engineering Oversight
Provisional Assembly Plan
CM2: Luke, Tom, Abi
CM3: (Luke) Tom, Abi, +1
CM4: Luke, +2
CM5: Tom, Abi, (Luke)
Ed
Nik
Ryan
Riggers
Luke B
Tom H
Abi L
Apprentices
Survey & Alignment
Lifting
+2 (peak)

## Slide 18: Instrumentation, Qualification & Testing
Technician Support
Vacuum
Cryo
All on-site vacuum, pressure and cold tests as part of qualification and outgoing acceptance
Andy B-M
Ivan S
Stu W
Ollie P
Luke B
Tom H
Carlos G
Electricals
Weld Qualification
Instrumentation

## Slide 19: Closing Remarks
Lots of improvements done & planned for series
  Parts Management is greatest opportunity
Clearer roles & responsibilities with sub-team management
QA is everyone's responsibility, & ALL needed for EDMS MTF requirements to be met
More effort = more staff budget
  More than £100k is a major change request
Even if accepted, additional staffing is not guaranteed

## Slide 20: Thank You! Questions?

## Slide 21: Assembly Procedures
Based on poster logic + tooling & infrastructure
To troubleshoot & de-risk technical tasks
‘BOM kits’ can be prepped by sub-step
Extremely valuable for LHC CC Cryomodules
Includes requirements, torques & sign-off checklists for travellers

## Slide 22: UK DQW Schedule
RFD build delays impacted DQW progress
RI Cavity Delivery delays