## Slide 1: HEARTS 1st Annual Meeting: WP2 Communication
Antoine Le Gall (CERN)
6 February 2024
https://indico.cern.ch/event/1314502/

## Slide 2: Tasks & Objectives
Main objectives:
  Maximise the project’s impact on the economical, societal, commercial, industrial, technical and scientific levels.
  Dissemination of the R&D achieved within the project and about knowledge transfer to external parties.

## Slide 3: The Communication setup
Internal and external communication → Antoine Le Gall, CERN
Information flow management → Pablo Lopez, CERN
With support for:
  Website Management → Dávid Lucsányi, CERN
  External communication → Ygor Aguiar, CERN

## Slide 4: WP2: Tasks
2.1. Communication M1-M12
2.2. Dissemination and outreach M1-M48
2.3. Knowledge transfer M24-M48

## Slide 5: Communication challenges
Three related topics: radiation to electronics, radiobiology, shielding.
  Yet, different communities, different target audience, different events.
Summary of the first year:
  No big results for the moment.
  Communication on TRL increase, job offers, first meetings and events.
  Highlight at the end of the year: HEARTS@CERN Run.

## Slide 6: HEARTS Internal Communication
~60 project members from 5 partners with new tools for some:
  19 dedicated egroups for WPs, management and ad-hoc topics.
  30 HEARTS meetings via Indico.
  43 HEARTS documents on EDMS.

## Slide 7: Communication plan

## Slide 8: Dissemination & outreach / External & internal communication
Communication and Dissemination Plan created with specific strategy for the following channels:
Project website
hearts.web.cern.ch
Events Workshop, conference, nights
Mailing lists
External newsletter
Accelerating News (quarterly).
LinkedIn account
Participants channels, including social media

## Slide 9: HEARTS Website
Continuously updated since its creation in March 2022 (!).
2200 unique visits since Jan. 23.
6800 pageviews (4000 uniq.).
Around 150 monthly visits, with spikes at 230.
Comment:
  Number to increase once calls are advertised.
Notes: Compared the 40 weekly readers with already established project with much, more complete websites:
900-1000 for I.FAST, with spike at 2500.
200 for AIDAinnova, with spikes at 500.

## Slide 10: HEARTS Social Media (LinkedIn)
Dedicated communication strategy.
Some numbers:
  >265 followers.
  >1300 page views.
Comments:
  Difficulties to find content at the early stage of the project (no big updates, no call to users).
  Plans to engage more from this year (one post per month at least).

## Slide 11: Articles and social media by partners
Post sur le heavy ion run

## Slide 12: Big communication moment: CERN Heavy-Ion Run
52-minute live on all CERN channels on 2 November 2023 with representatives from all CERN experiments and HEARTS.
  YouTube:
    >260 simultaneous viewers (usually 50-100 on CERN channel)
    9,1K total views.
    >200 messages.
  LinkedIn:
    16k total views.
    >200 messages.

## Slide 13: HEARTS @ Events
HEARTS was present at:
  EUCASS-CEAS, Lausanne, CH. >100 people passing by. ~15 conversations.
  NSREC 2023, Kansas City, USA. >300 people passing by. ~30 conversations.
  RADECS 2023, Toulouse, FR. >200 people passing by. ~30-40 conversations
Communication kit
(Leaflet, roll-up, presentation, video, stickers)

## Slide 14: HEARTS @ Events
EUCASS-CEAS
NSREC
RADECS

## Slide 15: Knowledge Transfer
CERN, GSI
Support wider exploitation with connected industries (space, medical, accelerators).
Exploitation plan set to render the knowledge built with the project accessible and easier to standardise .
Two webinars to be organised with interested industrial stakeholders to present would-be technologies.

## Slide 16: Deliverables due in Y1
Deliv. No. | Deliverable name | Due date | Status | Summary
D2.1 | Communication and dissemination plan | 2023-06-30 | Achieved | Communication objectives, messages, vectors, "hooks" and timeline. Includes descriptions of channels and social media strategy.
D2.2 | Exploitation and data management plan | 2023-12-31 | Achieved | How the consortium will proceed for valorisation of key exploitable results. Description of knowledge transfer procedures.
The achieved deliverables are available on HEARTS website page:
https://hearts-project.eu/project/deliverables/

## Slide 17: Milestones due in Y1
Milest. No. | Milestone name | Due date | Status | Summary
M09 | Project website launched, with update and maintenance plan | 2023-02-28 | Achieved | /
M10 | Project social media launched | 2023-03-31 | Achieved | /
The achieved milestones are available on HEARTS website page:
https://hearts-project.eu/project/milestones/

## Slide 18: Upcoming Deliverables & Milestones
Deliv. No. | Deliverable name | Due date | Status
D2.3 | Knowledge transfer turnover report | 2025-12-31 | Pending
D2.4 | Final report on communication, dissemination, outreach and exploitation | 2026-12-31 | Pending
No upcoming milestone.

## Slide 19: Plans for the future
Actions for Y2:
  Advertise beam time (social media, webpage, dedicated leaflet).
  Give life to social media (Open calls, Valentine's Day, International Day of Human Space Flight, Europe Day, World Space Week).
  Events:
    20-21 March: EU R&I Days (usually in September!).
    22-26 July: NSREC 2024.
    16-20 September: RADECS 2024.
    Other for radiobiology and shielding?

## Slide 20
Insert Video

## Slide 22: Communication objectives for Y1
Strategy and Planning
Basics: Logo, presentation template, images.
Communication plan (messages, contacts, etc.).
Communication calendar (events, major milestones).
Social media strategy.
Communication material
Communication channels
Mailing lists, Indico, CERNbox, EDMS to set up.
Project website to design and develop.
Project LinkedIn to design and develop.
Category in Accelerating News.
Introduction video